INFORMATION                                                As of 08.09.2015

Under the Project reconstruction of International Transit Corridor Western Europe -Western China, bridge over ILI river km 283 (Lot8) “Almaty- Kokpek-Chunja-Koktal-Khorgos”

- Contract: EWRP – Ili bridge (km 283) –ICB(W)-001/2013

- General Contractor: «OHL ZS»(Czech)/Subcontractor LLP “MO-25” (Kazakhstan)

- Contract amount: 6 134 720 000 tenge (Accepted Contract Amount 6 394 053 055tenge)

- Construction period: 30 months

Commencement date: 4 October 2013

Completion date:  3 April 2016

- Developed up to 2014 year: 3 565 080 000 tenge

- Plan for 2015 year: 1 952 540 000 tenge

- Consultant Engineer: DongSung Engineering Co. Ltd/Dong Myeong Enginering Consultants and Architecture Co. Ltd./ “Zhol Sapa” LLP

- Design Company: “Kazakhstan zholdary”

- Main indicators

Total number of artificial structures: 1-bridge over Ili river

New bridge: Length: 41,96 + (7 х 85,44) + 41,96 = 682 м

Width: 14.2 m (2 lane +sidewalk)

Type of the bridge: steel box girder

Existing bridge:

Reconstruction of pavement and traffic facilities of existing bridge ILI

- Detail of Work program performance:

  - Progress

| № | Descrition | Total | Developed in 2013-2014 years | Plan for 2015 (mln tg.) | Performed according to Contract |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Plan | Performed as of today | % | Sum | % |
| 1. | Physical progress, (mln.tenge) | 5 477,37 | 2 773 | 2 682,01 | 1 886,36 | 70 | 4 659,30 | 85 |
| 2. | Monetary progress, (mln.tenge) | 6 134,652 | 3 565,80 | 1 952,54 | 1 588,32 | 81 | 5 154,13 | 84 |

*Expected Money disbursement of 2015 is 1952.54 mln tenge (100% of plan)

  - Bridge works

| № | Work description | Total | Performed in 2013-2014 | 2015 |
| --- | --- | --- | --- | --- |
|  |  |  |  | Plan | Fact | % |
| 1 | Site clearance, m2 | 100 | 50 | 0 | 50 | 50 |
| 2 | Construction of piles, m3 | 9 034 | 8 102 | 932 | 932 | 100 |
| 3 | Construction of foundations, m3 | 4 857 | 2 418 | 2 439 | 2 432 | 99 |
| 4 | Construction of the body of pier), m3 | 1 822 | 535 | 1 288 | 1 288 | 100 |
| 5 | Reinforcing | 1 363 | 696 | 305,70 | 232,73 | 76 |
| 6 | Assembly of steel superstructures, ton | 3 222 | 0 | 3 222 | 2 805 | 87 |
| 7 | Installation of handrails | 2 768 | 0 | 2 768 | 0 | 0 |
| 8 | Installation of guard rails | 2 800 | 0 | 2 800 | 0 | 0 |

- Material procurement for 2015:

| № | Description | Total | 2015 | Suppliers |
| --- | --- | --- | --- | --- |
|  |  |  | Plan | As of 08.09.2015 | % |  |
| 1. | Crushed stone m3 | 17 680 | 8 436 | 6 352 | 75 | “Dostar S” LLP |
| 2. | Sand m3 | 8 210 | 1 774 | 1 724 | 97 | “Giada” LLP |
| 3. | Sand gravel mix m3 | 14 640 | 13 026 | 11 936 | 88 | “Aluan A” LLP |
| 4. | Cement ton | 7 100 | 2 340 | 1 924 | 80 | “Standard” LLP |
| 5. | Reinforced concrete products m3 | 192 | 192 | 0 | 0 | Not defined |
| 6 | Steel superstructures | 3 222 | 3 222 | 3 222 | 100 | “Kurganstalmost” |
| 7. | Re-bar and embedded parts, ton | 1 360 | 171 | 113 | 66 | “Modul” LLP, “Evraz” |

- Staff mobilization:

| № | Description | Requirement 2015 | As of 08.09.2015 | Including: |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign | Local |
| 1 | TED | 25 | 25 | 7 | 18 |
| 2 | Laboratory | 5 | 5 | 1 | 4 |
| 3 | Survey | 2 | 2 | 0 | 2 |
| 4 | Operators | 36 | 36 | 0 | 36 |
| 5 | Truck drivers | 8 | 13 | 0 | 13 |
| 6 | Laborers | 90 | 90 | 0 | 90 |
| 7 | Service staff | 6 | 6 | 0 | 6 |
| Total | 172 | 177 | 8 | 169 |

- Equipment mobilization:

| № | Description | Requirement for 2015 | As of 08.09.2015 | OHL ZS |
| --- | --- | --- | --- | --- |
|  |  |  |  | Contractor | Subcontractor |
| 1 | Bulldozer | 2 | 2 | - | 2 |
| 2 | Excavator | 1 | 1 | - | 1 |
| 3 | Loader | 2 | 2 | - | 2 |
| 4 | Auto grader | 0 | 0 | - | 0 |
| 5 | Rollers | 2 | 1 | - | 1 |
| 6 | Dump trucks | 4 | 3 | - | 3 |
| 7 | Water truck | 1 | 1 | - | 1 |
| 8 | Asphalt paver | 0 | 0 | - | 0 |
| 9 | Crane | 5 | 3 | - | 3 |
| 10 | Cement Concrete plant | 1 | 1 | - | 1 |
| 11 | Pile driver | 1 | 0 | - | 0 |
| 12 | Creeper | 1 | 1 | - | 1 |
| 13 | Concrete mixer | 2 | 2 | - | 2 |
| 14 | Vehicle | 6 | 6 | 4 | 2 |
| 15 | Others | 16 | 20 | - | 22 |
| Total | 44 | 43 | 4 | 41 |

- Issues / INFO

- Variation Order #2 is now preparing (Steel structures coating, etc)

- Decision on rehabilitation of existing bridge might impact the Contract Amount and the completion date of Contract