Information

On “Western Europe -Western China international transit corridor reconstruction project, 
km 0-50 (Lot No.1) Almaty - Horgos

Contractor: «Dogus InsaatVeTicaretA. S» (Turkey)

Engineer: Dongsung Enginering/ DongMeng/ “Zhop-Sapa” LLP

Contract cost: 25 233 582 346.00 tenge.

Contract conclusion date: 17.07.2013

Advanced payment are received on the mobilization:  November 6, 2013

Commencement date: November 6, 2013

Disbursed in 2104 - 4 040 119 964,86 tenge.

Work plan for 2014- 5 638 970 000 tenge.

| No. | Description | Total under Contract | Plan for 2014 | Plan for August end | Plan for 06.08.2014 | Delay |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks, th.m3 | 5 373,54 | 2 507,8 | 1 218,38 | 660.57 | -557,81 |
| 2 | Sub base, km | 50 | 12 | 4 | 0 | -4 |
| 3 | Construction coarse, h-18 cm, km | 50 | 10 | 2 | 0 | -2 |
| 4 | Cement concrete pavement, km | 50 | 8 | 0 | 0 | 0 |
| 5 | Bridges and overpasses, pcs | 34 | 10 | 3,2 | 2.5 | 0,7 |
| 6 | Culverts, pcs | 120 | 65 | 35 | 42/16 | 0 |

Work of program performance:

06.08.2014

Material Stockpile:

| No. | Material stockpile | Unit | Plan for 2014 | Plan on the august end | Fact on 10.07.2014 | Equip (+,-) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone (for base) | th, m3 | 28,73 | 5,75 | 15.31 | 0 |
| 2 | Crushed stone (for cement concrete pavement) | th, m3 | 10,75 | 0 | 23,71 | 0 |
| 3 | Gravel sand mix | th, m3 | 130,89 | 43.60 | 221,5 | 0 |
| 4 | Sand | th, m3 | 26,32 | 3,83 | 0 | -3,83 |
| 5 | Reinforced Cement Products | th, m3 | 18,59 | 7,01 | 13.6 | 0 |
| 6 | Cement | th, m3 | 11,87 | 0,51 | 0.78 | 0 |
| 7 | Dowel | t. | 121,54 | 0 | 0 | 0 |
| 8 | Anchor | t. | 25,23 | 0 | 0 | 0 |

Personnel:

At this moment, number of personnel as of 06.08.2014 - 526 people, among them 47 foreigners.

Quantity of technique required for work performance for 2014:

| No. | Description | Requirements for 2014 | Fact on 06.08.14 | Among them |
| --- | --- | --- | --- | --- |
|  |  |  |  | Own | subcont/rented |
| 1 | Dozer | 4 | 9 | 4 | 5 |
| 2 | Excavator | 11 | 15 | 12 | 3 |
| 3 | Loader | 11 | 10 | 10 |  |
| 4 | Grader | 4 | 9 | 4 | 5 |
| 5 | Roller | 12 | 10 | 6 | 4 |
| 6 | Dump truck | 70 | 63 | 40 | 23 |
| 7 | Water bawser | 7 | 4 | 2 | 2 |
| 8 | Paver | 3 | 1 | 1 |  |
| 9 | Concrete pvaer | 1 | 0 | 0 |  |
| 10 | Crane | 4 | 6 | 2 | 4 |
| 11 | Cement Concrete Plant | 2 | 2 | 2 |  |
| 12 | Crushing and screening plant | 1 | 1 | 1 |  |
| 13 | Piling machine | 1 | 1 | 0 | 1 |
| 14 | Trailer | 4 | 8 | 8 |  |
| 15 | Concrete mixer | 4 | 3 | 3 |  |
| 16 | Car | 34 | 35 | 32 | 3 |
| 17 | Others | 20 | 33 | 31 | 2 |
| TOTAL | 193 | 210 | 158 | 52 |

Subcontractors:

- “Yug – Assar” LLP – relocation of communications.

- “Otau Kurylys” LLP – relocation of power transmission line and lighting.

- “NikStroyMost” LLP – under engineering structures (bridges and culverts). PK280-PK330

- “KSZh Stroy” LLP – under earthworks and engineering structures at the section PK350-PK450

- “Danuras” LLP - under earthworks and engineering structures at the section PK100-PK200.

- “AtlantStroyService” LLP - under earthworks and engineering structures (not mobilized).

- “Vostokavtodor” JSC - under earthworks and engineering structures (not mobilized).

Subcontractors under supply:

- “AZMK” LLP – under supply of Reinforced Cement Products (Beam, span slab, culverts)

- “Kapshagai Kurylys” LLP – under supply of piles.

-ТОО «LC1 - МК» - under supply of Reinforced Cement Products (Piles and culverts)

Issues of concern:

- Premise on km 5 +770 (The land plot is not acquired for permanent works)

- Lack of technique and personnel at the section, low work progress under backfill of embankment due to few quantity of dump trucks.

- Low attraction of new subcontractors to construction approved by Engineers.

- Work delay due to low temp of test piling.

Reference:

Contractor carried out site clearance, technological passage construction for transport and is working under erection of embankment at the sections from km15+400 to km19+800, km 50 - km 42 and km 28- km 37+00.

At the section km 48+400 to 48+750 (350 m) Contractor prepared working base of filling and handed-over to Engineer.

At the section km 31+980 to 32+200 (220m) Contractor prepared working base of successive section to hand over.

Contractor will finish work base construction at the section km 49+500 to km48+000 (1500 m) by August 15, 2014.

Therefore, Contractor can proceed to sub base construction in August.

Pavers Wirtgen Wirtgen 1200 and Wirtgen 500 arrived at the Contractor base in July of this year in the installation and commissioning of which service team is currently working.

Contractor constructed the sample area (50m), where it constructed sub base and SCSCM coarse.

Contractor during work process, because of excessive swamp area at the section, has to construct drainage chutes, to carry out additional excavation of unsuitable soil and drying of soil foundation in order to receice stable base of subgrade, and to carry out backfill of swamp areas by stone materials from Turgen borrow pit (quarry).

Delivery of reinfoced concrete construction for artificial structures, mobilization of road building techniques and vehicle for agrregate transportation is continuing.

Culverts information:

42 culverts are being constructed, among them all parts are assembled and waterproofing held on 16 culverts.

Bridges information:

Work is being carried on 8 bridges.

- PK 499+00- as of 0б.08.2014 abutment performed to 100%. Work in progress under slope protection and erection of beams.

- PK 324+80 –Piles are driven to 100 %.  Abutment static test was carried out and works under construction of abutment caps are going on.

- PK333+56 - Piles driven to 100 %.

- PK 341+85 – Piles driven to 70 %. Work performed under piles driving.

- PK464+60 - Piles driven to 100 %.

- PK287+ 78 – Piles driven to 100 %.

- PK 281+41 –Piles driven to 100 %.

- PK 306+60 - 2 and 3 supporting structures are performed to 100%, Work is being performed under reinforcement of supporting structure cap No. 1 and abutment of canting No.4.