Information

about implementation of section km 0-50 of «Almaty-Khorgos» road of

«Western Europe – Western China» project in Almaty oblast by

the Contractor JV «Dogus Insaat &Gulsan Isaat Sanayi Turizm», Lot-1

Contractor: JV «Dogus Insaat &Gulsan Isaat Sanayi Turizm»

Contract: EWRP-0-50-ICB(W)-001/2013

Contract cocnluded: 17.07.2013

Construction period: November 2013 – 2016

Contract amount of the Contractor: 25 233 582 346,00 KZT

Disbursed in 2013, 2014: 7 277 764 588,53 KZT

Disbursement in 2015: 1 201 687 888,18 KZT

Disbursement plan for 2015: 7 675 180 000 KZT

Engineer: Dongsung Engineering/Dongmeyong/Zhol-Sapa

Designer : LLP KazNIiIPI «Dortrans»

- Project Data

| Length, km | 50 |
| --- | --- |
| Culverts, pcs. | 120 |
| Bridges and cattle passes, pcs | 30 |
| Overpasses, pcs | 1 |
| Transport interchanges, pcs | 3 |
| Earthworks, th.m3 | 5 282,3 |
| Subbase, km/th.m3 | 50/718,41 |
| Base course, km/th.m3 | 50/263,43 |
| Cement concrete pavement, km/th.m3 | 50/275,84 |

2. Main works

| № | Description | Total as per contract | Plаn for 2015. | Actual for 2015 | Performed from beginning of project |
| --- | --- | --- | --- | --- | --- |
| 1 | Earthworks (thous.m3) | 5 282,3 | 2753,07 | 442,17 | 1 205,93 |
| 2 | Sub-base, km | 50 | 12 | 2,0 | 2,52 |
| 3 | Base, km | 50 | 12 | 0 |  |
| 4 | Cement concrete pavement, km | 50 | 8 | 0 |  |
| 5 | Bridges | 34 | 16 | 14 in progress | 30 in progress |
| 6 | Culverts | 120 | 60 | 12 in progress | 62 in progress |

3. Materials Stockpile for 2015:

| № | Description | Total as per contract | Plan for 2015 | Actual as of current date | % | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone for base , thous.m3 | 421,09 | 141,44 | 55,83 | 39,47% | Own |
| 2 | Sand, thous.m3 | 227,03 | 99,03 | 54,31 | 54,84% | Own |
| 3 | Sand-gravel mix, thous.m3 | 954,12 | 365,94 | 135,33 | 36,98% | Own |
| 4 | Cement, thous.m3 | 144,06 | 66,24 | 12,94 | 19,53% | Own |
| 5 | R/c elements, thous.m3 | 43,01 | 9,22 | 3,77 | 40,8% | AZMK, KKK |

4. Personnel:

| № | Description | Requirement in 2014 | Actual as of today | Out of them |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign | Local |
| 1 | Engineers and Administration | 60 | 43 | 12 | 31 |
| 2 | Laboratory | 20 | 17 | 4 | 13 |
| 3 | Survey | 20 | 25 | 6 | 19 |
| 4 | Equipment operators | 100 | 91 | 6 | 85 |
| 5 | Dump truck drivers | 80 | 102 | 0 | 102 |
| 6 | Foremen and road workers | 230 | 108 | 6 | 102 |
| 7 | Miscellaneous | 38 | 222 | 22 | 200 |
| TOTAL | 548 | 608 | 66 | 542 |

5. Equipment mobilization:

| № | Name | Requirement for 2015 | Actual as of current date | Out of them: |
| --- | --- | --- | --- | --- |
|  |  |  |  | own | Subcontractor./rented. |
| 1 | Bulldozer | 4 | 13 | 1 | 12 |
| 2 | Excavator | 11 | 13 | 4 | 9 |
| 3 | Loader | 11 | 10 | 2 | 8 |
| 4 | Motor grader | 4 | 9 | 2 | 7 |
| 5 | Rollers | 12 | 15 | 3 | 12 |
| 6 | Dump trucks | 70 | 123 | 25 | 98 |
| 7 | Water spraying machine | 7 | 5 | 2 | 3 |
| 8 | Asphalt paver | 3 | 0 | 0 | 0 |
| 9 | Concrete paver | 1 | 1 | 1 | 0 |
| 10 | Crane | 4 | 3 | 0 | 3 |
| 11 | Batching plant | 2 | 2 | 2 | 0 |
| 12 | Crushing plant | 1 | 1 | 1 | 0 |
| 13 | Pile driving machine | 1 | 3 | 1 | 2 |
| 14 | Lowbed Trailer | 4 | 5 | 2 | 3 |
| 15 | Concrete mixer (миксер) | 4 | 3 | 3 | 0 |
| 16 | Cars | 34 | 21 | 15 | 6 |
| 17 | Miscellaneous | 20 | 35 | 15 | 20 |
| TOTAL | 193 | 262 | 79 | 183 |

6. Subcontractors:

| № | Description | Type of work | Section from km - to km | Note |
| --- | --- | --- | --- | --- |
| 1 | MO-1 LLP, Atlantstroiservice LLP | Bridges and overpasses | km 0-7 | approved |
| 2 | VSP Group LLP | Earthworks and culverts | km 0-10 | approved |
| 3 | Azamat BM LLP | Earthworks | km 15-20 | approved by the Engineer |
| 4 | Rashid and K LLP | Earthworks and culverts | km 15-20 | approved |
| 5 | Miraystroi LLP | Earthworks and culverts | km 25-30 | approved |
| 6 | EletroStar LLP and and Cellsistem LLP | PTL relocation | km 0-50 | approved |
| 7 | Nikstroi LLP | Bridges | km 25-35 | approved |
| 8 | Grand Empire LLP | Earthworks | km 38-42 | Approved by the Engineer |
| 9 | YusAsar LLP | Telecommunication lines relocation | km 0-50 | approved |

7. Pending issues:

| Issue | Solution |
| --- | --- |
| Designing and agreement of new fiber optic lines at section Km0-Km6 (Transtelekom, TUSM-1, Kazakhtelecom) | Design company shall speed up the performance of these works |
| Delays in earthworks | Two shifts works shall be organized and speed up the works |