Information as of 18.04.2015

Construction and (reconstruction) of section Almaty-Kokpek-Chundzha-Koktal-Khorgos Road Lot 2

Contract: EWRP-50-111,7-ICB(W)-001/2013

Designer : KazNIiPI “Dortrans” LLP

Engineer Service:  Dongsung/DongMyeong/Zhol-Sapa DDZ

The General Contractor: JV  Dogus Insaat&Gulsan Insaat Sanayi Turizm

Subcontractor:  ТОО «Юг Асар»,»Техстройподряд»,»Ew Intercomplex»

Laboratory: Dogus Insaat&Gulsan Insaat Sanayi Turizm

Contract cost of the General Contractor: 23 216  mln KZT

Disbursed (earlier) up to 2015: 7 859,68 mln KZT

Disbursement plan for 2015 :  17 050 mln KZT

Construction period: 30 months

Construction commencement date: 10.2014

Completion date: 04.2016

Summary of Project:

Source of financing: IBRD International Bank for Reconstruction and Development

Road category:  Ib

Length:  61,7 km

Type of wearing course: concrete

Thickness of pavement: 76 cm

Executive documents:

Number of issued in a week: improvement notice: 1 no., letters: 7 nos.

Dead line of submission of Work Performance Project, and Quality Control Plan:  10.2015

- Basic

| Description | Total on the Contract | Plan for 2015 | Actual as of date |
| --- | --- | --- | --- |
| Bridges and cattle passes | 18 | 18 | - |
| Overpasses | 4 | 4 | - |
| Interchanges | 4 | 4 | - |
| Culverts | 150 | 71 | 79 |
| Bus shelters | 2 | 2 | - |

| № | Description of works | Total on the Contract | Performed in 2013-2014 | Plan for 2015 | Actual 2015 | % |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks (thous.m3) | 4508,62 | 1437,30 | 3438 | 1183,26 | 34,4 |
| 2 | Granular subbase, km | 62 | 6,86 | 47 | 20,23 | 43,0 |
| 3 | Base course H-18, km | 62 | 5,85 | 48 | 15,56 | 32,4 |
| 4 | Concrete pavement, km | 62 | 3.26 | 48 | 13,81 | 28,7 |

- Materials procurement for 2015:

| № | Описание материала | Всего по контракту | Заготовлено с начало строительства | 2015 | Поставщики |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | План | Факт на текущую дату | % |  |
| 1 | Crushed stone for base course, thous.m3 | 519,99 | 150,59 | 101,1 | 58,14 | 57,1 | own |
| 2 | Crushed stone for pavement, thous.m3 |  |  | 96,93 | 34,88 | 36,2 | - |
| 3 | SGM, thous.m3 | 1,178,2 | 1192,16 | 512,32 | 240,38 | 46,3 | - |
| 4 | Sand 0-5, thous.m3 | 280,35 | 82,76 | 138,64 | 72,13 | 52,6 | - |
| 5 | R/C elements, thous.m3 | 22,36 | 10,81 | 12,9 | 5,41 | 43,3 | AZMK |
| 6 | Cement, thous.tn | 184,68 | 10,74 | 92,73 | 19,69 | 20,7 | Semei Cement |

- Mobilization of equipment:

| № | Description | Requirement for 2015 | Actual as of date | Out of them: |
| --- | --- | --- | --- | --- |
|  |  |  |  | own | Subcontractor/rented |
| 1 | Bulldozer | 4 | 6 | 6 |  |
| 2 | Excavator | 12 | 15 | 15 |  |
| 3 | Loader | 11 | 23 | 23 |  |
| 4 | Grader | 5 | 7 | 7 |  |
| 5 | Rollers | 14 | 18 | 18 |  |
| 6 | Dumper Trucks | 70 | 61 | 61 |  |
| 7 | Watering machine | 8 | 9 | 9 |  |
| 8 | Fuel – Oil Tank |  | 1 | 1 |  |
| 9 | Asphalt Paver | 3 | 2 | 2 |  |
| 10 | Concrete Paver | 1 | 1 | 1 |  |
| 11 | Crane | 4 | 5 | 5 |  |
| 12 | Batching Plant | 2 | 2 | 2 |  |
| 13 | Crushing plant | 1 | 1 | 1 |  |
| 14 | Crushing plant | 1 | 1 |  |  |
| 15 | Concrete mixer | 5 | 3 | 3 |  |
| 14 | Manipulator | 4 | 3 | 3 |  |
| 15 | Lowbed Trailer | 4 | 8 | 8 |  |
| 16 | Piling Machine | 1 | 1 | 1 |  |
| 17 | Cars | 34 | 36 | 36 |  |
| 18 | Others | 15 | 21 | 21 |  |
|  | Total | 200 | 224 | 224 |  |

- Pending Issues:

| Issues | Ways of solution |
| --- | --- |
| Delay of work performance schedule | Adequate organization and qualified specialists |
| Purchase of land (Shelek) | Speed up all documents |
| Delays of bridge construction | Adequate organization and qualified specialists |