Information

Salini Costruttori S.p.A

South West road project: Western Europe – Western China International Transit Corridor

km 1330-1398 (Lot № 2) in Kyzylorda oblast

length 68 km.

Contractor:  Salini Costruttori S.p.A

Engineer:    Isan Corporation in association with Zhol Sapa LLP

Contract amount: KZT 10.737bln;

Disbursed in 2010- 2012 - KZT 7,45 bln.;

Amount of works to be done in 2013 – KZT 4,915 bln.

DMSU- 22AB Sub-Contractor is involved.

Laboratory.

Laboratory in Lot № 2 is located at PK 1215+6, it is fully equipped.

Compliance with Work Program  (Plan for 2013 г.)                       13.09.2013

| № | Description of works | Total in Contract | Performed in 2010-2012 | Planned for 2013 | Fact as of 13.09. 2013 | Fact for September 2013 | Total for 2010-2013 | Remaining for 2013 (+,-) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks, thous. m3: slope of subgrade and junctions | 1961,96 | 1684,33 | 277,63 | 146,33 | 1,5 | 1830,66 | -131,3 |
| 2 | Subbase, km | 68 | 68 | 0 | 0 | 0 | 68 | - |
| 3 | Base coarse С-4, km | 68 | 68 | 0 | 0 | 0 | 68 | - |
| 4 | Upper layer, km | 68 | 68 | 0 | 0 | 0 | 68 | - |
| 5 | Lower layer, km | 68 | 68 | 0 | 0 | 0 | 68 | - |
| 6 | Upper layer from CSMA, km | 68 | 1,6 | 66,4 | 27,49 | 0,69 | 29,09 | -38,91 |
| 7 | Bridges, pcs. | 1 | 0,89 | 0,11 | 0 | 0 | 0,89 | 0,11 |
| 8 | Shoulder stabilization | 68 | 0 | 68 | 6,0 | 2 | 6,0 | -62,0 |
| 9 | Culverts, pcs. | 14 | 14 | 0 | 0 | 0 | 14 | 0 |

| Procurement of material | Plan for 2013 | Fact for 13.09.2013 | Supply Per day | Required (+,-) | Remains in the sections |
| --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone thous./tons | 198,76 | 99,39 | 0 | -99,37 |  |
| Incl.: -10-20 | 83,78 | 42,17 | 0 | -41,61 | 0 |
| 5-10 | 6,0 | 0 | 0 | 6,0 | 0 |
| -0-40 | 104,26 | 41,38 | 0 | -62,88 | 15,0 |
| -0-5 | 23,85 | 8,98 | 0 | -14,87 | 1,0 |
| 2 | GSM thous./tons | 20,0 | 11,02 | 0 | -6,0 | 0 |
| 3 | Bitumen thous./tons | 6,15 | 3,89 | 0 | -2,26 | 0,50 |
| 4 | Min.fine thous./tons | 11,17 | 4,09 | 0 | -7,08 | 0,35 |
| 5 | Topcell thous. /tons | 0,36 | 0,29 | 0 | -0,07 | 0,05 |

| Equipment required for work schedule implementation for 2013 |
| --- |
| Analysis of availability and condition of Road Building Equipment |
| № Description Requirement Available at site Repairs Additionally Required Section PK 900 – PK 1578 “DMSU-22AB” LLP (Salini) 1 Автогрейдер/ Grader 4 2 2 - 2 Бульдозер/Dozer 4 2 1 1 3 Экскаватор/Excavator 4 1 1 2 4 Погрузчики/Loader 6 4 1 1 5 Катки грунтовые/Roller for earthwork 6 4 2 - 6 Катки для асфальта/Roller for asphalt 6 4 1 1 7 Водовозы/Water tank 5 3 1 1 8 Асфальтоукладчики/Paver 4 2 1 1 9 Фреза/Milling machine 1 1 - - 10 Автокран/Crane 3 1 1 1 11 Автосамосвалы на технологию/Dumper for technology 25 11 5 9 12 Автосамосвалы На перевозку ДСМ/Dumper for transporting materials 15 6 - 9 13 АБЗ/Asphalt plant 2 2 - - 14 Прочая техника/Others 15 9 6 - Total/Всего 100 52 22 26 |  |  |  |  |  |