Information on Work progress

“AKM-Planum” LLP

under the project of reconstruction of “Western Europe-Western China”international transit corridor 
km 2216.1-2231 (“Temirlan bypass”) in South Kazakhstan region

Performance of work progress schedule

| № | Work description | Unit | Quantity for 2013 | Plan for 09.09 | Fact for 09.09 | % |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Earth works: | ths.m3 | 607 | 607 | 607 | 100 % |
| 2. | Culverts | pcs. | 6 | 6 | 4 | 67 % |
| 4. | Bridges | % | 100 | 100 | 90 | 90 % |
| 5. | Sub base | km | 21,6 | 21,6 | 14,5 | 67 % |
| 6. | Base coarse from CSSCM | km | 23,9 | 23,9 | 10,1 | 42 % |
| 7 | Cement concrete pavement | km | 28,6 | 18,6 | 5,4 | 29 % |