Information on Work progress

“Azerkorpu-Tepe”

under the project of reconstruction of international transit corridor “Western Europe-Western China” km 36,5 in South Kazakhstan region for 10.10.2013 year

Performance of work progress schedule (plan for 2013year).

| № | Work description | Total under contract | Work done for 2011-2012years. | Plan for 2013year. | Fact for 20.05.13 | Implementation % | Delay (+,-) | Delay (days) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Earth works ths.m3 | 2526.7 | 1995,1 | 554,60 | 554 | 100 |  |  |
| 2 | Sub base (km) | 70.90 | 55,58 | 15,32 | 15.32 | 100 |  |  |
| 3 | Base coarse (km) | 70,90 | 48,05 | 22,85 | 22.85 | 100 |  |  |
| 4 | Cement concrete payment (km) | 70,47 | 39,80 | 30,67 | 29.97 | 97.4 |  | 3 |
| 5 | Bridges (un.) | 7 | 3,54 | 3,46 | 3.2 | 92.4 |  | 1 |
| 6 | Pipes (un.) | 34 | 28 | 6 | 6 | 100 |  |  |
| 7 | Transport barriers | 77341 |  | 77341 | 36500 | 47.2 | + | 10 days |

Procurement of materials

| № | Procurement of materials | Total under contract | Plan for 2013 year | Fact for 10.09.13 | Implementation% | Delay (+,-) days |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone ths/м3 | 560,0 | 177,19 | 178.00 | 100 | no |
| 2 | Sand gravel mix ths/м3 | 566,6 | 154,80 | 155.30 | 100 | no |
| 3 | Reinforced concrete products ths/м3 | 11,5 | 2,5 | 3.01 | 100 | no |
| 4 | Cement t | 225 | 44,70 | 43.0 | 96.2 | finance |
| 5 | Sand |  | 41.7 | 41.9 | 100 |  |