INFORMATION

JV «Copri Construction Enterprises W.L.L/SeiSer Ltd»

South West road project: Western Europe – Western China International Transit Corridor km 2111-2135 
(Lot 3) in South Kazakhstan with the length

of 23.9 km.

Compliance with Work Program    (Plan for 2013)                         as of 09.09.2013

| № | Description of works | Unit | Total in Contract | Performed in 2011-12 | Planned for 2013 | Performed in 2013 | Performed from the beginning of construction | % of completion from the beginning of construction | Outstanding works |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Earth works | ths.m3 | 1353 | 1341,6 | 11 | 11 | 1353 | 100 | 0 |
| 2 | Subbase | km | 47.8 | 47 | 0,8 | 0,8 | 47,8 | 100 | 0 |
| 3 | Base coarse | km | 47.8 | 46,7 | 1,1 | 1,1 | 47,8 | 100 | 0 |
| 4 | Cement concrete pavement 25 cm | km | 47.8 | 36,4 | 11,4 | 6,70 | 43,1 | 92 | 4,7 |
| 5 | Brigdes, Overpasses | pcs | 3/3 | 3/2,93 | 0/0,07 | 0.03 | 3/2,97 | 91 | 0,4 |
| 6 | Culverts, | pcs | 80 | 74 | 6 | 6 | 80 | 100 | 0 |
| 7 | Culverts (m) in rural road | pcs | 25 | 0 | 25 | 21 | 21 | 90 | 4 |
| 8 | Curved bar | L m | 16120 | 0 | 16120 | 8205 | 8205 | 51 | 7915 |
| 9 | Lighting poles (КЗЭЛТО) | pcs | 226 | 0 | 226 | 0 | 144 | 0 | 82 |
| 10 | Road Signs (Тенгиз+) | pcs | 535 | 0 | 535 | 0 | 0 | 0 | 535 |
| 11 | Marking | L m/m2 | 119178/18332 | 0 | 119178/18332 | 0 | 0 | 0 | 119178/18332 |

Moreover, in 2013 six (6) additional culverts were constructed

| Material Procurement | Total in Contract | Procured in 2011-12 | Plan for 2013 | Completed in 2013 | % completion from the beginning of construction |
| --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone ths./m3 | 200.75 | 142.1 | 58.65 | 53.722 | 96 |
| 2 | SGM ths./m3 | 477.8 | 439,93 | 37.87 | 37,87 | 100 |
| 3 | RCP ths. m3 | 7.8 | 6.5 | 1.3 | 1,1 | 86 |
| 4 | Cement ths./tons | 74.6 | 62,3 | 18.86 | 17,873 | 98 |

The works being performed by General Contractor at the moment:

- Construction of culverts in rural road

- Constructionof sugrade in rural road

- Asphalt concrete pavement at the approach to overpasses

- Soil fillout on center line

- Construction shoulders

- Planning of slopes

- Asphalt pavement on rest areas (at parking area)

- Cement concrete pavement

- Construction of backwall between main road and local road in Intimak village

- Instalment of guardrails

- Asphalt concrete pavement in local road in Intimak village

| PK of overpass | Completion |
| --- | --- |
| PK 681+68,1 | 95% |
| PK 729+17,6 | 90% |
| PK 782+73,2 | 97% |