INFORMATION

“Kukdong Engineering &Construction Co., LTD”

Project of Reconstruction of International Transit Corridor “Western Europe – Western China” km 2231-2260 (LOT 6) in South Kazakhstan region

Length - 24.6 km.

Observance of the progress schedule (Plan for 2013)                         09.09.2013

| № | Description | Total for the contract | Performed in 2011-2012 | Plan for 2013 | Plan for 20.05. 2013 | Actually done from the beginning of the year | performed% | Delay (+,-) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Earth works, thous. m3 | 810.725 | 704,29 | 106,44 | 106.44 | 107.8 | 100% |  |
| 2 | Subbase, km | 38.8 | 27,67 | 11,14 | 11.4 | 11.4 | 100% |  |
| 3 | Base course , km | 38.8 | 26,41 | 12,4 | 12.4 | 12.4 | 100% |  |
| 4 | Cement stabilized base course, km | 38,8 | 26,19 | 12,4 | 12.4 | 12.4 | 100% |  |
| 5 | Cement concrete pavement 27 cm | 38,8 | 26,07 | 12,73 | 12.73 | 12.74 | 100% |  |
| 6 | Bridges, pieces | 1 | 0,91 | 0,09 | 0,09 | 0,09 | 100% |  |
| 7 | Water drain and protection works | 1 | 0,54 | 0,46 | 0,46 | 0.46 | 100% |  |
| 8 | Additional lane of cement concrete, m3 |  |  |  |  | 3130 |  |  |
|  | LLP | Bereke | PK0-PK52 |  |  |  |  |  |
| 9 | Subbase, km | 9.5 | 5,6 | 3.9 | 3,9 | 3,9 | 100% |  |
| 10 | Base course , km | 9.5 | 5,6 | 3.9 | 3,9 | 3,9 | 100% |  |
| 11 | Top layer of asphalt concrete pavement, 5 cm | 15,10 |  | 15,10 | 10,4 | 10,28 | 98,85% |  |
| 12 | Bottom layer of a/c pavement – 10 cm, km | 15,10 | 3,6 | 11,5 | 10.4 | 10,28 | 98,85% | 12 |
| 13 | Highly porous a/c Н-12, cm | 15,10 | 10,4 | 4,7 | 4.7 | 4,7 | 100% |  |
| 14 | A/c leveling course Н-8, cm | 4,8 | 4,8 |  |  |  |  |  |
|  |  | PK00-PK246 |  |  |  |  |  |  |
| 15 | Road guard rail, rm | 34,4 |  | 53.015 |  | 8,70 | 14% | 44,32 |
| 16 | Road signs, pieces | 304 |  | 304 | 125 | 125 | 41% | 179 |
| 17 | Thermoplasic, t | 3,3 |  | 3,3 |  |  |  |  |
| 18 | Road marking paint, t | 1,1 |  | 1,1 |  |  |  |  |
| 19 | Ramps, pieces | 25,0 |  | 25,0 | 25,0 | 22,0 | 88% | 3 |
| 20 | Trestle pieces | 1 |  | 1 | 1 | 0,7 | 70% | 0,3 |
| 21 | Rest area pieces | 1 |  | 1 | 1 | 0,5 | 50% | 0,5 |
| 22 | Bus stops pieces | 18 |  | 18 | 18 | 14 | 78% | 4,0 |
| 23 | Concrete channels В-1-22-75 rm | 7777 |  | 7777 | 7777 | 7777 | 100% |  |
| 24 | Concrete channels В-1-20-50 rm | 1500 |  | 1500 | 1500 | 1500 | 100% |  |
| 25 | Toilets pieces | 1 |  | 1 | 1 | 0,7 | 70,0% | 0,3 |
|  | Road interchange |  |  |  |  |  |  |  |
| 26 | Bottom layer of a/c pavement 15cm thous.m3 |  |  |  |  | 2,647 |  |  |
| 27 | Medium layer of a/c pavement 10cm thous.m3 |  |  |  |  | 1,764 |  |  |
|  | Top layer of asphalt concrete pavement 5cm thous.m3 |  |  |  |  | 882,3 |  |  |
| 27 | Subbase thous.m3 |  |  |  |  | 15,98 |  |  |
| 28 | Base course thous.m3 |  |  |  |  | 3,95 |  |  |

| Procurement of materials | Total for the contract | Plan for 2013 | Actually done 09.09.2013 | performed. % | Delay (+,-) |
| --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone thous./m3 | 363.4 | 115.124 | 130.65 | 100% |  |
| 2 | Subbase thous./m3 | 361.38 | 97.883 | 146,259 | 100% |  |
| 3 | Concrete products thous./m3 | 2.7 | 0,76 | 0,76 | 100% |  |
| 4 | Cement thous./ t | 55.034 | 18.339 | 21.56 | 100% |  |

Resident Engineer

Sharipov Zh.S.