INFORMATION

Sinohydro Corporation & Limited

South West road project: Western Europe – Western China International Transit Corridor km 2183-2216.1 (Lot 5) in South Kazakhstan length

33.2 km.   as on  09.09.13.

Compliance with Work Program

As on 10.09.2013

| № | Description of works | Total in Contract | Actually completed in 2011-12 | Planned for 2013 | Actually completed | % of completion | Underrun (+,-) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks, thous. m3 | 1964 | 1653,5 | 310,5 | 378,8 | 128 | 68,3 |
| 2 | Subbase, km | 65,48 | 55,09 | 10,39 | 10,39 | 100 | - |
| 3 | Granular material road base, km | 65,48 | 55,05 | 10,43 | 10,43 | 100 | - |
| 4 | Cement concrete pavement, km | 65,48 | 49,38 | 16,1 | 16,1 | 100 | - |
| 5 | Bridges, pcs | 3 | 2 | 1 | 0,98 | 98 | - |
| 6 | Culverts, pcs | 21 | 19,5 | 1,5 | 1,5 | 100 | no |

| No. | Name of material | Unit of meas. | Under the Project | Available on the site | Installed | left | % of completion | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Guardrail | r.m. | 48 115 | 48 115 | 41 709 | 6 406 | 87 | number of people working - 42 poles installed - 900м |
| 2 | Road edge marker post | pcs | 1 657 | 1 657 | 1 507 | 150 | 91 | number of people working - 10 |
| 3 | Handrail | r.m. | 361,8 | 361,8 | 361,8 | 0 | 100 | completed |
| 4 | Road sign | pcs | 322 | 209 | 186 | 136 | 58 | Installed road sign supports -180pcs Foundation for road signs - 322pcs |
| 5 | Road traffic markings | km | 66 | 66 | 65 | 1 | 98 | 7 people |
| 6 | Lamp support | pcs | 110 | 110 | 95 | 15 | 86 | Support foundation - 100pcs. Cabel placed- 4000m. |
| 7 | Trestle | pcs | 4 | 4 | 4 | 0 | 100 | completed |
| 8 | Rest area | pcs | 4 | 4 | 4 | 0 | 100 | completed |
| 9 | Bus shelter | pcs | 4 | 4 | 4 | 0 | 100 | completed |
| 10 | Toilet | pcs | 4 | 4 | 4 | 0 | 100 | completed |
| 11 | Water drainage ditch | pcs | 5 800 | 5 800 | 5 520 | 280 | 95 | Sealing of joints with mastic - construction team of 12 people Construction of water drainage channels on subgrade slopes - 15 pcs |

Resident Engineer                                     S. Irmanov