Information as of 20.01.2017

Construction (reconstruction) of “Almaty-Kokpek-Chunja-Koktal-Khorgos” road, Lot 2

Contract: EWRP-50-111,7-ICB(W)-001/2013

General Contractor:  JV  Dogus Insaat&Gulsan Insaat Sanayi Turizm

Contract amount: 23 216  mln.tenge

Signing of contract – 17.07.2013

Construction period : 30 months

Disbursement in 2013-2015 - 14 693 062 515,78 tenge

Disbursement in 2015 - 3 453 732 662,28  tenge

Disbursement plan for 2016 -8 299 634 483,30 tenge

Engineering Service: Dongsung/DongMyeong/Zhol-Sapa DDZ

Designer: « KazNIiPI«Dortrans  » LLP

Construction commencement date:10.2013

- Project’s key results

| Section length, km | 61,7 км |
| --- | --- |
| Culverts, nos | 150 |
| Bridges and overpasses, km | 18 |
| Earthworks thous.m3 | 4520, |
| Subbase km.thous/m3 | 61,7/1651,88 |
| Base course km/thous.m3 | 61,7/1279,92 |
| Cement-concrete pavement km/thous.m3 | 61,7/6552,67 |

2. Analysis of work schedule performance

| № | Description | Total as per Contract | Performed from the begging of the construction | Remaining |
| --- | --- | --- | --- | --- |
| 1 | Earthworks thous.m3 | 4 520,00 | 4 132,0 compacted | 388 (on interchanges) |
| 2 | Sub base, km | 61,7 | 61,7 (2 sides) | - |
| 3 | Base course , km | 61,7 | 61,7 (2 sides) | - |
| 4 | Cement concrete pavement | 61,7 | 61,7 (2 sides | - |
| 5 | Asphalt, km | 61,7 | 61,7 | - |
| 6 | Guard rails, km | 151,1 | 113.11 | 37.99 |
| 7 | Bridges nos | 18,00 | 17,5 | 0,5 |
| 8 |  | 61,7 | 26 | 35,7 |
| 9 | Culverts nos | 150,00 | 141 | 9 |

3.Materials procurements for 2016

| № | Description | Total as per Contract | Plan for 2017 | Actual | % | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone, base, thous.m3 | 519,99 | 25,99 | 23,99 | 92,3 | own |
| 2 | Sand, thous.m3 | 280,35 | 14,02 | 13,19 | 94,1 | own |
| 3 | SGM, thous.m3 | 1178,2 | 58,91 | 58,03 | 98,5 | own |
| 4 | Cement thous.tn | 184,68 | 5,54 | 3,9 | 70,4 | Semei Cement |
| 5 | R/C Elements thous. m3 | 22,36 | 1,56 | 0,52 | 33,1 | AZMK |

4. Mobilization of equipment:

| № | Descriptions | Required for 2016 | Actual | Among them |
| --- | --- | --- | --- | --- |
|  |  |  |  | Own | Subcont./rent |
| 1 | Bulldozer | 4 | 5 | 3 | 2 |
| 2 | Excavator | 12 | 11 | 9 | 2 |
| 3 | Loader | 11 | 3 | 2 | 1 |
| 4 | Grader | 5 | 3 | 2 | 1 |
| 5 | Roller | 14 | 5 | 2 | 3 |
| 6 | Dumper Trucks | 70 | 70 | 20 | 50 |
| 7 | Watering machine | 8 | 2 | 2 |  |
| 8 | Fuel – Oil Tank | 1 | 1 | 1 |  |
| 9 | Asphalt Paver | 3 | 1 | 1 |  |
| 10 | Concrete Paver | 1 |  |  |  |
| 11 | Crane | 4 |  |  |  |
| 12 | Batching Plant | 3 | 1 | 1 |  |
| 13 | Crusher Plant | 2 | 1 | 1 |  |
| 14 | Piling machine | 1 |  |  |  |
| 15 | Lowbed trailer | 4 |  |  |  |
| 16 | Concrete Trans mixer | 5 |  |  |  |
| 17 | Cars | 14 | 4 | 4 |  |
| 18 | others | 37 | 4 | 2 | 2 |
|  | Total | 199 | 111 | 50 | 61 |

5. Attraction of personnel:

| № | description | Required for 2016 | Actual | Among them |
| --- | --- | --- | --- | --- |
|  |  |  |  | foreign | local |
| 1 | ИТР, АУП | 3 | 14 | 6 | 8 |
| 2 | Laboratory | 5 | 10 | 3 | 7 |
| 3 | Survey | 10 | 21 | 6 | 15 |
| 4 | Equipment operators | 70 | 64 | 15 | 49 |
| 5 | Dump track drivers | 70 | 53 |  | 53 |
| 6 | road workers | 283 | 63 |  | 63 |
| 7 | Working personnel | 112 | 202 | 20 | 100 |
| Total | 553 | 345 | 50 | 295 |

7. Subcontractors:

| № | Description | Work type | Section from km to km | Notes |
| --- | --- | --- | --- | --- |
| 1 | “Rus Ali Energo” LLP | Relocation of PTL | 50-112 | Approved |