The project Enquiry Unit  as of 22.09.2015

Regarding site implementation at 0-50 km, Project of Almaty- Khorgos Road, Section “International Transit Corridor ‘Western Europe-Western China” with JV «Dogus Insaat &Gulsan Isaat Sanayi Turizm», Lot 1

General  Contractor –JV «Dogus Insaat &Gulsan Isaat Sanayi Turizm»

Contract– EWRP-0-50-ICB(W)-001/2013

Signing of contract – 17.07.2013

Construction period –November 2013 –   2016

Contract amount of General Contractor : 25 233 582 346,00 tenge

Disbursement till 2015.: 7 277 764 588,53 tenge

Disbursement  in 2015 :    1,817,734,328.21 tenge

Disbursement plan: 7 675 180 000 tenge

The Consultant – DongSung Engineering Co. Ltd./Dong Myeong Engineering Consultants and Architecture Co. Ltd./ LLP Zhol Sapa

Designer – KazNIiPI  “Dotrans” LTD

- Project’s key results

| Section length, km | 50 |
| --- | --- |
| Culverts, nos | 120 |
| Bridges and overpasses, km | 30 |
| Overpasses, km | 1 |
| Transport junction, km | 3 |
| Earthworks thous.m3 | 5 282,3 |
| Subbase km.thous/m3 | 50/718,41 |
| Base course km/thous.m3 | 50/263,43 |
| Cement-concrete pavement km/thous.m3 | 50/275,84 |

| № | Наименование работ | Total as per Contract | Plan for | Actual 2015 | Performed from the beginning of the project |
| --- | --- | --- | --- | --- | --- |
| 1 | Earthworks (thous.m3) | 5 282,3 | 2753,07 | 1 211,30 | 1 791,71 |
| 2 | Granular subbase, km | 50 | 12 | 6,54 | 7,06 (с лев. стор.) |
| 3 | Base course, км | 50 | 12 | 6,08 | 6,08 (с лев. стор.) |
| 4 | Concrete pavement, км | 50 | 8 | 5,78 | 5,78 (с лев. стор.) |
| 5 | Bridges, pcs | 34 | 16 | 30 in progress | 30 в работе |
| 6 | Culverts, pcs | 120 | 60 | 54 in progress (16 смон.) | 54 в работе (23 смонтир.) |

- Analysis of work schedule performance

- Material procurement for 2014

| № | Description | Total as per Contract | Plan for 2015 | Actual for 2015 | % | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone, base, thous.m3 | 421,09 | 141,44 | 100,21 | 70,8% | Own |
| 2 | Sand, thous.m3 | 227,03 | 99,03 | 80,46 | 81,2% | Own |
| 3 | SGM, thous.m3 | 954,12 | 365,94 | 140,26 | 38,3% | own |
| 4 | Cement, thous.tn | 144,06 | 66,24 | 37,49 | 56,6% | Own |
| 5 | R/C elements, thous.m3 | 43,01 | 9,22 | 7,46 | 80,9% | АЗМК, ККК |

- Attraction of personnel:

| № | description | Required for 2014 | Actual | Among them |
| --- | --- | --- | --- | --- |
|  |  |  |  | foreign | local |
| 1 | ИТР, АУП | 60 | 48 | 17 | 31 |
| 2 | Laboratory | 20 | 17 | 4 | 13 |
| 3 | Survey | 20 | 25 | 6 | 19 |
| 4 | Equipment operators | 100 | 84 | 6 | 78 |
| 5 | Dump track drivers | 80 | 69 | 0 | 69 |
| 6 | Foremen and road workers | 230 | 107 | 6 | 101 |
| 7 | others | 38 | 211 | 27 | 184 |
| Total | 548 | 561 | 66 | 495 |

- Mobilization of equipment:

| № | Description | Required for 2015 | Actual | Among them |
| --- | --- | --- | --- | --- |
|  |  |  |  | own | Subcon/rent |
| 1 | Bulldozer | 4 | 11 | 1 | 10 |
| 2 | Excavator | 11 | 17 | 4 | 13 |
| 3 | Loader | 11 | 9 | 2 | 7 |
| 4 | Grader | 4 | 8 | 2 | 6 |
| 5 | Roller | 12 | 12 | 3 | 9 |
| 6 | Dumper Trucks | 70 | 100 | 25 | 75 |
| 7 | Watering machine | 7 | 8 | 2 | 6 |
| 8 | Fuel – Oil Tank | 3 | 0 | 0 | 0 |
| 9 | Asphalt Paver | 1 | 1 | 1 | 0 |
| 10 | Concrete Paver | 4 | 3 | 0 | 3 |
| 11 | Crane | 2 | 2 | 2 | 0 |
| 12 | Batching Plant | 1 | 1 | 1 | 0 |
| 13 | Crushing plant | 1 | 3 | 1 | 2 |
| 14 | Piling Machine | 4 | 5 | 2 | 3 |
| 15 | Lowbed Trailer | 4 | 3 | 3 | 0 |
| 16 | Concrete mixer | 34 | 28 | 15 | 13 |
| 17 | Cars | 20 | 28 | 15 | 13 |
| Total | Others | 239 | 79 | 160 |
| № | Description | Work type | Section from km to km | Notes |
| 1 | «МО-1», “Atlantstroyservice”LLP | Bridges and overpasses | км 0-7 | Approved |
| 2 | “KazGeoResurs” LLP | Earthworks and culverts | км 0-10 | Approved |
| 3 | “Azamat BM” LLP | Earthworks and culverts | км 15-20 | Approved by the Engineer |
| 4 | “Rashid I K” LLP | Earthworks and culverts | км 15-20 | Approved |
| 5 | “Miraystroy” LLP | Earthworks and culverts | км 25-30 | Approved |
| 6 | “ ElektroStar” and “Cellsistem” LLP | PTL Relocation | км 0-50 | Approved |
| 7 | “Nikstroy” LLP | Bridges | км 25-35 | Approved |
| 8 | “Euro Grad” LLP | Earthworks | км 42-50 | Approved |
| 9 | “Yug Asar” LLP | Relocation of communication | км 0-50 | Approved by the Engineer |

- Subcontractors :

- Pending issues:

| Pending issues | Way of solutions |
| --- | --- |
| Delay of work on earthworks quantities execution | It is necessary to arrange double shift work and speed up work pace |