Information as of 30.03.2016

Regarding site implementation at 0-50 km, Project of Almaty- Khorgos Road, Section “International Transit Corridor ‘Western Europe-Western China” with JV «Dogus Insaat &Gulsan Isaat Sanayi Turizm», Lot 1

General  Contractor –JV «Dogus Insaat &Gulsan Isaat Sanayi Turizm»

Contract– EWRP-0-50-ICB(W)-001/2013

Signing of contract – 17.07.2013

Construction period –November 2013 –  2016

Contract amount of General Contractor : 25 233 582 346,00 tenge

Disbursement (earlier) till  2016: 10 759 806 070,30 tenge

Disbursement  in 2016 :  0 tenge

Disbursement plan: 14 473 776 275,80 tenge

The Consultant – DongSung Engineering Co. Ltd. /Dong Myeong Engineering Consultants and Architecture Co. Ltd./ LLP Zhol Sapa

Designer – KazNIiPI  “Dotrans” LTD

- Project’s key results

| Section length, km | 50 |
| --- | --- |
| Culverts, nos | 120 |
| Bridges and overpasses, km | 30 |
| Overpasses, km | 1 |
| Transport junction, km | 3 |
| Earthworks thous.m3 | 5 282,3 |
| Subbase km.thous/m3 | 50/718,41 |
| Base course km/thous.m3 | 50/263,43 |
| Cement-concrete pavement km/thous.m3 | 50/275,84 |

2. Analysis of work schedule performance

| № | Description | Total as per Contract | Plan for 2016 | Actual for 2016 | Performed from the beginning of the project |
| --- | --- | --- | --- | --- | --- |
| 1 | Earthworks (thous.m3) | 5 282,3 | 3 178,93 | 1 027,60 | 3 019,08 |
| 2 | Granular subbase, km | 50 | 43,98 | 3,5 | 7,28 (left) 6,58 (right) |
| 3 | Base course, км | 50 | 43,98 | 2,5 | 6,02 (left.) 6,02 (right) |
| 4 | Concrete pavement, км | 50 | 44,04 | 0 | 6,02 (left.), 5,89 (right.) |
| 5 | Bridges, pcs | 34 | 34 | 30 in progress | 30 in progress |
| 6 | Culverts, pcs | 120 | 76 | 14 in progress (11 insttalled.) | 14 in progress (79 installed.) |

3. Material procurement for 2016

| № | Description | Total as per Contract | Plan for 2016 | Actual work done to the current date | % | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone, base, thous.m3 | 421,09 | 206,08 | 40,09 | 19% | Own |
| 2 | Sand, thous.m3 | 227,03 | 86,27 | 29,35 | 34% | Own |
| 3 | SGM, thous.m3 | 954,12 | 266,94 | 66,61 | 25% | own |
| 4 | Cement, thous.tn | 144,06 | 92,83 | 8,32 | 9% | Own |
| 5 | R/C elements, thous.m3 | 43,01 | 15,03 | 1,51 | 10% | AZMK, ККК |

4. Attraction of personnel:

| № | Description | Required for 2016 | Actual | Among them |
| --- | --- | --- | --- | --- |
|  |  |  |  | foreign | local |
| 1 | ИТР, АУП | 60 | 36 | 12 | 24 |
| 2 | Laboratory | 20 | 17 | 4 | 13 |
| 3 | Survey | 20 | 17 | 6 | 11 |
| 4 | Equipment operators | 100 | 67 | 20 | 47 |
| 5 | Dump track drivers | 80 | 87 | 0 | 87 |
| 6 | Foremen and road workers | 230 | 128 | 27 | 101 |
| 7 | others | 38 | 63 | 4 | 59 |
| Total | 548 | 415 | 73 | 342 |

5. Mobilization of equipment:

| № | Description | Required for 2015 | Actual | Among them |
| --- | --- | --- | --- | --- |
|  |  |  |  | own | Subcon/rent |
| 1 | Bulldozer | 4 | 5 | 4 | 1 |
| 2 | Excavator | 11 | 8 | 6 | 2 |
| 3 | Loader | 12 | 6 | 6 | - |
| 4 | Grader | 4 | 5 | 4 | 1 |
| 5 | Roller | 12 | 7 | 6 | 1 |
| 6 | Dumper Trucks | 70 | 31 | 20 | 11 |
| 7 | Watering machine | 7 | 4 | 3 | 1 |
| 8 | Asphalt Paver | 3 | 2 | 2 | - |
| 9 | Concrete Paver | 1 | - | - | - |
| 10 | Crane | 4 | 3 | 1 | 2 |
| 11 | Batching Plant | 2 | - | - | - |
| 12 | Crushing plant | 1 | 1 | 1 | - |
| 13 | Piling Machine | 1 | 2 | 1 | 1 |
| 14 | Lowbed Trailer | 4 | 2 | 2 | - |
| 15 | Concrete mixer | 4 | 3 | 3 | - |
| 16 | Cars | 34 | 30 | 25 | 5 |
| 17 | Other | 19 | 21 | 17 | 4 |
| Total | 193 | 130 | 101 | 29 |
| № | Description | Work type | Section from km to km | Notes |
| 1 | “Atlantstroyservice”LLP | Bridges and overpasses | km 0-7 | Approved |
| 2 | “ ElektroStar” and “Cellsystem” LLP | PTL Relocation | km 0-50 | Approved |
| 3 | “Nikstroy” LLP | Bridges | km 25-35 | Approved |
| 4 | “Yug Asar” LLP | Relocation of communication | km 0-50 | Approved |

6. Subcontractors:

7. Pending issues:

| Pending issues | Way of solutions |
| --- | --- |
| Delay on execution of earthworks quantities | It is necessary to arrange double shift work and speed up work pace |