Information as of 30.03.2016

Construction (reconstruction) of “Almaty-Kokpek-Chunja-Koktal-Khorgos”   road, Lot 2

Contract: EWRP-50-111,7-ICB(W)-001/2013

General Contractor:  JV  Dogus Insaat&Gulsan Insaat Sanayi Turizm

Contract amount: 23 216  mln.tenge

Signing of contract – 17.07.2013

Construction period : 30 month

Disbursement in 2013-2014 -8 084 690 008,30 tenge

Disbursement in 2015 - 6 832 629 965,40 tenge

Disbursement plan for 2016 -8 299 634 483,30 tenge

Engineering Service: Dongsung/DongMyeong/Zhol-Sapa DDZ

Designer: « KazNIiPI«Dortrans  » LLP

Construction commencement date:10.2013

Construction completion date:04.2016

- Project’s key results

| Section length, km | 61,7 км |
| --- | --- |
| Culverts, nos | 150 |
| Bridges and overpasses, km | 18 |
| Earthworks thous.m3 | 4520, |
| Subbase km.thous/m3 | 61,7/1651,88 |
| Base course km/thous.m3 | 61,7/1279,92 |
| Cement-concrete pavement km/thous.m3 | 61,7/6552,67 |

2. Progress

| № | Description | As per Contract | Disbursement in 2013-2015 | Plan for 2016 | As per contract |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Plan | Done to date | % | Sum | % |
| 1 | Physical progress ( mln.tenge) | 23 216,954 | 10 721,97 | 12 494,98 | 2 033,80 | 16 | 12 755,77 | 55 |
| 2 | Progress in cash equivalent (mln.tenge) | 23 216,954 | 14 917,32 | 8 299,63 | 1 509,84 | 18 | 16 427,16 | 71 |

3. Analysis of work schedule performance

| № | Description | Total as per Contract | Plan for 2016 | Performed | Performed from the begging of the constructiom |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | In 2016 |  |
| 1 | Earthworks thoun.m3 | 4520,00 | 1520,00 | 323,42 | 3323,42 |
| 2 | Sub base, km | 62,00 | 11,94 | 0,00 | 49,76 |
| 3 | Base course , km | 62,00 | 13,01 | 0,00 | 48,69 |
| 4 | Cement concrete pavement | 62,00 | 13,25 | 0,00 | 48,45 |
| 5 | Bridges nos | 18,00 | 18 | 0,00 | 18 in progress |
| 6 | Culverts nos | 150,00 | 25 | 0,00 | 125 |

4.Materials procurements for 2016

| № | Description | Total as per Contract | Plan for 2016 | Actual | % | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone, base, thous.m3 | 519,99 | 186,58 | 28,51 | 15,1 | own |
| 2 | Sand, thous.m3 | 280,35 | 60,68 | 19,64 | 32,3 | own |
| 3 | SGM, thous.m3 | 1178,2 | 77,12 | 13,02 | 17,4 | own |
| 4 | Cement thous.tn | 184,68 | 28,83 | 5,18 | 18,2 | Semei Cement |
| 5 | R/C Elements thous. m3 | 22,36 | 0,30 | 0,00 | 0,00 | AZMK, |

5. Mobilization of equipment:

| № | Descriptions | Required for 2016 | Actual | Among them |
| --- | --- | --- | --- | --- |
|  |  |  |  | Own | Subcont./rent |
| 1 | Bulldozer | 4 | 4 | 3 | 1 |
| 2 | Excavator | 12 | 4 | 2 | 2 |
| 3 | Loader | 11 | 3 | 3 |  |
| 4 | Grader | 5 | 3 | 2 | 1 |
| 5 | Roller | 14 | 4 | 3 | 1 |
| 6 | Dumper Trucks | 70 | 53 | 43 | 10 |
| 7 | Watering machine | 8 | 3 | 2 | 1 |
| 8 | Fuel – Oil Tank | 1 | 1 | 1 |  |
| 9 | Asphalt Paver | 3 | 1 | 1 |  |
| 10 | Concrete Paver | 1 | 2 | 2 |  |
| 11 | Crane | 4 | 2 | 2 |  |
| 12 | Batching Plant | 3 | 3 | 3 |  |
| 13 | Crusher Plant | 2 | 2 | 2 |  |
| 14 | Piling machine | 1 | 1 | 1 |  |
| 15 | Concrete Trans mixer | 4 | 4 | 4 |  |
| 16 | Lowbed trailer | 5 | 3 | 3 |  |
| 17 | Cars | 14 | 10 | 10 |  |
| 18 | others | 37 | 115 | 112 | 3 |
|  | Total | 199 | 119 | 100 | 19 |

6. Attraction of personnel:

| № | description | Required for 2016 | Actual | Among them |
| --- | --- | --- | --- | --- |
|  |  |  |  | foreign | local |
| 1 | ИТР, АУП | 3 | 7 | 6 | 1 |
| 2 | Laboratory | 5 | 16 | 3 | 13 |
| 3 | Survey | 10 | 9 | 3 | 6 |
| 4 | Equipment operators | 70 | 23 | 3 | 20 |
| 5 | Dump track drivers | 70 | 53 |  | 53 |
| 6 | road workers | 283 | 25 | 10 | 15 |
| 7 | Working personnel | 112 | 121 | 44 | 77 |
| Total | 553 | 254 | 69 | 185 |

7. Subcontractors:

| № | Description | Work type | Section from km to km | Notes |
| --- | --- | --- | --- | --- |
| 1 | “Yug Asar” LLP | Relocation of communication | 50-112 | Approved |
| 2 | “ ElektroStart” LLP | Electric works | 50-112 | Approved |
| 3 | “Rus Ali” LLP | Electric works | 50-112 | Approved |

8. Pending issues:

| № | Pending Issues | Ways of solutions |
| --- | --- | --- |
| 1 | Delay on work schedule | Adequate organization and qualified specialists |