# Work progress information

Western Europe – Western China International Transit Corridor reconstruction project km1702-km 1752 (LOT №7) in Kyzylorda region.

length 49 km.

# Contractor:  «Evrascon» JSC

# Engineer:     «Kazdorproject» LLP

New Contract amount:  8 323 920 292,09 KZT;

Advance payment: 1 221 721 945,94 KZT

Disbursement until 2016 – 4 739 481 225,27 KZT.

Disbursed from 2016: 898 102 891,82 KZT

Remaining disbursment – 2 686 336 175,00 KZT;

Subcontractors: General Contractor has concluded the Contract with Subcontractor KREC JSC for PTL-35 kV relocation in Kyzylorda region.

Base at the section PK196  (ACP, CCP and Laboratory).

Work program performance                                               		   	 05.10.2016

| № | Work description | Total under Contract | Actual from beginning of construction | Remaining work as of 05.10.16 | Actual performed from the beginning of the year | Performance |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks, km | 49 | 49,0 | 0,0 | 0,0 | 100% |
| 2 | Subbase, km | 49 | 49,0 | 0,0 | 0,0 | 100% |
| 3 | Lower layer of the base course С-4, km | 49 | 49,0 | 0,0 | 0,0 | 100% |
| 4 | Binding course 12 cm, km | 49 | 49,0 | 0,0 | 0,0 | 100% |
| 5 | Wearing course 10 cm, km | 49 | 49,0 | 0,0 | 0,0 | 100% |
| 6 | Top layer of crushed stone mastic asphalt concrete, km | 49 | 49,0 | 0,0 | 0,0 | 100% |
| 7 | Culverts, pcs. | 45 | 42,8 | 2,2 | 3,6 | 95% |
| 8 | Bridges, pcs. | 13 | 12,6 | 0,4 | 1,35 | 96% |
| 9 | Shoulder protection С6, km | 98 | 26 | 72 | 26 | 26% |
| 10 | Intersection and junction construction, rest area with wearing course Н=10 cm, pcs | 33 | 26 | 7 | 0 | 93% |
| 11 | Slope strengthening by geogrid with filling of topsoil, m2 | 222 220 | 85 600 | 136 620 | 85 600 | 38% |
| 12 | Slope strengthening with biomat, m2 | 69 945 | 43 000 | 26 945 | 43 600 | 61% |
| 13 | Bus stop, pcs. | 11 | 10 | 1 | 10 | 90% |
| 14 | Edge chutes on the road, r.m. | 7101 | 7053 | 48 | 7053 | 99% |
| 15 | Existing road on Akzharmy village bypass section (base course for asphalt concrete pavement is ready), km | 6,33 | 6,33 | 0 | 6,33 | 100% |

Material procurement:

| Material procurement | Plan for 2016 | Actual stockpiled as of 05.10.2016 |  | Performed taking into account laid. |
| --- | --- | --- | --- | --- |
| 1 | Quarry stone for preparation of crushed stone thous./tons |  | 1,500 |  |  |
| 2 | Crushed stone thous./tons | 29, 902 | 2,510 |  | 24,830 |
| 4 | Sieve thous./tons | 21, 548 | 0,400 |  | 17,530 |
| 5 | С6 for slope strengthening, thous.tons | 74,970 | 3,600 |  | 23,760 |
| 6 | Bitumen thous./tons | 2, 382 | 0,360 |  | 2,200 |
| 7 | Geotextile thous/m2 | 162,567 | 20,000 |  | 110,120 |
| 8 | Geogrid thous/m2 | 222,220 | 50, 000 |  | 135,600 |
| 9 | Biomat thos/m2 | 59, 945 | 14,000 |  | 57,600 |
| 10 | Barier guardrail, r.m | 45656 | 2424 |  | 0 |

# Количество техники, необходимое  для выполнения программы работ на 2015 год.

| Name | Requirement for October 2016 | As of 05.10.2016 |
| --- | --- | --- |
|  |  | Actual available as of 05.10.2016 | Additional requirement |
| Бульдозер / Bulldozer | 2 | 0 | 2 |
| Экскаватор / Excavator | 6 | 6 |  |
| АВЗ/ ACP | 1 | 1 |  |
| Бетонный завод/ Concrete plant | 1 | 1 |  |
| ДСУ/RCA | 3 | 3 |  |
| Погрузчик / Loader | 3 | 2 | 1 |
| Автогрейдер / Grader | 3 | 2 | 1 |
| Катки / Rollers | 3 | 2 | 1 |
| Асфальтовый каток/Asphalt compactor | 5 | 5 |  |
| Асфальтоукладчик / Asphalt paver | 2 | 1 | 1 |
| Автосамосвалы / Dump trucks | 50 | 38 | 12 |
| Автогудронатор / Bitumen distributor | 1 | 1 |  |
| Битумовоз / Bitumen truck | 2 | 1 | 1 |
| Поливочная машина / Water truck | 2 | 2 |  |
| Бензовоз / Gas tank truck | 1 | 1 |  |
| Кран / Crane | 2 | 1 | 1 |
| тралл / Trailer | 1 | 1 |  |
| миксеры для бетона / Concrete mixer | 2 | 2 |  |
| Всего | 90 | 71 | 19 |

# Personnel:

| Personnel | Lot №7 | % |
| --- | --- | --- |
|  | Plan | Actual |  |
| Total personnel for October 2016. | 222 | 122 | 55 |

# Issues of concern and reasons occuring at this section:

- Partial absence of SGM;

- Absence of funds for work performance;

- Absence of materials for strengthening of shoulders and slopes;

- Malfunction of road-building machinery and equipment.

- Insufficient quantity of qualified personnel