INFORMATION

On the “Western Europe-Western China”

International transit corridor Reconstruction Project

km 774-806 (LOT 2) in South-Kazakhstan Region

on the 11.10.2016

General Contractor –  «EVRASCON» JSC Evro-Asian Construction Corporation (Azerbaijan)

Contract EBRD/CW-02/2013 (22/08/2014)

Contract price – 12 585 798 659,48 tenge

Amount of advance  – 1 887 869 798,91 tenge (28/12/2014)

Construction Supervision Consultant –«KazDorNII» in association with «KazNiiPI»  Dortrans and KHA

Time for Completion – 18 months (540 days)

Project Designer – SK «Engineering» LLP

- Main aspects of the project:

| Section length (km) | 32 |
| --- | --- |
| Culverts, including: (nos) - on the main road - on the ramps | 96 35 61 |
| Traffic interchange in two levels (nos) | 2 |
| Bridges, overpasses, driveways for agricultural machinery (nos) | 3/2/5 |
| Earthworks (thous. m3) | 697,58 |
| Gravel and sand mix С-4 for subbase with thickness Н=35cm(thous. m3) | 566,90 |
| Crushed stone base course С-6 treated with cement 7%, thickness Н=20cm(thous. m3) | 176,86 |
| Concrete pavement type Btb-4,8 – bending tensile strength; B-35 compression strength; thickness Н=27cm(thous. m3) | 157,64 |
| Bus shelters / Stopping points / Pedestrian underpass 4mх45,73m (nos) | 10/10/2 |
| Rest area with repair trestle (nos) | 1 |

- Laboratory:

The laboratory is located at the production base km 780 (right side).

- Production base (12 he. at km 780, right side):

All the buildings as follows: office, canteen, laboratory, dormitories for engineering staff and labors are being operated

Concrete batching plant with production capacity 180 m3/hour produces concrete for cement-concrete pavement and equipped with cement silos of total capacity 650 tons. The second Concrete batching plant with production capacity 120 m3/hour produces mix for CCSM (7%) and equipped with cement silos of total capacity 450 tons. The Asphalt concrete plant "Lintek" is also mounted with a production capacity 300 ton / hour. On production base the concrete goods are issued (beams and culvert links).

- Information on executed works as:

| No | Works | Unit of measure | Plan on Contract | Actual on 2015 | Plan on 2016 | Actual on 2016 | Accumulative fact | % of execution | balance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks | m3 | 697,57 | 285,420 | 412,157 | 183,15 | 468,57 | 67% | 229,00 |
|  |  | km | 58,80 | 5,94 | 52,86 | 22,14 | 28,08 | 47% | 30,72 |
| 2 | Subgrade | km | 58,80 | 1,74 | 57,06 | 24,87 | 26,61 | 45% | 32,19 |
| 3 | Crushed stone base | km | 51,40 | 0,60 | 50,80 | 19,99 | 20,59 | 40% | 30,81 |
| 4 | Concrete pavement | km | 7,40 | 0,00 | 7,40 | 5,70 | 5,70 | 77% | 1,70 |
| 5 | Culverts on main road | nos | 51,40 | 0,00 | 51,40 | 17,458 | 17,458 | 34% | 33,942 |
| 6 | Culverts on ramps | nos | 35 | 3 | 32 | 27,5 | 30,5 | 87% | 4,5 |
| 7 | Bridges | nos | 61 | 0,00 | 61 | 2 | 2 | 3% | 59 |
| 8 | Overpasses | nos | 3,00 | 0,00 | 3,00 | 1,90 | 1,90 | 63% | 1,10 |
| 9 | Agricultural machinery passes | nos | 2,00 | 0,00 | 2,00 | 1,35 | 1,35 | 68% | 0,65 |
| 10 | Milling | km | 5,00 | 0,00 | 5,00 | 2,30 | 2,30 | 46% | 2,70 |
| 11 | Dismantling of lean concrete | km | 58,80 | 14,50 | 36,90 | 24,30 | 38,8 | 66% | 20,00 |

- Financial Disbursement.

| Total on Contract | Disbursed 2015 | Plan from construction beginning on October 03, 2016 | Fact from construction beginning on October 03, 2016 | % disbursement |
| --- | --- | --- | --- | --- |
| 12 585,82 mill. t-ge | 699,47 | 12 585,798 | 5 884,9 | 47 |

- Main road-construction materials procurement as :

| No | Works | Unit of measure | Plan on Contract | Actual on 2015 | Plan on 2016 | Actual on 2016 | Accumulative fact | % of execution |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone | thous.m3 | 433,92 | 20,116 | 413,800 | 153,612 | 173,728 | 40% |
| 2 | Sand and gravel mix | thous.m3 | 566,83 | 115,00 | 451,833 | 256,564 | 371,564 | 66% |
| 3 | Sand | thous.m3 | 138,812 | 4,28 | 134,532 | 32,338 | 36,618 | 26% |
| 4 | Cement | thous.ton | 98,809 | 1,909 | 96,900 | 30,939 | 32,847 | 33% |
| 5 | Reinforced concrete goods | thous.m3 | 6,45 | 1,253 | 5,197 | 4,234 | 5,487 | 85% |

- Personnel:

| No. | Description | Plan | Foreign | Local | Total |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | SKR | RK |  |
| 1 | Administration | 12 | 4 |  |  | 4 |
| 2 | Engineering and administrative personnel | 15 | 9 | 2 |  | 11 |
| 3 | Surveyor | 5 | 5 | 3 | 1 | 9 |
| 4 | Surveyor Assistant | 10 |  | 5 |  | 5 |
| 5 | Laboratory Assistant | 4 | 1 | 1 | 1 | 3 |
| 6 | Laboratory Engineer | 5 | 0 | 2 | 2 | 4 |
| 7 | Laboratory Workers | 8 | 0 | 2 |  | 2 |
| 8 | Mechanical Engineer | 4 | 1 |  |  | 1 |
| 9 | Mechanic | 17 | 3 | 21 |  | 24 |
| 10 | Mechanical Assistant | 8 | 4 | 11 |  | 15 |
| 11 | Drivers and operators | 320 | 40 | 41 |  | 81 |
| 12 | Road Worker | 152 | 13 | 221 |  | 234 |
| 13 | Support personnel | 173 | 48 | 80 |  | 128 |
| 14 | Office manager | 40 | 2 | 15 |  | 17 |
| 15 | Office Workers | 8 |  | 15 | 1 | 16 |
|  | Total | 781 | 130 | 419 | 5 | 554 |

(the number of one watch is 554 people, total number is 819 people)

- Equipment mobilization:

| No. | Name | Plan on month | Own/subcontract | Rent | On repair | Total | % |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Bulldozer | 6 | 4/3 | 1 | 4 | 4 | 66% |
| 2 | Excavator | 18 | 14/7 |  | 3 | 18 | 100% |
| 3 | Loader | 10 | 7/4 | 1 | 2 | 10 | 100% |
| 4 | Dump truck | 110 | 90/32 |  | 47 | 75 | 68% |
| 5 | Water tank | 10 | 4 |  | 1 | 3 | 30% |
| 6 | Fuel tank | 3 | 3 |  |  | 3 | 100% |
| 7 | Grader | 7 | 7/3 |  | 2 | 8 | 114% |
| 8 | Roller | 16 | 12/7 |  | 3 | 16 | 100% |
| 9 | Concrete batching plant | 1 | 1 |  |  | 1 | 100% |
| 10 | Crushing plant | 1 | 1 |  |  | 1 | 100% |
| 11 | Concrete paver | 2 | 1 |  |  | 1 | 50% |
| 12 | CSCM paver | 2 | 1 |  |  | 1 | 50% |
| 13 | Crane | 10 | 6 | 2 |  | 8 | 80% |
| 14 | Trailer | 4 | 2 |  |  | 2 | 50% |
| 15 | Milling machine | 2 | 2 |  |  | 1 | 50% |
| 16 | Light vehicles | 18 | 18 | 2 |  | 20 | 111% |
| 17 | Crushing screening plant | 1 | 1 |  |  | 1 | 100% |
| 18 | Asphalt batching plant | 1 | 1 |  |  | 1 | 100% |
| 19 | Others | 76 | 29 |  | 5 | 24 | 32% |
|  | TOTAL | 298 | 204/56 | 6 | 67 | 195 | 65% |

- Interim Payment Certificates:

| No. of IPC | Period | Amount (with VAT) | Date of giving | Remark |
| --- | --- | --- | --- | --- |
| 1 | 14.11.2014 | 123 505 262,99 | 15.11.2015 | Paid |
| 2 | from 08.04.2015 till 08.06.2015 | 145 333 157,41 | 15.06.2015 | Paid |
| 3 | from 08.06.2015 till 08.09.2015 | 140 282 975,29 | 15.09.2015 | Paid |
| 4 | from 08.09.2015 till 25.11.2015 | 170 075 757,04 | 27.11.2015 | Paid |
| 5 | from 26.11.2015 till 22.12.2015 | 120 277 348,49 | 22.12.2015 | Paid |
| 6 | from 23.12.2015 till 27.01.2016 | 135 117 345,21 | 28.01.2016 | Paid |
| 7 | from 28.01.2016 till 01.03.2016 | 81 273 565,72 | 02.03.2016 | Paid |
| 8 | from 02.03.2016 till 15.03.2016 | 150 251 887,11 | 17.03.2016 | Paid |
| 9 | from 16.03.2016 till 25.04.2016 | 350 010 336,78 | 26.04.2016 | Paid |
| 10 | from 26.04.2016 till 05.05.2016 | 152 981 200,00 | 06.05.2016 | Paid |
| 11 | from 06.05.2016 till 23.05.2016 | 333 579 453,17 | 24.05.2016 | Paid |
| 12 | from 24.05.2016 till 06.06.2016 | 337 067 188,62 | 17.06.2016 | Paid |
| 13 | from 17.06.2016 till 30.06.2016 | 401 182 336,19 | 01.07.2016 | Paid |
| 14 | from 01.07.2016 till 23.07.2016 | 382 466 646,88 | 24.07.2016 | Paid |
| 15 | from 24.07.2016 till 10.08.2016 | 344 216 216,91 | 11.08.2016 | Paid |
| 16 | from 11.08.2016 till 05.09.2016 | 334 147 751,18 | 05.09.2016 | Not paid 26 983 148.17 tenge |
| 17 | from 06.09.2016 till 27.10.2016 | 413 045 040,09 | 27.10.2016 | Not paid |
| Total | 4 114 723 469,07 |  |  |

- LLP " Accord-Kazakhstan SDI" has started to work on the PK 694 ÷ 844 + 00 + 00 in RHS lane of the road and today executed the following works:

- milling of existing asphalt concrete pavement PK 694 + 00 + 750 ÷ PK 00 = 5100 r/m.

- removal of lean concrete PK 694 + 00 + 712 ÷ PK 00 = 1800 r/m.

- removal of unsuitable ground PK 694 + 00 + 710 ÷ PK 00 = 1600 r/m.

- recompacting of existing embankment PK 694 ÷ 00 + 700 + 00 = 600 r/m.

- filling of subgrade PK 694 + 00 + 697 ÷ PK 00 = 300 r/m.

Number of equipment  - 26 units. Personnel - 34 people.

- Subcontract Organizations:

LLP "Shyrak-LKS»  performs work on the transfer lines.

LLP "Corporation Bereke A" works on the device of asphalt pavement in the village of Zhibek Zholy (due to lack of finances is not working).

LLP "ShymNurServis" continues to work on the device subgrade and subbase on the main road PK 872  + 00 ÷ PK 955 + 00.

LLP "Mary Company" is working to install traffic lights.

LLP "Atom BG" has completed the construction of fences, parking lots № 4-4, № 2-2 and installation of canopies in parking lots № 4-4, № 2-2. At this time, completed the construction of toilets in the parking lots, the remaining work on the electricity and water supply.

LLP "UPK Adhesion" has finished work on the transfer of the gas pipeline of low and medium pressure, began harvesting material to the transfer of a high-pressure pipeline.

LLP "KazTsep" performs the transfer of power lines (0.4 kW).

LLP "Accord - Kazakhstan-SDI" began work on the PK 694 ÷ 844 + 00 + 00, and performs the following: earthworks, structural layers of pavement and artificial structures.

12. Material suppliers:

| No. | Material | Supplier | Note |  |
| --- | --- | --- | --- | --- |
| 1 | Crushed stone | LLP "Taza Astyk" IP "Tulametov" | for pavement | approved approved |
|  |  | LLP "Nygmet Kum" | for base course | approved |
| 2 | Sand Gravel Mix | LLP "Nygmet LTD", LLP "Kaz Tas" | for sub base | approved |
| 3 | Sand | LLP "Sairam Trans" | for pavement | approved |
| 4 | Cement | LLP "Standard Cement" | for pavement | approved |
|  |  | LLP "Standard Cement" | for base course | approved |
| 5 | Film (geomembrane) | LLP "Kurylys Polymer" | for pavement | approved |
| 6 | Dowel bar | LLP "Kor.Metall Service" | for pavement | approved |
| 7 | Anchor bar | Com. "EVRASCON" | for pavement | approved |
| 8 | Concrete goods for bridges | Com. "EVRASCON" | for artificial constructions | approved |
| 9 | Concrete goods for culverts and tubings | Com. "EVRASCON" | for artificial constructions | approved |

Resident Engineer  _______________________   S. Irmanov

Performed: 		Quantity Engineer, Erezhepov A.T.

Mobile: 8 702 608 62 33