# Work progress information

Western Europe – Western China International Transit Corridor reconstruction project km1702-km 1752 (LOT №7) in Kyzylorda region.

length 49 km.

# Contractor:  «Evrascon» JSC

# Engineer:     «Kazdorproject» LLP

New Contract amount:  8 233 648 569,50 KZT;

Disbursement – 4 979 456 298,94 KZT.

Incl. advance payment of 5% for mobilization – 407 240 645 KZT.

Remaining works –3 254 192 270,56 KZT;

Subcontractors: General Contractor has concluded the Contract with Subcontractor KREC JSC for PTL-35 kV relocation in Kyzylorda region.

Base at the section PK196  (ACP, CCP and Laboratory).

Work program performance                                               		   	 31.03.2016

| № | Work description | Total under Contract | Actual from beginning of construction | Remaining work as of 31.03.16 | Actual performed from the beginning of the year | Delay /advance from the work program, in days | Performance |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks, km | 49 | 49,0 | 0,0 | 0,0 | 0 | 100% |
| 2 | Subbase, km | 49 | 49,0 | 0,0 | 0,0 | 0 | 100% |
| 3 | Lower layer of the base course С-4, km | 49 | 49,0 | 0,0 | 0,0 | 0 | 100% |
| 4 | Binding course 12 cm, km | 49 | 49,0 | 0,0 | 0,0 | 0 | 100% |
| 5 | Wearing course 10 cm, km | 49 | 49,0 | 0,0 | 0,0 | 0 | 100% |
| 6 | Top layer of crushed stone mastic asphalt concrete, km | 49 | 49,0 | 0,0 | 0,0 | 0 | 100% |
| 7 | Culverts, pcs. | 45 | 42,79 | 2,4 | 0,19 | -17 | 95% |
| 8 | Bridges, pcs. | 13 | 11,45 | 1,55 | 0,23 | -27 | 86% |
| 9 | Shoulder protection С6, km | 49 | 0,0 | 49 | 0,0 | -120 | 0% |
| 10 | Intersection and junction construction, rest area with wearing course Н=10 cm, pcs | 33 | 27 | 6 | 0 | -30 | 81% |
| 11 | Guardrails, m | 45 656 | 0,0 | 45 656 | 0,0 | -75 | 0% |
| 12 | Rad marking, r.m | 229 680 | 0,0 | 229 680 | 0,0 | -81 | 0% |
| 13 | Sand depot | 1 | 0,0 | 1 | 0,0 | -63 | 0% |

Material procurement:

| Material procurement | Plan for 2016 | Actual stockpiled as of 31.03.2016 | Delay/advance from work program, in days | Performed % |
| --- | --- | --- | --- | --- |
| 1 | Quarry stone for procurement of crushed stone thous./tons | 10,000 | 10,000 | 0 | 100% |
| 2 | GSM thous./tons | 21, 958 | 21, 958 | 0 | 100% |
| 3 | CSSM thous./tons | 10 ,000 | 0 | 29 | 0 |
| 4 | Sieve thous./tons | 29, 902 | 9,557 | -1 | 32% |
| 5 | Bitumen thous./tons | 21, 548 | 5,758 | -1 | 26% |
| 6 | Geotextile thous./m2 | 2, 382 | 0,680 | -20 | 28% |
| 6 | Geogrid thous./m2 | 162,567 | 60,000 | -6 | 36% |
| 7 | Biomat thous./m2 | 203, 059 | 25,000 | -5 | 12% |
|  |  | 59, 745 | 0 | -30 | 0 |

# Number of machinery required for performance of work program for 2015.

| Name | Requiremetn for March 2016 | As of 31.03.2016 |
| --- | --- | --- |
|  |  | Actual available as of 31.03.2016 | Additional requirement |
| Бульдозер / Bulldozer | 1 | 0 | 1 |
| Экскаватор / Excavator | 6 | 6 |  |
| АВЗ/ ACP | 1 | 1 |  |
| Бетонный завод/ Concrete plant | 1 | 1 |  |
| ДСУ/RCA | 2 | 2 |  |
| Погрузчик / Loader | 2 | 2 |  |
| Автогрейдер / Grader | 2 | 2 |  |
| Фреза / Milling machine | 1 |  |  |
| Катки / Rollers | 3 | 3 |  |
| Асфальтовый каток/Asphalt compactor | 4 | 3 | 1 |
| Асфальтоукладчик / Asphalt paver | 2 | 1 | 1 |
| Автосамосвалы / Dump trucks | 55 | 38 | 17 |
| Автогудронатор / Bitumen distributor | 1 | 1 |  |
| Битумовоз / Bitumen truck | 2 | 1 | 1 |
| Поливочная машина / Water truck | 2 | 1 | 1 |
| Бензовоз / Gas tank truck | 1 | 1 |  |
| Кран / Crane | 2 | 2 |  |
| тралл / Trailer | 1 | 1 |  |
| миксеры для бетона / Concrete mixer | 2 | 2 |  |
| Цементовоз/Cement truck | 1 | 1 |  |
| Разметочная машина / Measuring machine | 1 |  | 1 |
| Total | 93 | 69 | 23 |

# Personnel:

| Personnel | Lot №7 | % |
| --- | --- | --- |
|  | Plan | Actual |  |
| Total personnel for March 2016. | 234 | 159 | 67 |

# Issues of concern and reasons occuring during construction:

- Partial lack of SGM;

- Lack of funds for work performance.