INFORMATION

On the “Western Europe-Western China” International transit corridor

Reconstruction Project

km 774-806 (LOT 2) in South-Kazakhstan region

on the 09.02.2016

General Contractor –  «EVRASCON» JSC Evro-Asian Construction Corporation (Azerbaijan)

Contract EBRD/CW-02/2013 (22/08/2014)

Contract price – 12 585 798 659,48 tenge

Amount of advance  – 1 887 869 798,91 tenge (28/12/2014)

Construction Supervision Consultant –«KazDorNII» in association with «KazNiiPI»  Dortrans and KHA

Time for Completion – 18 months (540 days)

Project Designer – SK «Engineering» LLP

- Main aspects of the project

| Section length (km) | 32 |
| --- | --- |
| Culverts, including: (nos) - cattle underpass | 99 9 |
| Traffic interchange in two levels (nos) | 2 |
| Bridges, overpasses, driveways for agricultural machinery (nos) | 3/2/5 |
| Earthworks (thous. m3) | 697,58 |
| Gravel and sand mix С-4 for subbase with thickness Н=35cm(thous. m3) | 566,90 |
| Crushed stone base course С-6 treated with cement 7%, thickness Н=20cm(thous. m3) | 176,86 |
| Concrete pavement type Btb-4,8 – bending tensile strength; B-35 compression strength; thickness Н=27cm(thous. m3) | 157,64 |
| Bus shelters / Stopping points / Pedestrian underpass 4mх45,73m (nos) | 10/10/2 |
| Rest area with repair trestle (nos) | 1 |

- Laboratory:

Mounting works on the Contractor’s laboratory are completed. The laboratory is located at the production base km 780 (right side). Arrangement of the laboratory is completed. Certification and tools examination have been performed.

- Production base (12 he. at km 780, right side)

All the buildings as follows: office, canteen, laboratory, dormitories for engineering staff and general labors. At the present time three dormitories for 194 places and the canteen are being operated.  Conducted works on editing of 4 dormitories into 60 places. Office for the Engineer’s Service is provided at the production base.

Concrete batching plant «Jaguar» (production capacity 125 m3/hour) has been installed and produces concrete for production base needs (dormitories and etc.). Concrete batching plant is equipped with 3 cement silos of total capacity 450 tons. The second concrete batching plant with production capacity 180 m3/hour is being installed (99%) with 1 silos for cement of total capacity 500 ton. A mobile crushing plant produced by TEREXS with production capacity 180 ton/hour has been arranged at the production base, composed as follows: sieve – 2 pc., cone – 1 pc. Executed installation and put into on operation mechanical facility with production capacity 180 ton/hour for producing crushed stone and sand mix added by cement, and equipped by cement silo of 150 ton capacity. A Plant for production reinforce-concrete culvert links of pipe is entered into on operation. Setting a plant for production of reinforce-concrete span beams.

- Survey operations:

Geodetic survey works are finished; a new executive survey has been completed; working drawings of the road 17 km, 2 bridge, 1 overpass, 1 agriculture machinery overpass and 20 culverts are ready.

- Physical progress as:

| Year | Month | Plan of disbursement (tenge) | Physical progress (tenge) | % | Remarks |
| --- | --- | --- | --- | --- | --- |
| 2014 | December | 123 505 262,94 | 123 505 262,94 | 100 | IPC # 1 |
| 2015 | June | 124 773 558,55 | 124 773 558,55 | 100 | IPC # 2 |
|  | September | 79 730 062,85 | 79 730 062,85 | 100 | IPC # 3 |
|  | November | 152 836275,53 | 152 836 275,53 | 100 | IPC # 4 |
|  | December | 43 724 147,59 | 43 724 147,59 | 100 | IPC # 5 |
|  | Total as 2014-2015y | 524 569 307,46 | 524 569 307,46 | 100 | Including VAT |
| 2016 | January | 164 150 000 | 106 124 161,11 | 64,65 | IPC # 6 |
|  | Total as 2014-2016г | 688 719 307,46 | 630 693 468,57 | 91,57 | Including VAT |

6. Financial progress as :

| Year | Month | Plan of disbursement | Financial progress | % | Remarks |
| --- | --- | --- | --- | --- | --- |
| 2014 | December | 123 505 262,99 | 123 505 262,99 | 100 | IPC # 1 |
| 2015 | June | 145 333 157,41 | 145 333 157,41 | 100 | IPC # 2 |
|  | September | 140 282 975,29 | 140 282 975,29 | 100 | IPC # 3 |
|  | November | 170 075 757,04 | 170 075 757,04 | 100 | IPC # 4 |
|  | December | 120 277 348,49 | 120 277 348,49 | 100 | IPC # 5 |
|  | Total as 2014-2015y | 699 474 501,21 | 699 474 501,21 | 100 | Including VAT |
| 2016 | January | 155 940 000 | 135 117 345,21 |  | IPC # 6 |
|  | Total as 2014-2016y | 855 414 501,21 | 834 591 846,42 | 97,56 | Including VAT |

7. Interim Payment Certificates

| № | Period | Amount | Remark |
| --- | --- | --- | --- |
| 1 | 14.11.2014 | 123,505,262.99 | Paid |
| 2 | from 08.04.2015 till 08.06.2015 | 145,333,157.41 | Paid |
| 3 | from 08.06.2015 till 08.09.2015 | 140,282,975.29 | Paid |
| 4 | from 08.09.2015 till 25.11.2015 | 170 075 757,04 | Paid |
| 5 | from 26.11.2015 till 22.12.2015 | 120 277 348,49 | Not paid |
| 6 | From 23.12.2015 till 27.01.2016 | 135 117 345, 21 | Not paid |

- Information on executed works as of February:

| Works | Unit of measure | Plan | Actual | % of execution | Advancing/delay |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | quantity | days |
| Earthworks | th.m3 | 697,58 | 285,29 | 40,9 | -411,98 | -150 |
| Subgrade | km | 60 | 5,94 | 9,9 | -54,06 | -180 |
| Subbase | km | 60 | 1,74 | 2,9 | -58,26 | -180 |
| Crushed stone base | km | 60 | 0,59 | 0,98 | -59,41 | -180 |
| Cement concrete pavement | km | 51,34 | 0 | 0 | -51,34 | -140 |
| Culverts | nos | 99 | 3,5 | 3,53 | -95,5 | -170 |
| Bridges and overpasses | nos | 10 | 0,06 | 0,6 | -9,94 | -170 |
| Milling | km | 60 | 15,4 | 25,66 | -49,6 | -110 |
| Dismantling of lean concrete | km | 60 | 13,2 | 22 | -46,8 | -105 |

- Main road-construction materials procurement as of February:

| Material | Unit of measure | Plan | Actual | % of execution | Advancing / delay |
| --- | --- | --- | --- | --- | --- |
| Crushed stone | thous.m3 | 433,92 | 20,11 | 4,6 | -125 |
| Sand and gravel mix | thous.m3 | 566,9 | 79,94 | 14,1 | -120 |
| Sand | thous.m3 | 138,8 | 4,28 | 3,1 | -130 |
| Cement | thous.ton | 98,8 | 2,65 | 2,68 | -130 |
| Reinforced concrete goods | thous.m3 | 6,45 | 1,51 | 23,4 | -120 |

- Personnel mobilization:

| № | Personnel | Requirement for 2016 | Actual as of the current date | Among them |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign | Local |
| 1 | Engineering and administrative personnel | 46 | 31 | 23 | 8 |
| 2 | Laboratory | 12 | 4 |  | 4 |
| 3 | Surveyors | 15 | 5 | 2 | 3 |
| 4 | Specialized machinery operators | 90 | 94 | 5 | 89 |
| 5 | Road workers | 178 | 108 | 52 | 56 |
| 6 | Others | 65 | 108 | 20 | 88 |
| TOTAL | 406 | 350 | 102 | 248 |

- Equipment mobilization:

| № | Equipment | Requirement for 2016 | Actual as of the current date | % | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | Bullldozer | 4 | 3 | 75,0 |  |
| 2 | Excavator | 12 | 12 | 100 |  |
| 3 | Loader | 8 | 4 | 50,0 |  |
| 4 | Grader | 5 | 5 | 100 |  |
| 5 | Roller | 9 | 7 | 77,7 |  |
| 6 | Dump truck | 90 | 80 | 88,8 |  |
| 7 | Water tank | 6 | 3 | 50,0 |  |
| 8 | Asphalt paver | 2 | 1 | 50,0 |  |
| 9 | Concrete paver | 1 | 1 | 100,0 |  |
| 10 | Crane | 7 | 5 | 71,42 |  |
| 11 | Concrete batching plant | 2 | 2 | 100,0 |  |
| 12 | Crushing plant | 2 | 1 | 50,0 |  |
| 13 | Piling machine | 2 | 1 | 50,0 |  |
| 14 | Hauler | 2 | 2 | 100,0 |  |
| 15 | Concrete mixer | 5 | 2 | 40,00 |  |
| 16 | Light vehicles | 16 | 18 | 125 |  |
| 17 | Milling machine | 1 | 1 | 100,0 |  |
| 18 | Others | 61 | 47 | 77 |  |
| TOTAL | 235 | 195 | 82,97 |  |

- Subcontractors mobilization:

«Shyrak-LKS» LLP started the works on communication lines relocation.

«KazTSEP» LLP commenced the main works.

Road construction materials suppliers:

Negotiations for execution of construction and inert materials suppliers are in progress.

Progress of work

Commencement of works – on 8th of April, 2015.

- Milling -  15,8 km.

- Dismantling works on the overpass at PK 715 and Kokparsay bridge at PK 755 are finished.

- Dismantling works on the bridge Sary-Bulaksay at PK 864+68 are began.

- On the overpass at PK715 conducting works on device of grillage, begun works on arrangement of base from GSM (Gravel Sand Mixture) under grillage on supports 2,3 and filling grillage with reinforcement on support 1,5 was finished.

- On the bridge at PK 755 hammering in a pile is begun under support 1 and 2.

- 10 culverts are uncovered. Works on the device of links of cattle pass at PK 717 from a monolithic concrete are begun. 6 culvert links installation has been completed, at PK 699+22, PK 702+93, PK 724+67, PK 731+70 backfilling has been completed. At PK 740+24, PK 762+48, PK799+27 culvert links installation has been completed and backfilling is conducting. At PK 784+27, PK 789+15, PK 815+91, PK 818+67 development of foundation pit is conducting, at PK 829+39, PK 834+64, PK 846+55, PK848+85 device of foundation under the body of culvert is conducting. Contractor has no intention to purchase reinforced concrete products for culverts and bridges as he started to produce them at his production base. Installation of beam workshop for reinforced concrete production of bridge structures has been completed. It was collected framework for beams long a 21 meter in an amount 4 pcs.

- Top soil removal – 13,5 km executed on the left side.

- Trees uprooting has been performed on 17,1 km.

- Connection to the main power supply line of production base is completed.

- Water supply works on the production base are completed by “Nur-AiKen Service” LLP. 350 m depth have been drilled.

Resident Engineer					S. Irmanov