Information for Almaty-Khorgos Roads section km 50,00-111.7

Western Europe – Western China Project in Almaty Oblast

Contractor “Dogus-Gulsan”, Lot 2

General Constractor  –«Dogus Insaat Ve TicaretA.S» JV

Contract– EWRP-50-111.7-ICB(W)-001/2013

Сontract cost  – 23 216 954 457,00 tenge

Contract conclusion date – 17.07.2013г.

Construction period – 30 month.

Disbursed in  2013– 2 574 102 889,4 tenge

Disbursement plan in 2014 – 9 677 560 000,00 tenge

Consultant Engineer  - Dongsung Engineering/Dong Meong/ Zhol-Sapa LLP

Designer – KazNIIiPI «Dortrans»

- Basic Indicators of the Project:

| Length of section, km | 61,7 km |
| --- | --- |
| Culverts, pcs | 150 |
| Bridges, pcs | 6 |
| Overpasses, pcs | 4 |
| Transport interchanges, pcs | 4 |
| Earthworks, th.m3 | 4520,00 |
| Subbase, km/th.m3 | 61,7/1651,88 |
| Base Course from CSSCM, km/th.m3 | 61,7/1279,92 |
| Cement Concrete Pavement, km/th.m3 | 61,7/6552,67 |

- Analyses of work program performance:

| No. | Description | Total under Contract | Performed 2013 | Paln for 2014 | Fact on 08.08.14 |
| --- | --- | --- | --- | --- | --- |
| 1. | Earthworks (th.m3) | 4520,00 |  | 3122,16 | 934,32 |
| 2. | Sub base, km | 62 |  | 18 |  |
| 3. | Base Course from CSSCM, km | 62 |  | 16 |  |
| 4. | Cement concrete pavement, km | 62 |  | 15 |  |
| 5. | Bridge, pcs | 18 |  | 8 |  |
| 6. | Culverts, pcs | 150 |  | 72 | 8 |

Note:

- Material Stockpile for 2014:

| No. | Description | Project requirement | Plan for 2014 | Fact on 08.08.14 | Suppliers |
| --- | --- | --- | --- | --- | --- |
| 1. | Crushed stone, th.m3 | 519,99 | 76,82 | 51,34 |  |
| 2. | Sand, th.m3 | 280,35 | 51,21 | 8,13 |  |
| 3. | Sand Gravel Mixture, th.m3 | 1178,20 | 205,21 | 245,27 |  |
| 4. | Cement, th.m3 | 184,68 | 24,52 | 0,46 |  |
| 5. | Reinforced Cement Product, th.m3 | 30,465 | 16,74 | 10,35 | “AZMK” |
| 6. | Fitting (anchor) t. | 210,0 | 50,27 |  |  |
| 7. | Fitting (dowel) t. | 1000,0 | 238,27 |  |  |

Note:

- Mobilization of Equipments:

| No. | Description | Requirement for 2014 | Fact on 08.08.14 | Among them: |
| --- | --- | --- | --- | --- |
|  |  |  |  | Own | subcont/rented |
| 1 | Dozer | 4 | 5 | 4 | 1 |
| 2 | Excavator | 12 | 17 | 10 | 7 |
| 3 | Loader | 11 | 12 | 9 | 1 |
| 4 | Grader | 5 | 8 | 5 | 3 |
| 5 | Rollers | 14 | 11 | 8 | 3 |
| 6 | Dump truck | 70 | 66 | 36 | 30 |
| 7 | Water bawser | 4 | 2 | 1 | 1 |
| 8 | Fuel tanks | 3 | 2 | 2 |  |
| 9 | Paver | 3 | 1 | 1 |  |
| 10 | Concrete paver | 1 |  |  |  |
| 11 | Crane | 4 | 2 | 2 |  |
| 12 | Batching Plant | 3 | 2 | 2 |  |
| 13 | Crusher Plant, Screening Plant | 1 |  |  |  |
| 14 | Piling machine | 1 | 1 | 1 |  |
| 15 | Trailer | 4 | 1 | 1 |  |
| 16 | Concrete mixer | 5 | 2 | 2 |  |
| 17 | Car | 34 | 33 | 33 |  |
| 18 | Others | 21 | 61 | 59 | 4 |
| TOTAL | 200 | 226 | 176 | 50 |

- Personnel Mobilization:

| No. | Description | Requiments for 2014 | Fact on 08.08.14 г. | Among them: |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign | Local |
| 1 | Engineers | 3 | 6 | 2 | 4 |
| 2 | Laboratory | 5 | 13 | 4 | 9 |
| 3 | Land Surveyors | 10 | 15 | 4 | 11 |
| 4 | Equipments operation | 70 | 26 | 6 | 20 |
| 5 | Drivers of dump truck | 70 | 67 |  | 67 |
| 6 | Road workers | 283 | 366 |  | 366 |
| 7 | Service personnel | 120 | 79 | 40 | 39 |
| TOTAL | 553 | 571 | 55 | 516 |

- Subcontractors:

| No. | Subcontractors | Type of work | Section from km – to km | Remarks |
| --- | --- | --- | --- | --- |
| 1 | “Siltek” LLP | Earthworks | km 50-111,7 | Under consideration |
| 2 | “Latona” LLP | Bridges and Interchanges | PK 612 | Approved, not mobilized |
| 3 | “AtlantStroyService” LLP | Earthworks | km 50-111,7 | Approved, not mobilized |
| 4 | ”VostokAvtodor” JC | Earthworks | km 50-111,7 | Not mobilized |
| 5 | “EW-INTERCOMPEX’ LLP | Earthworks | km 50-111,7 | Approved, not mobilized |
| 6 | “NikStroyMost” LLP» | Bridges and culverts | km 50-111,7 | approved |
| 7 | “Long City” LLP | Earthworks | Km 60 - km69 | approved |
| 8 | “Otau-Kurylys” LLP | Relocation of communications | Km 50- km 111,7 | approved |
| 9 | " Techstroypodryad" LLP | Earthworks | Km 80-km89 | approved |

- Issues of Concern:

| No. | Issues of Concern | Ways of solution |
| --- | --- | --- |
| 1 | Backlog of subgrade filling | Proper organization and Skilled professionals |
| 2 | Backlog under construction of culverts | Proper organization and Skilled professionals |
| 3 | Backlog under construction bridges, the lack of additional pile drivers | Proper organization and Skilled professionals, mobilization of piling machine |
| 4 | The delay of installation and launching of concrete mixing plant, crushing and screening plant | Attraction of skilled professionals |
| 5 | Lot of issues in the working drawing | Removal of discrepancies in design drawing |
| 6 | The executive documentation preparation | Attraction of skilled professionals |

- Removal of fertile coarse is on the PK769+00-786+00,507+00-509+00,664+00-667+00,740+00-741+00.

- Work on the bridges at PK625+90 was started, piles in the amount of 144 pieces were driven. 192 piles are driven at PK762+70.

- Work at 43 culverts is being carried out under borrow pit working out, foundation filling under pipe placing, mounting pipe. Construction of crushed stone sand mix.

- Soil export under subgrade at km 60-68,68-70,74-76,80-90 is being carried out. As of 08.08.2014, 934 320,0 m3 loose soil was exported.