Information

On Almaty-Khorgos Roads section km 111.7-171.1

Western Europe – Western China Project in Almaty Oblast

Contractor “Todini/Impregilio/Kazakhdorstroi” JV, Lot 3

General Contractor -  “Todini/Impregilio/Kazakhdorstroi  JV (Italy/Kazakhstan)

Contract             -   EWRP- 111,7- 171,1- ICB(W)-001/2013

Сontract cost  -  14 683 716 863. 00 tenge

Contract conclusion date -  30.07.2013

Construction period -  months

Disbursement in 2013 - 1 586 696 997

Disbursement plan in 2014 - 4 895 530 000

Consultant Engineer  - Dongsung Engineering/Dong Meong/ Zhol-Sapa LLP

Designer - Kazdorproject LLP

- Basic Indicators of the Project:

| Length of section, km | 59,51 |
| --- | --- |
| Culverts, pcs | 64 |
| Bridges, pcs | - |
| Overpasses, pcs | - |
| Traffic interchanges, pcs | 1 |
| Earthworks, th.m3 | 3785,47 |
| Subbase, km/th.m3 | 54,51 / 607,86 |
| Base Course, km/th.m3 | 59,51 / 256,30 |
| Cement Concrete Pavement, km/th.m3 | 59,51 / 286,28 |

- Analyses of work program performance:

| No. | Description | Total in Contract | Plan for 2014 | Daily rate th.m3 | Daily embankment, th.m3 | Actual as of today th.m3 |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 06.08. | 07.08 | 08.08. |  |
| 1. | Earthworks (th.m3) | 3785,47 | 3785,47 | 25,00 | 12,05 | 13,12 | 11,14 | 1651,81 |
| 2. | Sub base, km | 59,40 | 20,00 | 1,68 | 0,61 | 0,09 | 0,00 | 7,64 |
| 3. | Base Course, km | 59,40 | 18,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 |
| 4. | Cement concrete pavement, km | 59,40 | 6,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 |
| 5. | Bridges, pcs | 1,00 | 1,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 |
| 6. | Culverts, pcs | 64,00 | 64,00 | 0,00 | - | - | - | 17,00 |

- Material Stockpile for 2013:

| No. | Description | Project requirement | Plan for 2014 | Actual as of today | % | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Crushed stone, th.m3 | 672,00 | 129,70 | 26,20 | 20% | Own |
| 2. | Sand, th.m3 | 128,73 | 32,32 | 0,00 |  |  |
| 3. | Sand Gravel Mixture, th.m3 | 607,86 | 204,66 | 3,84 | 2% | Own |
| 4. | Cement, th.m3 | 143,14 | 36,15 | 0,00 |  |  |
| 5. | R/C elements, th.m3 | 3,85 | 3,57 | 0,54 | 15% | AZMK |

- Personnel Mobilization:

| No. | Description | Requirement for 2014 | Actual of today | Among them: |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign | Local |
| 1 | Engineers | 102 | 85 | 12 | 41 |
| 2 | Laboratory | 18 | 9 |  | 9 |
| 3 | Surveyors | 20 | 11 | 1 | 10 |
| 4 | Equipments operators | 158 | 93 |  | 93 |
| 5 | Drivers of dump trucks | 142 | 91 |  | 91 |
| 6 | Road Workers | 147 | 23 |  | 23 |
| 7 | Service Personnel | 105 | 56 | 12 | 44 |
| TOTAL | 692 | 336 | 20 | 316 |

- Mobilization of Equipments:

| No. | Description | Requirement for 2014 | Actual of today | Among them: |
| --- | --- | --- | --- | --- |
|  |  |  |  | Own | Subcon/ Rented |
| 1 | Dozer | 10 | 9 | 1 | 8 |
| 2 | Excavator | 15 | 13 |  | 13 |
| 3 | Loader | 12 | 8 |  | 8 |
| 4 | Autograder | 12 | 6 | 2 | 4 |
| 5 | Rollers | 17 | 13 | 4 | 9 |
| 6 | Dump trucks | 120 | 56 | 1 | 55 |
| 7 | Water tanks | 10 | 9 |  | 9 |
| 8 | Fuel tanks | 5 | 6 |  | 6 |
| 9 | Asphalt Paver | 2 |  |  |  |
| 10 | Concrete Paver | 1 |  |  |  |
| 11 | Autcrane | 4 | 4 | 1 | 3 |
| 12 | Batching Plant | 3 |  |  |  |
| 13 | Crusher Plant, Screening Plant | 1 | 1 | 1 |  |
| 14 | Piling machine | 1 |  |  |  |
| 15 | Trailer | 1 |  |  |  |
| 16 | Concrete Mixer | 2 |  |  |  |
| 17 | Light cars |  |  |  |  |
| 18 | Miscellaneous | 15 | 15 | 8 | 7 |
| TOTAL | 231 | 140 | 18 | 122 |

- Subcontractor Companies:

| No. | Description of Subcontractors | Type of work | section km | Notes |
| --- | --- | --- | --- | --- |
| 1 | AZMK Service LLP | bridges and overpasses | км 0,0- км 0,0 | approved |
| 2 | Vesta Trans Service LLP | Earthworks | км 6 – км24 | approved |
| 3 | Zhanbota Trans Service LLP | Earthworks | км 0 – км6; км54-км59 | approved |
| 4 | Montazhnik LLP | Culverts construction | 64 шт/pcs | approved |
| 5 | Azia Energo Stroi LLP | Relocation of PTL | 111,7-171,1 | approved |
| 5 | Almate Sviz Stroi LLP | Relocation of | 111,7-171,1 | approved |