INFORMATION                                                As of 06.10.2016

Under the Project reconstruction of International Transit Corridor Western Europe -Western China, bridge over ILI river km 283 (Lot8) “Almaty- Kokpek-Chunja-Koktal-Khorgos”

- Contract: EWRP – Ili bridge (km 283) –ICB(W)-001/2013

- General Contractor: «OHL ZS»(Czech)/Subcontractor LLP “MO-25” (Kazakhstan)

- Contract amount: 6 394 053 055 tenge

- Contract amount after variation: 6 916 834 612,88 tenge (taking into account VO No.4)

- Construction period: 30 months (900 calendar days)

Commencement date: 4 October 2013

Completion date:  31 April 2016

- Disbursed up to 2016: 5 442 047 586,22 tenge

- Plan for 2016 disbursement: 1 270 325 458,03 tenge (taking into account VO)

- Consultant Engineer: DongSung Engineering Co. Ltd/Dong Myeong Enginering Consultants and Architecture Co. Ltd./ “Zhol Sapa” LLP

- Designer: “Kazakhstan zholdary” JSC

- Main indicators

Total number of artificial structures: 1-bridge over Ili river

| Name | Quantity | Name | Quantity |
| --- | --- | --- | --- |
| Bridges | 1 | Overpasses | 0 |
| Cattlepasses | 0 | Interchanges | 0 |

  - Bridge works

| № | Work description | Total uner Contract | Performed up to 2016 | 2016 |
| --- | --- | --- | --- | --- |
|  |  |  |  | Plan | Fact | % |
| 1 | Site clearance, m2 | 445 874 | 236 595 | 209 279 | 44 851 | 21 |
| 2 | Base course from crushed stone, m3 | 2 680 | 2 273 | 407 | 51 | 13 |
| 3 | Construction of piles , m3 | 9 034 | 9 034 | 0 | 0 | 100 |
| 4 | Construction of foundation grille, m3 | 4 857 | 4 857 | 0,015 | 0,015 | 100 |
| 5 | Construction of the body of pier), m3 | 1 822 | 1 822 | 0 | 0 | 0 |
| 6 | Reinforcing | 1 382,90 | 1 347,9 | 35,000 | 26,737 | 76 |
| 7 | Assembly of steel superstructures, ton | 3 222 | 3 222 | 0 | 0 | 100 |
| 8 | Installation of handrails, r.m. | 2 859 | 1 384 | 1 475 | 1 460 | 99 |
| 9 | Installation of guard rails, r.m. | 2 800 | 0 | 1 540 | 1 260 | 0 |
| 10 | Precast reinforced concrete slabs at site of connection to bridges, m3 | 183 | 177 | 6 | 6 | 100 |
| 11 | Insitu reinforced concrete slope strengthening of class B20 F200, m3 | 1 038 | 386 | 652 | 585 | 90 |
| 12 | Precast r/c sidewalk blocks, pcs. | 448 | 0 | 448 | 448 | 100 |
| 13 | Repair of slabs of carriageway, m2 | 7 649 | 0 | 7 649 | 7 137 | 93 |
| 14 | Repair of bedstones fo interior support, pcs. | 30 | 0 | 30 | 16 | 53 |
| 15 | Painting works under new bridge metal span, m2 | 52 966 | 23 520 | 29 446 | 6 826 | 23 |
| 16 | Repair, cleaning and painting of existing bridge, m2 | 20 154 | 0 | 20 154 | 5 668 | 28 |
| 17 | Waterproof finishing of bridge deck, m2 | 16 942 | 10 185 | 6 757 | 6 757 | 100 |
| 18 | Pavement works applying bitumen, m3 | 1 636 | 490 | 1 146 | 134 | 12 |

- Material procurement for 2016:

| № | Description | Total under Contract | 2016 | Suppliers |
| --- | --- | --- | --- | --- |
|  |  |  | Plan | Actual | % |  |
| 1. | Crushed stone thous.m3 | 19,44 | 2,216 | 0,857 | 39 | “Dostar S” LLP |
| 2. | Sand thous.m3 | 5,88 | 3,000 | 1,204 | 40 | “Sunkar” LLP |
| 3. | Sand gravel mix thous.m3 | 16,14 | 2,082 | 1,802 | 87 | “Aluan A” LLP |
| 4. | Cement ton | 7,05 | 1,388 | 0,593 | 55 | “Standard” LLP |
| 5. | Reinforced concrete products pcs. | 448 | 448 | 448 | 100 | Industrial base MO-25 |
| 6. | Re-bar and embedded parts, thous.ton | 1,36 | 0,043 | 0,025 | 58 | “Modul” LLP |

- Staff mobilization:

| № | Description | Requirement 2016 | As of 06.10.2016 | Including: |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign | Local |
| 1 | TED | 25 | 12 | 4 | 8 |
| 2 | Laboratory | 5 | 3 | 1 | 2 |
| 3 | Survey | 2 | 2 | 0 | 2 |
| 4 | Operators | 36 | 34 | 0 | 34 |
| 5 | Truck drivers | 8 | 16 | 0 | 16 |
| 6 | Laborers | 74 | 63 | 0 | 63 |
| 7 | Service staff | 6 | 5 | 0 | 5 |
| Total | 156 | 135 | 5 | 130 |

- Equipment mobilization:

| № | Description | Requirement for 2016 | As of 06.10.2016 | OHL ZS JSC |
| --- | --- | --- | --- | --- |
|  |  |  |  | Contractor | Subcontractor |
| 1 | Bulldozer | 1 | 0 | - | 0 |
| 2 | Excavator | 1 | 1 | - | 1 |
| 3 | Loader | 1 | 1 | - | 1 |
| 4 | Auto grader | 0 | 0 | - | 0 |
| 5 | Rollers | 5 | 4 | - | 4 |
| 6 | Dump trucks | 2 | 16 | - | 16 |
| 7 | Water truck | 1 | 1 | - | 1 |
| 8 | Asphalt paver | 2 | 1 | - | 1 |
| 9 | Crane | 3 | 1 | - | 1 |
| 10 | Cement Concrete plant | 1 | 1 | - | 1 |
| 11 | Pile driver | 0 | 0 | - | 0 |
| 12 | Creeper | 1 | 0 | - | 0 |
| 13 | Concrete mixer | 2 | 1 | - | 1 |
| 14 | Vehicle | 5 | 7 | 5 | 2 |
| 15 | Others | 14 | 14 | - | 14 |
| Total | 39 | 48 | 5 | 43 |

- Maintenance

| Name | Under ToR/Contract | Actual |
| --- | --- | --- |
| Accomodation | 10 | 10 |
| Vehicle | 3 | 3 |
| Office | 1 | 1 |
| Special clothes | 10 | 10 |

- Issues of concern (production):

| Content of issue | Ways of resolution |
| --- | --- |
| 1.Variation Order №-4 (Repair of existin gbridge) | 1.Approved. |
| 2. Variation Order №-2 | 2. Approved. |
| 3. Variation Order №-3 (Painting works of new bridge) | 3. Approved. |