Information sheet

South-West Roads Project International Transit corridor Western Europe – Western Chine (CAREC 1B), Reconstruction (construction) of “Almaty-Kokpek-Chunja-Koktal-Khorgos”

Km-283 (Lot-8) in Almaty region

As of 14.03.2017

- Contract: EWRP – Ili bridge (km 283) –ICB(W)-001/2013

- General Contractor:  «OHL ZS» JSC (Czech Republic)/ Subcontractor «МО-25» LLP (Kazakhstan)

- Contract amount: 6 394 053 055 KZT

- Contract amount with VO: 6 982 414 184.74 KZT

(including VO)

- Construction period: 30 months (900 calendar days)

Commencement date: 4 October 2013

Completion date:  2017

- Purchased until 2017: 6 752 625 768.18 KZT

- To be purchased in 2017: 229 788 416.56 KZT

- Consultant Engineer: DongSung Engineering Co. Ltd/Dong Myeong Enginering Consultants and Architecture Co. Ltd./ “Zhol Sapa” LLP

- Designer: “Kazakhstan Zholdary”

- Main indicator of design

Total number of Artificial Structures: 1-Bridge over Ili river

New bridge:  Length: 41,96 + (7 х 85,44) + 41,96 = 682 m

Width: 14,2+(2 х 0,75 - sidewalk)

Bridge type: Box-shaped continuous

- Work progress schedule performance details:

| № | Description | Performed % |
| --- | --- | --- |
| 1 | New bridge over Ili r. | Support | 100% |
|  |  | Superstructure | 100% |
|  |  | A/c pavement | 85% |
|  |  | Strengthening works | 100% |
| 2 | Repair of the existing bridge | Removal of the existing a/c pavement, blocks | 100% |
|  |  | Repair of support of intermediate piers | 66% |
|  |  | A/c pavement | 100% |

2.1 Progress

| № | Item | Total under the contract | Purchased in 2013-2016 г. | Plan for 2017 (Mil. KZT) | Performed |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Plan | Done as of the current date | % | Amount | % |
| 1. | Physical progress, (Mil. KZT) | 6 234.30 | 5 996.44 | 237.86 | 0 | 0 | 5 996.44 | 96 |
| 2. | Progress in money equivalent, (Mil. KZT ) | 6 982.41 | 6 752.63 | 229.78 | 0 | 0 | 6 752.63 | 97 |

2.2 Bridge works

| Work item | Total under the contract | Completed until 2017 | 2017 | % |
| --- | --- | --- | --- | --- |
|  |  |  | Plan | Actual |  |
| Site clearance, % | 100 | 50 | 50 | 35 | 70 |
| Crushed stone base, m3 | 2 680 | 2 680 | 0 | 0 | 100 |
| Installation of piles, m3 | 9 034 | 9 034 | 0 | 0 | 100 |
| Footings, m3 | 4 857 | 4 857 | 0 | 0 | 100 |
| Construction (pier body), m3 | 1 822 | 1 822 | 0 | 0 | 100 |
| Reinforcing, (tons) | 1 384,700 | 1 349,678 | 4,820 | 1,739 | 36 |
| Construction of beams, (tons) | 3 222 | 3 222 | 0 | 0 | 100 |
| Side walk blocks (l.m.) | 2 868 | 2 868 | 0 | 0 | 100 |
| Guard rails installation (l.m.) | 2 800 | 2 800 | 0 | 0 | 100 |
| Subplates installation | 183 | 183 | 0 | 0 | 100 |
| Monolithic concrete slope protection type В20 F200 (м3) | 1 310 | 1 310 | 0 | 0 | 100 |
| Precast r/c sidewalk (pcs) | 448 | 448 | 0 | 0 | 100 |
| Repair of bridge deck slab (m2) | 7 649 | 7 649 | 0 | 0 | 100 |
| Repair of bearing block of intermediate piers (pcs) | 30 | 30 | 0 | 0 | 100 |
| Painting works on spans (м2) | 51 666 | 51 124 | 542 | 0 | 0 |
| Repairing, clearing and painting of the existing bridge (m2) | 20 154 | 20 154 | 0 | 0 | 100 |
| Waterproofing (м2) | 16 942 | 16 942 | 0 | 0 | 100 |
| Works with bitumen (м3) | 2 019 | 1 665 | 354 | 0 | 0 |
| Replacement of concrete of pier body (16,15,14,13,12,11, 10,5,4,2) | 480 | 230 | 250 | 90 | 36 |
| Power supply | 100% | 40% | 60% | 55% | 92 |
| Stone apron m3 | 537 | 46 | 491 | 129 | 26 |
| Strengthening with stone (filling washouts) m3 | 2 040 | 0 | 2 040 | 0 | 0 |

9. Road construction materials stocking:

| № | Material name | Total under the contract | 2017 | Supplier |
| --- | --- | --- | --- | --- |
|  |  |  | Plan | Actual as of a current date | % |  |
| 1. | Crushed stone, thous.m3 | 19,44 | 0,136 | 0,42 | 31 | «Dostar-S» LLP |
| 2. | Sand, thous.m3 | 5,88 | 0 | 0 | 100 | «Sunkar» LLP |
| 3 | Quarry stone, thous.m3 | 0,538 | 0,491 | 0,385 | 72 | «City-Mall-Energo» LLP |
| 4. | GSM, thous.m3 | 16,14 | 2,082 | 2,802 | 100 | «Aluan A» LLP |
| 5. | Cement, thous. tons | 7,05 | 0,132 | 0,41 | 31 | «Standard» LLP |
| 6. | Precast RCP, (pcs) | 448 | 456 | 456 | 100 | Industrial base of «МО-25» LLP |
| 7. | Reinforcement and embedded details, thous. tons | 1,36 | 0,005 | 0,005 | 100 | «Module» LLP |

10. Personnel Authorization:

| № | Item | Requirement for 2017 | Actual | Of which |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign | Local |
| 1. | Engineers, administrative personnel | 12 | 11 | 2 | 9 |
| 2. | Laboratory | 2 | 2 | 0 | 2 |
| 3. | Lad surveyer | 2 | 2 | 0 | 2 |
| 4. | Operators of machines, welders | 12 | 13 | 0 | 13 |
| 5. | Dump truck drivers | 4 | 2 | 0 | 2 |
| 6. | Workers | 40 | 39 | 0 | 39 |
| 7. | Other | 6 | 5 | 0 | 5 |
| TOTAL | 78 | 74 | 2 | 72 |

- Mobilization of machines:

| № | Item | Requirement for 2017 | Actual | «OHL ZS» JSC |
| --- | --- | --- | --- | --- |
|  |  |  |  | Contractor | Subcontractor |
| 1. | Dozer | 1 | 0 | - | 0 |
| 2. | Excavator | 1 | 1 | - | 1 |
| 3. | Loader | 1 | 1 | - | 1 |
| 4. | Grader | 0 | 0 | - | 0 |
| 5. | Roller | 5 | 0 | - | 0 |
| 6. | Dump trucks | 2 | 2 | - | 2 |
| 7. | Distributing tank | 1 | 1 | - | 1 |
| 8. | Asphalt paver | 2 | 0 | - | 0 |
| 9. | Crane | 2 | 1 | - | 1 |
| 10. | Concrete plant | 1 | 1 | - | 1 |
| 11. | Drilling machine | 0 | 0 | - | 0 |
| 12. | Trawl net | 1 | 0 | - | 0 |
| 13. | Mixer | 2 | 1 | - | 1 |
| 14. | Motor car | 1 | 7 | 5 | 2 |
| 15. | Others | 14 | 16 | - | 16 |
| Total | 34 | 31 | 5 | 26 |