INFORMATION                                                As of 26.01.2017

Under the Project reconstruction of International Transit Corridor Western Europe -Western China, bridge over ILI river km 283 (Lot8) in Almaty region

- Contract: EWRP – Ili bridge (km 283) –ICB(W)-001/2013

- General Contractor: «OHL ZS»(Czech Republic)/Subcontractor LLP “MO-25” (Kazakhstan)

- Contract amount: 6 394 053 055 tenge

- Contract Amount after Variation: 6 916 834 612.88 tenge (taking into account VO No. 4)

- Construction period: 30 months (900 calendar days)

Commencement date: 4 October 2013

Completion date:  2017

- Disbursed up to 2017: 6 716 013 118.21 tenge

- Disbursement Plan for 2017: 200 821 494.67 tenge (taking into account variation order)

- Engineer: DongSung Engineering Co. Ltd/Dong Myeong Enginering Consultants and Architecture Co. Ltd./ “Zhol Sapa” LLP

- Designer: “Kazakhstan zholdary” JSC

- Main indicators

Total number of artificial structures: 1-bridge over Ili river

| Name | Quantity | Name | Quantity |
| --- | --- | --- | --- |
| Bridges | 1 | Overpass | 0 |
| Cattlepass | 0 | Interchanges | 0 |

  - Bridge works

| № | Work description | Total under Contract | Performed up to 2017 | 2017 |
| --- | --- | --- | --- | --- |
|  |  |  |  | Plan | Fact | % |
| 1 | Site clearance, m2 | 100 | 50 | 50 | 35 | 70 |
| 2 | Base from crushed stone, m3 | 2680 | 2680 | 0 | 0 | 100 |
| 3 | Construction of piles, m3 | 9 034 | 9 034 | 0 | 0 | 100 |
| 4 | Construction of foundations, m3 | 4 857 | 4 857 | 0 | 0 | 100 |
| 5 | Construction of the body of pier), m3 | 1 822 | 1 822 | 0 | 0 | 100 |
| 6 | Reinforcing, ton | 1 384.700 | 1 349.678 | 4,820 | 0 | 0 |
| 7 | Assembly of steel superstructures, ton | 3 222 | 3 222 | 0 | 0 | 100 |
| 8 | Installation of handrails, rm | 2 868 | 2 868 | 0 | 0 | 100 |
| 9 | Installation of guard rails, rm | 2 800 | 2 800 | 0 | 0 | 100 |
| 10 | Precast reinforced concrete slabs on area of bridge connection, m3 | 183 | 183 | 0 | 0 | 100 |
| 11 | In-situ reinforced concrete strengthening of slopes claa B20 F200, m3 | 1 310 | 1 310 | 0 | 0 | 100 |
| 12 | Precast reinforced concrete paving blocks, pcs | 448 | 448 | 0 | 0 | 100 |
| 13 | Repair of slabs of carriageway, m2 | 7 649 | 7 649 | 0 | 0 | 100 |
| 14 | Repair of abutment stone of intermediate support, pcs. | 30 | 30 | 0 | 0 | 100 |
| 15 | Painting works of new bridge, metal span, m2 | 51 666 | 51 124 | 542 | 0 | 0 |
| 16 | Repair, cleaning and painting of existingt bridge, m2 | 20 154 | 20 154 | 0 | 0 | 100 |
| 17 | Waterproofing of bridge road bed, m2 | 16 942 | 16 942 | 0 | 0 | 100 |
| 18 | Pavement works with application of bitumen, m3 | 2 019 | 1 665 | 354 | 0 | 0 |
| 19 | Replacement of concrete of support body | 480 | 186 | 294 | 30 | 11 |
| 20 | Electricity supply of brdge | 100% | 40% | 60% | 20% | 40 |

- Material procurement for 2017:

| № | Description | Total under Contract | 2017 | Suppliers |
| --- | --- | --- | --- | --- |
|  |  |  | Plan | As of date | % |  |
| 1. | Crushed stone thous.m3 | 19,44 | 0,166 | 0,42 | 26 | “Dostar S” LLP |
| 2. | Sand thous. m3 | 5,88 | 0,131 | 0 | 0 | “Sunkar” LLP |
| 3. | Sand gravel mix thous.m3 | 16,14 | 2,082 | 2,802 | 100 | “Aluan A” LLP |
| 4. | Cement thous.ton | 7,05 | 0,131 | 0,41 | 32 | “Standard” LLP |
| 5. | Reinforced concrete products pcs. | 448 | 456 | 456 | 100 | Industrial base “MO-25” LLP |
| 6 | Steel superstructures and embedded parts, thous. tons | 1,36 | 0,043 | 0,043 | 100 | “Modul” LLP |

- Staff mobilization:

| № | Description | Requirement 2017 | As of date | Including: |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign | Local |
| 1 | TED | 10 | 11 | 3 | 8 |
| 2 | Laboratory | 2 | 2 | 0 | 2 |
| 3 | Survey | 2 | 2 | 0 | 2 |
| 4 | Operators, weldors | 18 | 13 | 0 | 13 |
| 5 | Truck drivers | 2 | 2 | 0 | 2 |
| 6 | Laborers | 95 | 65 | 0 | 65 |
| 7 | Service staff | 5 | 5 | 0 | 5 |
| Total | 134 | 100 | 3 | 97 |

- Equipment mobilization:

| № | Description | Requirement for 2016 | As of date | OHL ZS |
| --- | --- | --- | --- | --- |
|  |  |  |  | Contractor | Subcontractor |
| 1 | Bulldozer | 1 | 0 | - | 0 |
| 2 | Excavator | 1 | 1 | - | 1 |
| 3 | Loader | 1 | 1 | - | 1 |
| 4 | Auto grader | 0 | 0 | - | 0 |
| 5 | Rollers | 5 | 0 | - | 0 |
| 6 | Dump trucks | 2 | 1 | - | 1 |
| 7 | Water truck | 1 | 1 | - | 1 |
| 8 | Asphalt paver | 2 | 0 | - | 0 |
| 9 | Crane | 3 | 1 | - | 1 |
| 10 | Cement Concrete plant | 1 | 1 | - | 1 |
| 11 | Pile driver | 0 | 0 | - | 0 |
| 12 | Creeper | 1 | 0 | - | 0 |
| 13 | Concrete mixer | 2 | 1 | - | 1 |
| 14 | Vehicle | 5 | 7 | 5 | 2 |
| 15 | Others | 6 | 14 | - | 14 |
| Total | 31 | 28 | 5 | 23 |

- Maintenance

| Name | Under Specification/Contract | Actual |
| --- | --- | --- |
| Flats | 10 | 6 |
| Cars | 3 | 3 |
| Office | 1 | 1 |
| Special clothes | 0 | 0 |