Information as of 29.10.2015                                                                                                                                                         under “Western Europe – Western China”

«Западная Европа – Западный Китай»project implementation in Almaty region                                         by Contractor "OHL ZS" JSC, lot-8

Contract: EWRP – Bridge Ili (km 283) –ICB(W)-001/2013

General Contractor: "OHL ZS" JSC (Czech Republic)

Contract amount: 6 394 053 055 tenge

(amount after variation change – 6 134 652 965,52 tenge)

Construction term: 30 months (900 calendar days)

Construction commencement date: 4 October 2013.

Completion date: 4 April 2016.

Disbursed until 2015 : 3 565 803 078,33 tenge

Disbursement plan for 2015: 1 952 540 000 tenge

Disbursed in 2015:  1 588 323 914 tenge

Engineer CSC: DongSung Engineering Co. Ltd/Dong Myeong Enginering Consultants and Architecture Co. Ltd./ «Zhol Sapa» LLP

Designer: «Kazakhstan Zholdary» JSC

As-built documentation:

Number given for week:   	  instructions: 0 pc.;   letters: 1 pc.

Term of delivery of work program and Quality control plan 4 April 2016.

Facility being constructed

1. Main project features

Total number of Engineering structures: 1

| Name | Quantity | Name | Quantity |
| --- | --- | --- | --- |
| Bridges | 1 | Overpasses | 0 |
| Cattle passes | 0 | Interchanges | 0 |

  - Bridge works

| № | Name of work | Total under Contract | Performed in 2013-2014 | 2015 | % |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Plan | Actual |  |
| 1. | Territory clearing , m2 | 100 | 50 | 50 | 0 | 50 |
| 2. | Base from crushed stone, m3 | 2 750 | 0 | 2 685 | 2 235 | 83 |
| 3. | Pile consrtuction, m3 | 9 034 | 8 102 | 932 | 932 | 100 |
| 4. | Construction of foundation frame, m3 | 4 857 | 2 417 | 2 440 | 2 432 | 99 |
| 5. | Construction of (body of pier), m3 | 1 822 | 535 | 1 290 | 1 290 | 100 |
| 6. | Reinforcing | 1 363 | 1 106 | 257 | 238 | 93 |
| 7. | Assembly of steel superstructures, tons | 3 222 | 0 | 3 222 | 3 222 | 100 |
| 8. | Installation of handrails | 2 768 | 0 | 2 768 | 0 | 0 |
| 9. | Installation of guardrails | 2 800 | 0 | 2 800 | 0 | 0 |
| 10. | Precast reiforced concrete slabs at brige joint areas | 0,183 | 0 | 0,183 | 0,130 | 71 |
| 11. | In-situ reinforced concrete slope strengthening of class В20 F200 | 1,028 | 0 | 0,155 | 0,873 | 15 |
| 12. | Painting works of metal superstructure | 52 966 | 0 | 52 966 | 6 249 | 12 |

- Procurement of materilas for 2015:

| № | Description of material | Total under Contract | 2015 | Suppliers |
| --- | --- | --- | --- | --- |
|  |  |  | Plan | Actual to date | % |  |
| 1. | Crushed stone, thous. m3 | 17,68 | 9,464 | 7,462 | 79 | «Dostar – S» LLP |
| 2. | Sand, thous. m3 | 8,21 | 2,274 | 1,864 | 82 | «Sunkar» LLP |
| 3. | GSM, thous. m3 | 14,64 | 14,526 | 13,878 | 95 | «Aluan А» LLP |
| 4. | Cement, thous. tons | 7,10 | 2,340 | 2,012 | 86 | «Standard» LLP |
| 5. | RCP, thous. m3 | 192 | 192 | 0 | 0 | Production base «МО-25» LLP |
| 6. | Fittings and embedded items, thous. tons | 1,36 | 0,142 | 0,138 | 97 | «Modul» LLP |

- Personnel involvement:

| № | Name | Need for 2015 | Actual to date | Of which |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign | Local |
| 1 | TED | 25 | 25 | 7 | 18 |
| 2 | Laboratory | 5 | 5 | 1 | 5 |
| 3 | Survey | 2 | 2 | 0 | 1 |
| 4 | Equipmetn operators and welders | 36 | 36 | 0 | 36 |
| 5 | Dumptruck drivers | 8 | 13 | 0 | 13 |
| 6 | Workers | 90 | 90 | 0 | 90 |
| 7 | Others | 6 | 6 | 0 | 6 |
| TOTAL | 172 | 177 | 8 | 169 |

- Equipment mobilization:

| № | Name | Need for 2015 | Actual to date | «OHL ZS» JSC |
| --- | --- | --- | --- | --- |
|  |  |  |  | Contractor | Subcontractor |
| 1 | Dozer | 2 | 2 | - | 2 |
| 2 | Excavator | 1 | 1 | - | 1 |
| 3 | Loader | 2 | 2 | - | 2 |
| 4 | Auto grader | 0 | 0 | - | 0 |
| 5 | Roller | 2 | 1 | - | 1 |
| 6 | Dump trucks | 4 | 3 | - | 3 |
| 7 | Water truck | 1 | 1 | - | 1 |
| 8 | Asphalt paver | 0 | 0 | - | 0 |
| 9 | Crane | 5 | 3 | - | 2 |
| 10 | CCP | 1 | 1 | - | 1 |
| 11 | Pile driver | 1 | 0 | - | 0 |
| 12 | Creeper | 1 | 1 | - | 1 |
| 13 | Concrete mixer | 2 | 2 | - | 2 |
| 14 | Vehicle | 6 | 6 | 4 | 4 |
| 15 | Others | 16 | 20 | - | 19 |
| TOTAL | 44 | 43 | 4 | 39 |

- Maintenance

| Name | Under Tech. Specification of Contract | Actual |
| --- | --- | --- |
| Flats | 10 | 10 |
| Vehicles | 3 | 3 |
| Office | 1 | 1 |
| Work clothes | 10 | 10 |

- Issues of concern (production):

| Content of issue | Ways of solution |
| --- | --- |
| 1.Existing bridge (repair is required) | 1.Without objection, but without increase of endorsed cost. |
| 2.Variation order №-2 | 2.Under consideration of Engineer. |
| 3. Variation order №-3 | 3.Remarks under quantity calculation. |

- Issues of concern (staff)

| Content of issue | Ways of solution |
| --- | --- |