INFORMATION

«Western Europe – Western China» road international transit corridor reconstruction project km 632-674 (LOT 002) in South-Kazakhstan region

Length 40,4km.

as on  September 2

Construction Supervision Consultant – Temelsu International Engineering Services Inc, in association with «ConsultLTD» LLP (Turkey/Kazakhstan)

General Contractor – Sinohydro Corporation&Limited (China),

Shymkent, "Nauryz" microdistrict, house 95

Contract -  SWRP-632-674-ICB(W)-002/2013 dated 27.06.2013

Contract amount –  14 096 302 009,00 tenge;

Work start date –  Notification about work start is given by the Engineer from 10.09.2013

Construction period – 24 months (730 days)

Plan on 2013 - 1,690 billion tenge, used on amount 1,314 billion tenge. In 2014 6 295,6 million tenge is used. In 2015 1 686,0 million tenge is used. Total from construction start 9 677,9 million tenge is used.

Subcontractors:

- "Kurylys" LLP – earth works, base course

- "Akzhol" LLP – earth works, base course, culverts

- "Bereke-А" LLP – overpass and bridge works construction

- "Kazspecelectryassemble-GSM" – PTL reconstruction

- "КаZaTService" LLP – communication line reconstruction

- «Adgeziya work training centre» gas pipe line reconstruction

-  «Omar Trans» LLP – works on road marking execution

Laboratory.

In Belye vody villiage km 661,5 Contracor’s laboratory is working, has attested and has passed calibration of an instruments. It is equipped on 100%, there are all necessary laboratory equipment and instruments. Also there are an industrial base, temporary dining room, medical station and hostel for personnel.

Work schedule execution

As on 02.09.2015

| № | Work description | All under the contract | Performed on 2014 | Plan on 2015 | Plan from the beginning of the year till August 2015 | Fact from the beginning of the year | Work remaining on today (+, -) | Execution in % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Earth works, thous. m3 | 2504,2 | 1602,7 | 901,5 | 694,5 | 473,5 | 428,0 | 52,5 |
| 2 | Base course, km | 80,8 | 45,48 | 35,3 | 35,3 | 25,32 | 9,98 | 71,7 |
| 3 | Foundation from CSSCM, km | 80,8 | 45,45 | 35,4 | 35,4 | 25,32 | 10,08 | 71,5 |
| 4 | Pavement from c/c and a/c, km | 80,8 | 41,45 | 39,4 | 34,19 | 24,4 | 15,0 | 61,9 |
| 5 | Bridges, Nos. | 11 | 4,7 | 6,3 | 4,3 | 3,9 | 2,5 | 61,9 |
| 6 | Culverts, Nos. | 41 | 28 | 19 | 19 | 13,0 | 6,0 | 68,42 |

| Materials procurement | All under the contract | Used 2014 | Plan on 2015 | Fact on June 30 | Execution in % from plan 2015 |
| --- | --- | --- | --- | --- | --- |
| 1 | Crushed-stone thous.m3 | 355,3 | 277,18 | 78,1 | 77,2 | 98,8 |
| 2 | GSM thous.m3 | 607,1 | 272,5 | 334,6 | 220,6 | 65,9 |
| 3 | Sand thous.m3 | 130,0 | 57,56 | 72,4 | 47,4 | 65,5 |
| 4 | Geomaterial thous. m2 | 1 212,9 | 779,5 | 433,4 | 340 | 78,5 |
| 6 | Cement thous.tenge | 110,3 | 42,2 | 68,1 | 42,1 | 60,5 |
| 7 | RCP thous.m3 | 10,9 | 3,4 | 7,5 | 5,0 | 66,6 |

- Cement supply from "Standard cement" plant, Shymkent.

- "Nurbek and K" borrow pit and  "Sairam" -  fr. crushed-stone, sieve, GSM, delivery is performed by  automobile transport of length on distance - 30 km,  up to date supplies of inert material are continued from "Birlik-4" LLP and "Altyn-kum" borrow pits, distances 4 km.

Technical equipment quantity, necessary for work program execution on September 2015

| № | Description Наименование ДСТ | Requirement on September 2015 Потребность на Сентябрь 2015г. | Available at site Находятся в работе | Repairs Находятся в ремонте | Additionally Required Дополнительная потребность |
| --- | --- | --- | --- | --- | --- |
|  | Участок ПК 632 – ПК 674/Section PK 632 – PK 674 |
| 1 | Автогрейдер/ Grader | 10 | 8 | 0 | -2 |
| 2 | Бульдозер/Dozer | 7 | 5 | 0 | -2 |
| 3 | Экскаватор/Excavator | 10 | 18 | 0 | 8 |
| 4 | Погрузчики/Loader | 20 | 22 | 0 | 2 |
| 5 | Каткигрунтовые/Roller for earthwork | 20 | 19 | 0 | -1 |
| 6 | Каткидляасфальта/Roller for asphalt | 4 | 1 | 0 | -3 |
| 7 | Водовозы/Water tank | 12 | 12 | 0 | 0 |
| 8 | Асфальтоукладчики/Paver | 2 | 2 | 0 | 0 |
| 9 | Фреза/Milling machine | 1 | 1 | 0 | 0 |
| 10 | Автокран/Crane | 5 | 8 | 0 | 3 |
| 11 | Автосамосвалына технологию/Dumper for technology | 89 | 89 | 0 | 0 |
| 12 | Автосамосвалы НаперевозкуДСМ/Dumper for transporting materials | 15 | 23 | 0 | 8 |
| 13 | ЦБЗ/Asphaltconcrete plant | 1 | 2 | 0 | 1 |
| 14 | Установка для приготовления ЩПЦС/Installation for CSSCM preparation | 1 | 1 | 0 | 0 |
| 15 | Прочая техника/Others | 46 | 41 | 2 | -3 |
| Total/Всего | 243 | 252 | 2 | 5 |

Background information:

- Works on laying of pavement from cement concrete are performed by «Sinohydro» General Contractor himself, for these purposes the Contractor has own paving machine «Wirtgen» SP 1600 and three concrete plants. Power of three plants are 360 m3 in hour of commercial concrete.

Personnel:

Personnel quantity: all on plan on 2015 there 324 per. workers are stipulated. At this moment there 332 persons work, including subcontracting, and rent of organization and RCM suppliers technique, from them: foreign workers - 50 per.

Kazakhstan personnel - 20 per.

Local personnel - 262 per.

Among them on «Ak zhol» LLP site 39 per. are mobilized, «Kurylys» LLP - 42 per., «Bereke» LLP 38 per, «Sinohydro» company 155 per. and etc. In general – 332 per., with start of main works in spring, with involving additional subcontractors quantity of personnel and technique will be increased.

Problematic issues and reasons, appeared on this site:

- «Bereke» Subcontractor conducts works on overpass and bridges slowly and low-quality, many remakes on Engineer’s comments. Reason – not equipment of necessary equipment, lack of qualified specialists and experience on bridge works.

- The issue on the Mashat pass by km 652+800 crossing with the Asian gas pipeline (AGP) isn't resolved. At the gas pipeline construction on crossing with road protective metal clothing is not correctly stipulated, the clothing is left concerning an axis of the existing road. With design the axis of the road doesn't get on the middle of the left gas pipe line protective clothing, the design road gets out of clothing. In this regard the operating organization of the gas pipeline doesn't give permission of the construction works in a security zone of the gas pipeline.

- Land acquisition questions are solved by halves, that slows down the construction process. Up to date the Contractor can’t conduct construction works on these sites:

Data on 2.09.2015

| №№ п.п. | Location, km | Name of not redeemed objects | Note |
| --- | --- | --- | --- |
| 1 | 2 | 3 | 4 |
| On Tyulkubas region territory |
| 1 | 650+950-651+150 | On the left of road axis there two residential houses have not yet been redeemed ; REP building, land plot and fence along the road owner have been paid 12 mln tenge last year by «Shymkentdorstroi» LLP, documents of buy/sell are processed. | Owners are dispossessed, houses dismantling has been started. Owners don’t agree with estimated value, court case in process |
| On Sairam region territory |
| 2 | 656+400-656+500 | On the left of the road «Gelios» gas station has not been redeemed, «OilMarketCorporation» LLP owner. Sairam region Akimat on 06.10.2014 by SKO court decision on economic issues have paid 22 287 409 tenge, at this moment receive-transmit documentation is made out. | On this moment question has not been solved, but on decision stage |
| 3 | 664+957-665+027 | On the left side of the road «Raiskii Sad» café has not been redeemed - assessed value 43 528 000,00 tenge, owner is Adahanova Aitoti. On this question on 09.09.2014 regional Akimat assigned the case into district course, after several considerations on 16.10.2014 case was redirected into SKO regional court on economical questions. After 4 sessions on 03.12.2014 according to district court decision the legal enquiry of object assessed value was held. According to district court decision on 23.01.2015 lawsuit of regional Akimat is satisfied. | Construction removal has become |
| 4 | 668+670-668+740 | On the left side of the road «Suan Baba» gas station has not redeemed - assessed value 83 699 000,00 tenge, owner is Ibragimov A.S. On this question law case is going according to scenario as on case of «Raiskii sad» café. | During decision stage |
| 5 | 669+240-669+300 | On the left side of the road «Zhantore» gas station has not redeemed – assessed value 54 471 000.00 tenge, owner is Panbayev А. On this question is the same thing, law case is going according to scenario as on case of «Raiskii sad» cafe. | During decision stage |
| 6 | 669+300-669+350 | On the left side of the road «Zhantore» café has not redeemed – assessed value is 13 285 000,00 tenge, owner is Panbayev А. On this question is the same thing, law case is going according to scenario as on case of «Raiskii sad» cafe. | Construction removal has become |

Conclusion.

- it’s necessary to increase supply and procurement of inert materials in work execution period, increase the necessary technique quantity.

- it’s necessary to mobilize the technique and personnel according to enclosure of confirmed  work schedule on 2015.

- it’s necessary to organize double-shift work for successful plan execution on 2015.

- it’s necessary to involve additionally the subcontracting organizations for bridges and overpasses construction, toughen control for work quality on bridges.

- to solve the questions on additional works together with Employer.

- to solve the question on land acquisition as soon as possible. Employer.

- to solve the question on procurement of permits of construction works in AGP gas pipe line protected zone, for this end it’s necessary to redesign the axis of the road with change of  radius of curvature  in plan in gas pipe line intersection region.

Deputy of Engineer Resident                                        К. Kobzhasarov