INFORMATION

Reconstruction of International Transit Corridor

“Western Europe – Western China”

km742-774 (LOT 1) in South Kazakhstan Oblast

as on 11.10.2016

Contract: EBRD/CW-01/2013

Employer: Committee for Roads Ministry of Investments and Development RK

General Contractor : «SinohydoCorporationLimited»  (China)

SCS: «KazDorNII» in association with «KAzNIIPI» Dortrans KHA

Designer – “SK Engineering” LLP

Cost of the Contract: 14 617 033423.74 tenge

Advance payment amount: 2 192 555 013.59 tenge

Commencement date: 08.04.2015

Completion period – 18 months (540 days)

1. Basic indicators

| Length of the section (km) | 32 |
| --- | --- |
| Culverts (nos), incl.: | 82 |
| cattle pass | 6 |
| Transport interchange in two levels(nos) | 1 |
| Bridges, underpasses, agricultural machinery pass (nos) | 3 /1 /4 |
| Earthworks (ths. m3) | 651.52 |
| GSM С-4 for sub base thick. Н=35cm(ths. m3) | 483.54 |
| CSGSM С-6 reinfor. 7% cement for base coarse thick. Н=20cm(ths. m3) | 227.71 |
| Cement concrete pavement Btb-4,8 – strength in bending; B-35 strength in compression thick. Н=27cm(ths. m3) | 208.67 |
| Bus pavilions / Bus stops | 10 / 10 |
| Rest area with ramp for vehicles in case of emergency situations, nos/Two-points Toillets nos | 4 / 4 |

2. Laboratory:

Laboratory of the Contractor is equipped for 100%.

Testing in the meteorology and standardization of SKO is done. The certification is received. The Laboratory room confirms to requirement of Specifications.

3. Office of the Engineer and General Contractor

The office of the Engineer is at km.754 LHS in the village Sharaphana. The Contractor provided office to the Engineer with all necessary office equipment, office furniture and household appliances according to the specification. The territory is fenced and access road is repaired, there is a shed for parking, alternative sources of industrial water and electricity are installed.

The office of the General Contractor is on production camp, at km.760 RHS. The office is equipped with all necessary office equipment, office furniture and household appliances. Also meeting room for 30 people, dormitory for 100 people and two dining rooms (for local and foreign staff) are available there. All utilities (electricity, water, internet) are connected, there are alternative sources of industrial water and electricity.

4. Camp

The Camp of the General Contractor is completed for 100%. The whole territory is fenced, there are areas for storage of road construction materials, elements and constructions, silos for storage of the cement (2 nos with 500tns capacity each and 3nos with 200tns capacity each); the areas for parking and repairing of the road construction machinery; two cement-concrete plants (180m3 each); one plant for production of CSSCM (production capacity 180m3/per hour); silos for cement (for base 500m3); reservoirs for drinking water (180m3), reservoirs for technical water (3nos with 150m3 capacity each), reservoirs for fuel storage (200m3) and weight bridge;.

5. Surveying works:

The works for acceptance and repair of benchmarks, the arrangement of road axes on the length of the road are completed.The works measurement of graded elevations of subgrade, base course, cement concrete pavement, and checking of the levels of base and foundations of the culverts, underpasses and minor bridges for agricultural machinery are being carried out.

6. Works on artificial structures:

Balance works on the main road - one underground pedestrian crossing (2,5x4m) and three culverts (ø1.5m) needed repair, and construction of 28 pipe at the ramps  (0,5x0,5m).

Works on bridges and overpasses.

PK 610 bridge over the river Keles – completed work on the foundation and pillars on 4 pillars of the bridge on the right side of the movement, set the span of the beam 30 pieces;	Bridge and overpass works.

PК 610 bridge over the river Keles – work began on dismantling the right side of the bridge, left side of the temporary open for  moving  traffic;

PК 621 Bridge over the river Sharbulak – open moving traffic  for transport stream driveway

PК 636 overpass at Turbat –– erection  Т- beams 100%.

PК 663 bridge over the river BKMK –open for traffic flow.

Works on the overpass for agricultural machinery pass

PК 446+54;  PK 505+53-construction of concrete pavement work is completed, open for moving traffic

PК 543+43;PК 583+60 – works on construction of overpass for agricultural equipment is completed. Balance of work –pavement of overpass, installation of  guard rails.

7. Communications relocation:

• Transmission Line (PTL 0.4 kW and 10 kW.). All work on the reconstruction of power lines are completed;

• Gas Pipeline. Work on the reconstruction of  gas pipeline are completed, except for the section near the overpass Kazygurt – Turbat at PK  636. Nowadays, negotiations are underway with the “Intergas” – the owner of the gas pipeline, for   receiving technical conditions. We note that the work on the reconstruction of gas  pipeline have not been accounted for in the original contract.

• Сommunication   Lines. (TUSM-11 and “Kazakhtelecom”) All works on the communication line reconstruction  is completed. We note that according to the updated technical conditions, the actual amount of work on the reconstruction of more than was included in the original design.

8. Procurement of the main road-building materials

| No | Materials | Unit | Plan under project | Actual for 2015 | Plan for 2016 | Actual for 2016 | Total actual | % executing | Remain |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone | Th.m3 | 409,00 | 214,02 | 194,98 | 194,98 | 409,00 | 100% | 0,00 |
| 2 | GSM | Th.m3 | 453,00 | 158,07 | 294,93 | 241,25 | 399,32 | 88% | 53,68 |
| 3 | Sand | Th.m3 | 75,60 | 27,30 | 48,30 | 45,65 | 72,94 | 96% | 2,66 |
| 4 | Cement | Th.ton | 104,17 | 28,81 | 75,36 | 73,05 | 101,86 | 98% | 2,31 |
| 5 | Reinforced goods | Th.m3 | 7,40 | 4,73 | 2,67 | 2,57 | 7,30 | 99% | 0,10 |

9. Progress of works:

| No | Materials | Unit | Plan under contract | Actual for 2015 | Plan for 2016 | Actual for 2016 | Total actual | % executing | remain |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Subgrade | КМ | 65,00 | 24,00 | 41,00 | 38,52 | 62,52 | 96% | 2,48 |
| 2 | Subbase | КМ | 65,00 | 19,74 | 45,26 | 40,51 | 60,25 | 93% | 4,75 |
| 3 | Base course | КМ | 63,86 | 19,39 | 44,47 | 39,06 | 58,45 | 92% | 5,41 |
| 4 | Concrete pavement | КМ | 63,86 | 16,98 | 46,88 | 36,18 | 53,16 | 83% | 10,70 |
| 5 | Pipe on the main road | ШТ | 46,00 | 24,00 | 22,00 | 22,00 | 46,00 | 100% | 0,00 |
| 6 | Pipes at ramps | ШТ | 30,00 | 1,00 | 29,00 | 1,00 | 2,00 | 7% | 28,00 |
| 7 |  | ШТ | 7,00 | 4,60 | 2,40 | 2,40 | 7,00 | 100% | 0,00 |
| 8 | Мосты | ШТ | 3,00 | 1,40 | 1,60 | 1,21 | 2,61 | 87% | 0,39 |
| 9 | Путепровод | ШТ | 1,00 | 0,36 | 0,64 | 0,45 | 0,81 | 81% | 0,19 |
| 10 | Проезды с/х техники | ШТ | 4,00 | 3,58 | 0,42 | 0,26 | 3,84 | 96% | 0,16 |
| 11 | Фрезерование | КМ | 63,86 | 31,50 | 32,36 | 32,36 | 63,86 | 100% | 0,00 |
| 12 | Разборка тощего бетона | КМ | 63,86 | 24,74 | 39,12 | 38,66 | 63,40 | 99% | 0,46 |

10. Personnel:

| № | Name | Plan | Actualт | Из них |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign China | Local RK |
| 1 | Administration | 10 | 4 | 2 | 2 |
| 2 | ETD | 8 | 7 | 4 | 3 |
| 3 | Surveyor | 6 | 4 | 3 | 1 |
| 4 | Surveyor’s assistant | 7 | 3 |  | 3 |
| 5 | Laboratory Engineer | 1 | 1 | 1 |  |
| 6 | Laboratory assistant | 2 |  |  |  |
| 7 | Lab worker | 4 | 2 |  | 2 |
| 8 | Mechanic Engineer | 2 | 1 | 1 |  |
| 9 | Mechanic | 96 | 12 |  | 12 |
| 10 | Dumper’s driver | 129 | 16 |  | 16 |
| 11 | Mechanic’s assistant | 12 | 13 | 1 | 12 |
| 12 | Road Workers | 20 | 10 |  | 10 |
| 13 | Supporting staff | 54 | 64 |  | 64 |
| 14 | Office manager | 1 | 1 | 1 |  |
| 15 | Office staff | 21 | 10 | 6 | 4 |
| TOTAL | 373 | 148 | 19 | 129 |

Note:

Local personnel – 129 per.:

95 per.  – Kazygurt district;

6  – Saryagash district

2  – Tolebi district

3  – Mahtaral district;

2  – Sairam district;

- – Sozak district;

6 – Baidibek district;

2 – Tulkubas district;

12 – Shymkent city

11. Equipment:

| № | Name | Plan for (December) | The fact the current date | mobilization |
| --- | --- | --- | --- | --- |
|  |  |  |  | own | subcontr/rented |
| 1 | Bulldozer | 4 | 1 | 1 |  |
| 2 | Excavator | 10 | 6 | 3 | 3 |
| 3 | Loader | 11 | 6 | 4 | 2 |
| 4 | Dump | 100 | 31 | 25 | 6 |
| 5 | Water tanker | 7 | 3 | 2 | 1 |
| 6 | Fuel tanker | 1 | 3 | 1 | 2 |
| 7 | Grader | 8 | 5 | 3 | 2 |
| 8 | Roller | 18 | 5 | 3 | 2 |
| 9 | CCP 180m3/h | 2 | 2 | 2 |  |
| 10 | Installation for the base | 1 | 1 | 1 |  |
| 11 | Concrete paver | 1 | 2 | 2 |  |
| 12 | Base paving machine | 2 | 2 | 2 |  |
| 13 | Crane | 3 | 2 | 1 | 1 |
| 14 | Trailer | 2 |  |  |  |
| 15 | Vehicle | 15 | 14 | 10 | 4 |
| 16 | Milling machine | 1 | 1 | 1 |  |
| 17 | Other | 59 | 28 | 28 |  |
| TOTAL | 245 | 113 | 89 | 24 |

12. IPC

| № IPC | period | amount | note |
| --- | --- | --- | --- |
| 1 | 14.11.2014 | 100 039 703,68 | Paid |
| 2 | From 08.04.2015 tо 30.04.2015 | 534 725 686,10 | Paid |
| 3 | From 01.05.2015 tо 30.06.2015 | 736 304 069,65 | Paid |
| 4 | From 01.07.2015 tо 31.07.2015 | 704 648 065,67 | Paid |
| 5 | From 01.08.2015 tо 31.08.2015 | 709 548 604,88 | Paid |
| 6 | From 01.09.2015 tо 30.09.2015 | 395 935 912,96 | Paid |
| 7 | From 01.10.2015 tо 31.10.2015 | 319 353 665,73 | Paid |
| 8 | From 01.11.2015 tо 20.12.2015 | 319 326 946,16 | Paid |
| 9 | From 21.12.2015 tо 20.01.2016 | 294 053 400,68 | Paid |
| 10 | From 21.01.2016 tо 29.02.2016 | 149 347 056,76 | Paid |
| 11 | From 01.03.2016 tо 30.04.2016 | 519 247 633,78 | Paid |
| 12 | From 01.05.2016 tо 31.05.2016 | 400 700 124,8 | Paid |
| 13 | From 01.06.2016 tо 15.06.2016 | 334 151 838,41 | Paid |
| 14 | From 16.06.2016 tо 11.07.2016 | 175 063 368,40 | Paid |
| 15 | From 12.07.2016 to 31.07.2016 | 550 548 524,83 | To CFR |
| 16 | From 01.08.2016 to 31.08.2016 | 751 069 086,15 | To CFR |
| 17 | From 01.08.2016 to 31.08.2016 | 504 824 792,87 | To CFR |
| 18 | From14.09.2016 tо 30.09.2016 | 828 612 379,23 | To CFR |
| Total |  | 8 327 290 423,36 |  |

13. Cash disbursement:

| No | Development | Physical disbursement | Financial disbursement |
| --- | --- | --- | --- |
|  |  | Plan | Actual | Plan | Actual |
| 1 | For the month | 14,2% | 12,2 % | 9,3 % | 8,8 % |
| 2 | Accumulative | 77,6 % | 65,7% | 61,7% | 54,8% |

14. Physical disbursement:

| Year | Month | Plan for development | physical development | % | Note |
| --- | --- | --- | --- | --- | --- |
| 2015 | January – December | 3 591 929 600,00 | 3 591 930 617,83 |  | IPC № 1 – 8 |
| 2016 | January – June | 2 030 067 200,00 | 2 030 070 252,80 |  | IPC № 9 – 13 |
|  | July | 2 127 742 400,00 | 1 130 363 109,59 |  | IPC № 14 – 15 |
|  | August | 1 896 843 200,00 | 1 380 875 296,35 |  | IPC № 16 |
|  | September | 2 159 617 600,00 | 757 653 398,81 |  | IPC № 17 |
|  |  |  | 1 859 732 293,16 |  | IPC # 17-18 |
| Total | 11 806 200 000,00 | 9 992 971 569,73 | 84,64% |  |

15. Financial disbursement:

| Year | Month | Plan for development | Financial development | % | Note |
| --- | --- | --- | --- | --- | --- |
| 2015 | January – December | 3 819 670 000,00 | 3 819 672 217,45 |  | IPC № 1 – 8 |
| 2016 | January – June | 1 238 550 000,00 | 1 697 500 054,43 |  | IPC № 9 – 13 |
|  | July | 1 220 670 000,00 | 725 611 893,23 |  | IPC № 14 – 15 |
|  | August | 1 238 550 000,00 | 751 069 086,15 |  | IPC № 16 |
|  | September | 1 410 140 000,00 | 1 333 437 172,10 |  | IPC № 17-18 |
| Total | 9 386 530 000,00 | 8 327 290 423,36 | 88,72 % |  |

16.  Variation order

| № | Description | Amount with VAT (kz) | Note |
| --- | --- | --- | --- |
| Initial value of the contract (without order) | 14 617 033 424,00 |
| 1 | Replacement of geotextile for reinforced plastic film | - 46 209 603.85 | Approved by CFR 23-23-03/2996 от 18.11.15 |
| 2 | Lean concrete. Dismantling of existing lean concrete layer | + 212 300 292.69 | Approved by CFR 23-23-03/2996 от 18.11.15 |
| 3 | Construction of RMD | + 426 205 997,80 | In progress |
|  | Contract value after Variation Order | 15 209 330 110,64 |

17. Subcontractor organization:

| № | Name of Sub.organization | Type of work | Note |
| --- | --- | --- | --- |
|  | "Baku Stroi" LLP | Earthworks and sub base | Approved by COR ref.№ 23-23-03/1797 dated 22.07.2015 |
|  | "ART-Kurylys" LLP | Erecting of artificial structures (culverts, tubing and cattle passes) | Approved by COR ref.№ 23-23-03/1796 dated 22.07.2015 |
|  | “Bereke А” Corporation" | Construction of bridges and underpasses | Approved by COR ref.№ 23-23-03/1799 dated 22.07.2015 |
|  | "Mega-Tech" LLP | Relocation of telephone line (Kazakhtelecom) | Approved by COR ref.№ 23-23-03/976 dated 30.04.2015 |
|  | "BerkutMika" LLP | Earthworks and sub base | Approved by COR ref.№ 23-23-03/2498 от 02.10.2015 |
|  | "Kazspetselectromontazh PGS" LLP | Relocation of PTL | Approved by COR ref.№ .№ 23-23-03/2498 от 02.10.2015 |

Currently, negotiations are  in progress with new subcontractors

18. Supplier of materials:

| № | Material | Supplier | Note |
| --- | --- | --- | --- |
| 1 | Crushed stone | Birlik 4 | For base |
|  |  | IP Tulemetov | For base |
| 2 | GSM | Kurbek I Kom |  |
| 3 | Sand | Kurbek I Kom |  |
| 4 | Cement | Standart cement | For pavement |
|  |  | Shymkent Cement | For pavement |
| 5 | Film (geomembrane) | Kyrylys Polimet |  |
|  |  | Kaz Geo Bel-1 |  |
| 6 | Dowel bar | Villar Kazakhstan |  |
|  |  | Kor Metal servic |  |
| 7 | Anchor | Mechel Kazakhstan |  |
| 8 | RSE for bridge | Bereke A |  |
| 9 | RSE for pipes and tubes | ART Kurulys |  |

19. Problem issues:

* Total delay. According to the results of monitoring of progress, the Contractor has a growing delay from the Work Program. Considering the limited period of construction, Contractor needs to take radical measures for the recovering the delay in order to avoid the penalties by the Employer in accordance with GCC 8.7 [Delay damages].

* Contractor's staff. * Contractor has a shortage of qualified personnel with experience in the road construction, from the management personnel competent for the planning and organization of work to the workers on the site Contractor needs to solve the problem of the personnel as per Clause 6.9 of GCC

* Pipeline. At PK 631, before the overpass, through  the road passes main line of the gas pipeline "Intergas". Work on the reconstruction, either instruction work on the gas pipeline lines were not provided under  project. Therefore, at this time the Contractor has been receiving technical conditions from the owner of the gas pipeline. This procedure takes a long time, leading to delays in the Contractor's works on reconstruction of the road at the site.

Resident Engineer  						          Irmanov S.

Prep.by. Quantity Engineer

Mamanazarov B.