INFORMATION

Reconstruction of International Transit Corridor

“Western Europe – Western China”

km742-774 (LOT 1) in South Kazakhstan Oblast

as on 15.04.2015

Contract: EBRD/CW-01/2013

Employer: Committee for Roads Ministry of Investments and Development RK

General Contractor : «SinohydoCorporationLimited»  (China)

SCS: «KazDorNII» in association with «KAzNIIPI» Dortrans KHA

Designer – “SK Engineering” LLP

Cost of the Contract: 14 617 033423.74 tenge

Advance payment amount: 2 192 555 013.59 tenge

Commencement date: 02.03.2015

Completion period – 18 months (540 days)

1. Basic indicators

| Length of the section (km) | 32 |
| --- | --- |
| Culverts (nos), incl.: | 88 |
| cattle pass | 6 |
| Transport interchange in two levels(nos) | 1 |
| Bridges, underpasses, agricultural machinery pass (nos) | 3 /1 /4 |
| Earthworks (ths. m3) | 310.81 |
| GSM С-4 for sub base thick. Н=35cm(ths. m3) | 483.54 |
| CSGSM С-6 reinfor. 7% cement for base coarse thick. Н=20cm(ths. m3) | 227.71 |
| Cement concrete pavement Btb-4,8 – strength in bending; B-35 strength in compression thick. Н=27cm(ths. m3) | 208.67 |
| Bus pavilions / Bus stops | 10 / 10 |
| Rest area with ramp for vehicles in case of emergency situations, nos/Two-points Toillets nos | 4 / 4 |

2. Laboratory:

-As on today the Laboratory of the Contractor is equipped for 100%  and the installation of the equipments is being carried out.

The request for testing in the meteorology and standardization of SKO is sent. The Laboratory room confirms to requirement of Specifications.

3. Camp

- The installation of the c/c plant is being carried out – 2nos. with the capacity 250 tns/hour each, it is completed for 90%. The installation of mixing plant for CSSCM production is done. Completed for 100%. Silos for cement with the capacity of 2100tns is at the cite, and the silos with capacity of  1000tns is being prepared in Shymkent, track scales are installed. The territory is protected, the water and electricity supply is provided. On the territory of the camp the boxes for office and dormitory for the employees of the company are installed. The canteen for foreign and local personnel is working.

4. Surveying works:

-The works for acceptance and repair of benchmarks are completed, the arrangement of road axes on the length of the road is being carried out.

Working drawings are being worked out. The intersection of cable, gas pipeline and electricity line is being defined.

5.  Information on the work performed:

| Name of work | unit | Total under the contract | Plan for 2015 | Performed from the beginning of the year | Remaining under contract | % Execution of the contract |
| --- | --- | --- | --- | --- | --- | --- |
| Earthworks | thous. m3 | 310.812 | 213.68 | 0 | 310.812 | 0 |
| Subbase | km | 64,0 | 34,0 | 0 | 32 | 0 |
| Base (CCSM) | km | 64,0 | 34,0 | 0 | 32 | 0 |
| C/C pavement | km | 62,4 | 32,0 | 0 | 32 | 0 |
| Culverts | pc | 88 | 45 | 0,5 | 87,5 | 0,6 |
| Bridges, overpasses, passages for / agricultural machinery | pc | 8 | 5 | 0,2 | 7,8 | 2,5 |
| Milling | km | 64,0 | 36,0 | 2,3 | 61,7 | 3,6 |

6. Procurement of the main road-building materials

| Name of material | Unit | Total under the contract | Plan for 2015 | Performed from the beginning of the year | Remaining under contract | % Execution of the contract |
| --- | --- | --- | --- | --- | --- | --- |
| Crushed stone 0-40mm | thous. m3 | 426.992 | 309.184 | 37,27 | 389,728 | 8,73 |
| SGM | thous. m3 | 571.260 | 374,680 | 0 | 571.260 | - |
| Sand | thous. m3 | 77,719 | 48,945 | 5,52 | 72,20 | 7,10 |
| Concrete goods | thous. m3 | 7,36 | 4,63 | 1,17 | 6,19 | 15,83 |
| Cement | thous. m3 | 84.970 | 43,600 | 0,13 | 84.836 | 0,16 |

7. Personnel:

| № | Name | Requirement for 2015 | The fact the current date | Personnel |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign | Local |
| 1 | ET | 30 | 15 | 15 | 0 |
| 2 | Administration | 15 | 12 | 12 | 0 |
| 3 | Laboratory | 10 | 8 | 6 | 2 |
| 4 | Surveying | 16 | 9 | 7 | 2 |
| 5 | Operator | 10 | 7 |  | 7 |
| 6 | Driver | 30 | 25 |  | 25 |
| 7 | Mechanic | 5 | 5 |  | 5 |
| 8 | Master | 18 | 18 |  | 18 |
| 9 | Workers | 75 | 15 | 2 | 13 |
| 10 | Other | 74 | 11 | 2 | 9 |
| Total | 283 | 125 | 48 | 44 |

8. Mobilization of equipment:

| № | Name | Requirement for 2015 | The fact the current date | Mobilization |
| --- | --- | --- | --- | --- |
|  |  |  |  | own | субподр./аренд. |
| 1 | Bulldozer | 5 |  |  |  |
| 2 | Excavator | 9 | 4 | 4 |  |
| 3 | Loader | 8 | 4 | 4 |  |
| 4 | Grader | 8 | 2 | 2 |  |
| 5 | Roller | 17 | 4 | 4 |  |
| 6 | Dump | 60 | 20 | 20 |  |
| 7 | watering machine | 7 | 1 | 1 |  |
| 8 | Asphalt paver | 3 | 1 | 1 |  |
| 9 | Concrete paver | 1 | 1 | 1 |  |
| 10 | Truck crane | 2 | 1 | 1 |  |
| 11 | CCP | 2 | 2 | 2 |  |
| 12 | Installation for the base of CCSM | 1 | 1 | 1 |  |
| 13 | piling machine | 1 |  |  |  |
| 15 | Concrete mixer (mixer) | 3 | 1 | 1 |  |
| 16 | Milling | 1 | 2 | 2 |  |
| 17 | Vehicle | 13 | 8 | 8 |  |
| 18 | Other | 55 | 12 | 12 |  |
| Total | 194 | 64 | 64 |  |

9. Subcontractor organization:

| № | Name of Sub.organization | Type of work | Note |
| --- | --- | --- | --- |
| 1 | "Kazvodenergostroy" LLP | Dismantling of bridges | Approved |
| 2 | «TIM-SAM» LLP | Culverts works | For review |
| 3 | «Baku stroy» LLP | Culverts work | For review |

10. Problem issues:

21. Receipt permission for the development of ground pits at the site.

Resident Engineer            Irmanov S.