INFORMATION

Reconstruction of International Transit Corridor

“Western Europe – Western China”

km742-774 (LOT 1) in South Kazakhstan Oblast

as on 15.07.2015

Contract: EBRD/CW-01/2013

Employer: Committee for Roads Ministry of Investments and Development RK

General Contractor : «SinohydoCorporationLimited»  (China)

SCS: «KazDorNII» in association with «KAzNIIPI» Dortrans KHA

Designer – “SK Engineering” LLP

Cost of the Contract: 14 617 033423.74 tenge

Advance payment amount:2 192 555 013.59 tenge

Commencement date: 08.04.2015

Completion period – 18 months (540 days)

1. Basic indicators

| Length of the section (km) | 32 |
| --- | --- |
| Culverts (nos), incl.: | 88 |
| cattle pass | 6 |
| Transport interchange in two levels(nos) | 1 |
| Bridges, underpasses, agricultural machinery pass (nos) | 3 /1 /4 |
| Earthworks (ths. m3) | 310.81 |
| GSM С-4 for sub base thick. Н=35cm(ths. m3) | 483.54 |
| CSGSM С-6 reinfor. 7% cement for base coarse thick. Н=20cm(ths. m3) | 227.71 |
| Cement concrete pavement Btb-4,8 – strength in bending; B-35 strength in compression thick. Н=27cm(ths. m3) | 208.67 |
| Bus pavilions / Bus stops | 10 / 10 |
| Rest area with ramp for vehicles in case of emergency situations, nos/Two-points Toillets nos | 4 / 4 |

2. Laboratory:

- Contractor’s laboratory is equipped for 100%.

The request for testing in the meteorology and standardization of SKO is sent. The Laboratory room confirms to requirement of Specifications.

3.  Engineer  and General Contractor’s office:

The office of the  Engineer located is  754 km left in the village Sharaphana. The Contractor has  provided to  the Engineer office with all necessary office equipment, office furniture and appliances  according to the specification. The territory is fenced and repair road access, there are car parking shed, installed alternative sources of industrial water and electricity on the site.

The office of the General Contractor on  production base, km.760 right of the road. The office is equipped with all necessary office equipment, office furniture and household appliances. There is meeting room for 30 people, a dormitory for a hundred beds and two dining rooms (for local and foreign staff). There are connected all communications (electricity, water, internet), there are alternative sources of industrial water and electricity.

4. Production base

General Contractor’s base is equipped  for  95%. The whole territory is protected, situated on the basis of the storage area of road-building materials, products and structures; containers (silos) for storage of cement ( 2 to  500t   and 3  to 200t); parking area and repair of road construction equipment; Two cement plant (with capacity of 180m3 each), one factory for making CSSCM (with capacity 180m3 / h) reservoirs for drinking water ( capacity of 180m3), technical water (3 to 150m3) fuel storage tank (capacity 200m3) and auto weights;

5. Surveying works:

-The works for acceptance and repair of benchmarks are completed, the arrangement of road axes on the length of the road is being carried out. Works graded elevation  measuring site  after milling the existing road, checking marks of base and foundations of culverts, overpasses and bridges for the passage of small agricultural machinery are being carry out .

6. Artificial structures works:

Today, work on artificial construction is being carried out on  25  sites. Of these, 17 facilities completed the installation of r/c construction on 3 sites filled solid foundation. On 12 objects works on backfilling  are completed.

Also, works on  driving pile on the bridge over the river Sharbulak (80%) is being carry out, filled monolithic grillage third support (20%).Dismantling of  overpass (50%) and  pile installation (20%), monolithic grillage (20%) and the bridge across the canal BKMK dismantling (50%).

7. Transfer of communication  works :

• Gas pipeline: works on  transfer of  line of the gas pipeline at PK  621 (the bridge across the river Sharbulak)  is completed , there are  being  preparatory works at  PK 610 (bridge over the river Keles)

• Communication lines: works on  transfer of  communication cable "Kazakhtelecom" at PK 663 + 48 (bridge over the canal BKMK) is completed, work is underway to transport link "TUSM-11" at  PK  610 (bridge over the river Keles), there are being preparatory works at PK 621 (bridge over the river  Shrabulak ) and PK 490  village Sharaphana.

8.  Information about performed works on 15.07.2015:

| Name of work | unit | plan | fact | % execution | Lead / lag |
| --- | --- | --- | --- | --- | --- |
| Earthworks | thous. m3 | 216,20 | 102,40 | 47,4 | -113,80 |
| Subbase | km | 13,80 | 0,40 | 2,9 | -13,40 |
| Base (CCSM) | km | 10,50 | 0,40 | 3,8 | -10,10 |
| C/C pavement | km | 8,00 | - | - | -8,00 |
| Culverts | pc | 19,00 | 18,20 | 95,8 | -0,80 |
| Bridges | pc | 1,15 | 1,29 | 112,2 | 0,14 |
| Milling | km | 216,20 | 102,40 | 47,4 | -113,80 |
| Dismantling of weak concrete | km | 13,80 | 0,40 | 2,9 | -13,40 |

9. Procurement of the main road-building materials on 15.07.2015

| Name of material | Unit | Plan | Fact | % Excecution | Lead / lag |
| --- | --- | --- | --- | --- | --- |
| Crushed stone | тыс. м3 | 112,70 | 134,42 | 119,3 | 21,72 |
| SGM | тыс. м3 | 138,30 | 16,56 | 12,0 | -121,74 |
| Sand | тыс. м3 | 17,90 | 16,76 | 93,6 | -1,14 |
| Cement | тыс.тн | 15,40 | 2,54 | 16,5 | -12,86 |
| Concrete goods | тыс. м3 | 1 650,00 | 2,93 | 0,2 | -1 647,07 |

10. Personnel:

| № | Name | Plan for month (July) | The fact the current date | Personnel |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign China | Local РК |
| 1 | Administration | 10 | 11 | 10 | 1 |
| 2 | FP | 9 | 23 | 7 | 16 |
| 3 | Surveying | 5 | 10 | 3 | 7 |
| 4 | axman | 4 | 4 | 0 | 4 |
| 5 | Laboratory engineer | 1 | 1 | 1 | 0 |
| 6 | Laboratory assistant | 2 | 2 | 2 | 0 |
| 7 | Laboratory worker | 4 | 4 | 0 | 4 |
| 8 | Mechanic Engineer | 2 | 2 | 2 | 0 |
| 9 | Mechanic | 88 | 94 | 0 | 94 |
| 10 | Dump truck driver | 123 | 133 | 0 | 133 |
| 11 | assistant Mechanic | 12 | 13 | 2 | 11 |
| 12 | roadman | 20 | 31 | 0 | 31 |
| 13 | Support staff | 54 | 84 | 0 | 84 |
| 14 | Office manager | 1 | 1 | 1 | 0 |
| 15 | Office worker | 17 | 17 | 17 | 0 |
| TOTAL | 352 | 430 | 45 | 385 |

Note:

Local staff in number of 140 people are consist:

302 people - Kazygurt region;

21 people - Saryagash region;

17 people - Tolebi district;

16 person - Makhtaral district;

14 people - Baidibek district;

14 person – Shymkent city;

1 person – Taraz  city .

11. Mobilization of equipment:

| № | Name | Plan for month (july) | The fact the current date | Mobilization |
| --- | --- | --- | --- | --- |
|  |  |  |  | own | Subcont.rental |
| 1 | Buldozer | 4 | 7 | 1 | 6 |
| 2 | Excavator | 10 | 22 | 4 | 18 |
| 3 | Loader | 11 | 13 | 5 | 8 |
| 4 | Dumping truck | 100 | 100 | 20 | 80 |
| 5 | Water tank truck | 12 | 10 | 3 | 7 |
| 6 | gasoline tanker | 1 | 2 | 1 | 1 |
| 7 | Grader | 8 | 8 | 2 | 6 |
| 8 | Roller | 15 | 14 | 5 | 9 |
| 9 | CCC 180m3/h | 2 | 2 | 2 | 0 |
| 10 | Installation of base | 1 | 1 | 1 | 0 |
| 11 | Concrete paver | 1 | 1 | 1 | 0 |
| 12 | Layer of base | 2 | 2 | 2 | 0 |
| 13 | Crane | 3 | 9 | 4 | 5 |
| 14 | Trawl | 1 | 5 | 1 | 4 |
| 15 | Vehicle | 11 | 16 | 10 | 6 |
| 16 | Millimg | 1 | 1 | 1 | 0 |
| 17 | Other | 63 | 58 | 28 | 30 |
| TOTAL | 246 | 271 | 91 | 180 |

12. Subcontractor organization:

| № | Name of Sub.organization | Type of work | Note |
| --- | --- | --- | --- |
| 1 | "Shym NurServis" LLP | Earthworks and subbase installation | Returned to General Contractor. There are not complete set of documents Outgoing № 04-15 (287) |
| 2 | "Akzhol Astana 2030" LLP | Earthworks and subbase installation | Approved by CFR out.№ 23-23-03/976 от 30.04.2015 |
| 3 | "ТimSam" LLP | Earthworks and subbase installation | Approved by CFR out..№ 23-23-03/976 от 30.04.2015 |
| 4 | "BerkutMika" LLP | Earthworks and subbase installation | For approval to CFR |
| 5 | "BAKU STROI" LLP | Earthworks and subbase installation | For approval to CFR |
| 6 | "ART-Kurylys" LLP | installation of artificial structures (culverts) | For approval to CFR |
| 7 | "Sovremennye stroitelnye izdelia" LLP | installation of artificial structures (culverts) | For approval to CFR |
| 8 | "Kazspecelectromontazh PGS" LLP | reorganization / transfer of power lines | Returned to General Contractor. There are not complete set of documents out.№ 04-15 (287) |
| 9 | "MEGA-TEH" LLP | reorganization / transfer of power lines (Кazakhtelecom) | approved by CFR out .№ 23-23-03/976 от 30.04.2015 |
| 10 | "Kazvodenergostroi-Servis"LLP | Dismantling of bridge | Approved by Engineer |
| 11 | "Corporacia “Bereke A”" | Construction of bridge and overpass | For approval to CFR |
| 12 | LLP “ Oner 2002” | Earthworks and subbase installation | Returned General Contractor. There is not complete set of documents .№ 04-15 (293) |

13. IPC

| № | Period | Amount | Note |
| --- | --- | --- | --- |
| 1 | 14.11.2014 | 1 196 317 210,48 (advance) | Paid |
| 2 | с 08.04.2015 по 30.04.2015 | 534 725 686,10 | Paid |
| 3 | с 01.05.2015 по 30.06.2015 | 736 304 069,65 | On approval to CFR |

14. Variation Order

| № | Period | Amount | Note |
| --- | --- | --- | --- |
| 1 | Geomembrane. Replacement of geotextile-reinforced tape on | - 15 579 027,99 (without VAT) | Under development |
| 2 | Weak concrete. Dismantling of the existing foundation of lean concrete | + 181 676 800,00 (without VAT) | Under development |
| 3 | Transfer line TUSM - 11 and Kazakhtelecom JS | Not determined | Under development |

15. Problematic issues:

* Prompt response received from Employer regarding ROS. Type of work (construction or major repairs) and location (pass Kazygurt or village Zhibek Zholy)

* Prompt response received from Employer ring egar construction of pedestrian crossings. Approval or amendment of the list prepared by the Engineer in accordance with the requests and wishes of local residents and Akimov.

* Facilitate the Employer on acceptance of the dismantled elements of arrangement road construction and concrete culverts, underpasses, bridges and overpasses. Today on the site ROS-69 allocated to the storage of the dismantled elements is no free space for storage.

Resident Engineer  Irmanov S.A.

Prepared by:Quantity Engineer

Mamanazarov B.