INFORMATION

Reconstruction of International Transit Corridor

“Western Europe – Western China”

km742-774 (LOT 1) in South Kazakhstan Oblast

as on 31.08.2015

Contract: EBRD/CW-01/2013

Employer: Committee for Roads Ministry of Investments and Development RK

General Contractor : «SinohydoCorporationLimited»  (China)

SCS: «KazDorNII» in association with «KAzNIIPI» Dortrans KHA

Designer – “SK Engineering” LLP

Cost of the Contract: 14 617 033423.74 tenge

Advance payment amount:2 192 555 013.59 tenge

Commencement date: 08.04.2015

Completion period – 18 months (540 days)

1. Basic indicators

| Length of the section (km) | 32 |
| --- | --- |
| Culverts (nos), incl.: | 88 |
| cattle pass | 6 |
| Transport interchange in two levels(nos) | 1 |
| Bridges, underpasses, agricultural machinery pass (nos) | 3 /1 /4 |
| Earthworks (ths. m3) | 310.81 |
| GSM С-4 for sub base thick. Н=35cm(ths. m3) | 483.54 |
| CSGSM С-6 reinfor. 7% cement for base coarse thick. Н=20cm(ths. m3) | 227.71 |
| Cement concrete pavement Btb-4,8 – strength in bending; B-35 strength in compression thick. Н=27cm(ths. m3) | 208.67 |
| Bus pavilions / Bus stops | 10 / 10 |
| Rest area with ramp for vehicles in case of emergency situations, nos/Two-points Toillets nos | 4 / 4 |

2. Laboratory:

Laboratory of the Contractor is equipped for 100%.

Testing in the meteorology and standardization of SKO is done. The certification is received. The Laboratory room confirms to requirement of Specifications.

3. Office of the Engineer and General Contractor

The office of the Engineer is at km.754 LHS in the village Sharaphana. The Contractor provided office to the Engineer with all necessary office equipment, office furniture and household appliances according to the specification. The territory is fenced and access road is repaired, there is a shed for parking, alternative sources of industrial water and electricity are installed.

The office of the General Contractor is on production camp, at km.760 RHS. The office is equipped with all necessary office equipment, office furniture and household appliances. Also meeting room for 30 people, dormitory for 100 people and two dining rooms (for local and foreign staff) are available there. All utilities (electricity, water, internet) are connected, there are alternative sources of industrial water and electricity.

4. Camp

The Camp of the General Contractor is completed for 100%. The whole territory is fenced, there are areas for storage of road construction materials, elements and constructions, silos for storage of the cement (2 nos with 500tns capacity each and 3nos with 200tns capacity each); the areas for parking and repairing of the road construction machinery; two cement-concrete plants (180m3 each); one plant for production of CSSCM (production capacity 180m3/per hour); silos for cement (for base 500m3); reservoirs for drinking water (180m3), reservoirs for technical water (3nos with 150m3 capacity each), reservoirs for fuel storage (200m3) and weight bridge;.

5. Surveying works:

The works for acceptance and repair of benchmarks, the arrangement of road axes on the length of the road are completed.

The works on measurement of graded elevation of the sections after milling of the existing pavement, measurement of graded elevations of subgrade, base course, cement concrete pavement, and checking of the levels of base and foundations of the culverts, underpasses and minor bridges for agricultural machinery are being carried out.

6. Works on artificial structures:

As on date 25 artificial structures are under construction. On 17 of them the erecting of reinforced concrete structures are completed, on 3 of them the monolithic foundation is arranged. 12 of them are being backfilled.

Also pile driving works on the bridge across the river Sharbulak is being carried out (80%), monolithic grillage of the third pillar is laid (20%). The overpass is being dismantled (50%), pile driving (20%), monolithic grillage (20%) and the bridge acrocc BKMK channel is dismantled for 50%.

7. Communications relocation:

- Gas pipeline: the relocation of gas pipeline at PK 621 (bridge across Sharbulak river) is finished, the preparation works for relocation at PK 610 (bridge across Keles river) are carried out

- Communication lines: relocation of “Kazakhtelecom” communication line at PK 663+48 (bridge across BKMK channel) is finished, relocation of “TUSM-11” communication line at PK 610 (bridge across Keles river) is in process, preparation works at PK 621 (bridge across Sharbulak river) and at PK 490 (Sharapkhana village) are being carried out.

8.  Variation order

| № | Period | Amount | Note |
| --- | --- | --- | --- |
| 1 | Geomembrane. Replace of geotextile to reinforced polyfilm | - 40. 895 mln tenge (excluding VAT) | In progress |
| 2 | Lean concrete. Dismantling of existing lean concrete layer | + 94. 776 mln tenge (excluding VAT) | In progress |
| 3 | Relocation of TUSM-11 and Kazakhtelecom JSC communication lines | Not determined | In progress |

9. IPC

| № | Period | Amount | Note |
| --- | --- | --- | --- |
| 1 | 14.11.2014 | 1 196 317 210,48 (advance payment) | Paid |
| 2 | from 08.04.2015 till 30.04.2015 | 534 725 686,10 | Paid |
| 3 | from 01.05.2015 till 30.06.2015 | 736 304 069,65 | Paid |
| 4 | From 01.07.2015 till 31.07.2015 | 704 648 065,67 | In MID RK |

10. Physical progress:

| Year | Month | Disbursement plan (tenge) | Physical progress (tenge) | % | Note |
| --- | --- | --- | --- | --- | --- |
| 2014 | November | 100 039 703,68 | 100 039 703,68 |  | IPC # 1 |
| 2015 | April | 104 003 200,00 | 93 661 557,98 |  | IPC # 2 |
|  | May | 396 513 600,00 | 234 787 143,07 |  | IPC # 3 |
|  | June | 971 432 000,00 |  |  |  |
|  | Subtotal | 1 571 988 503,68 | 428 488 404,72 | 27,26% |  |
|  | July | 1 086 321 600,00 | 413 000 359,05 | approximately | IPC # 4 |
|  | Total | 2 658 310 103,68 | 841 488 763,77 | 31,66% |  |

11. Financial progress:

| Year | Month | Disbursement plan | Financial progress | % | Note |
| --- | --- | --- | --- | --- | --- |
| 2014 | November | 1 096 277 506,80 | 1 196 317 210,48 |  | IPC # 1 |
| 2015 | April | 227 460 000,00 | 534 725 686,10 |  | IPC # 2 |
|  | May | 529 770 000,00 | 736 304 069,65 |  | IPC # 3 |
|  | June | 1 024 670 000,00 |  |  |  |
|  | Subtotal | 2 878 177 506,80 | 2 467 346 966,23 | 85,73% |  |
|  | July | 1 128 920 000,00 | 722 174 114,58 | approximately | IPC # 4 |
|  | Total | 4 007 097 506,80 | 3 189 521 080,81 | 79,60% |  |

12.  Information on the work performed as on 31.08.2015:

| Name of work | unit. | Plan | Actual | % performed | Advancing/delay |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Quantity | Days |
| Earthworks | thous | 313,95 | 163,46 | 52,1% | -150,49 | -56 |
| Subgrade | km | 27,30 | 14,18 | 51,9% | -13,12 | -56 |
| Subbase | km | 23,30 | 7,68 | 33,0% | -15,62 | -78 |
| Base (CCSM) | km | 19,00 | 6,94 | 36,5% | -12,06 | -74 |
| Base (CCSM) | km | 17,00 | 3,30 | 19,4% | -13,70 | -93 |
| Culvert ) | pc | 28,00 | 21,40 | 76,4% | -6,60 | -27 |
| Bridges and interchange | pc | 1,34 | 0,70 | 52,4% | -0,64 | -55 |
| Bridges and interchange | pc | 3,27 | 2,57 | 78,6% | -0,70 | -25 |
| Agr. Machinery pass Milling | km | 25,90 | 31,30 | 120,8% | 5,40 | 24 |
| Lean concrete removal | km | 31,20 | 25,54 | 81,9% | -5,66 | -21 |

13. Procurement of the main road-building materials as on 31/08/.2015

| Material | Unit | Plan | Actual | % performed | Advancing/delay |
| --- | --- | --- | --- | --- | --- |
| Crushed stone | тыс.м3 | 161,60 | 128,88 | 79,7% | -32,73 |
| SGM | тыс.м3 | 197,40 | 59,75 | 30,3% | -137,65 |
| Sand | тыс.м3 | 26,40 | 26,62 | 100,8% | 0,22 |
| Cement | тыс.тон | 31,40 | 4,50 | 14,3% | -26,90 |
| RSE | тыс.м3 | 2,49 | 3,38 | 135,7% | 0,89 |

14. Mobilization of equipment:

| № | Name | Plan for a month (Aug.) | The fact the current date | Mobilization |
| --- | --- | --- | --- | --- |
|  |  |  |  | own | subcontr/rented |
| 1 | Bulldozer | 4 | 1 |  | 1 |
| 2 | Excavator | 10 | 9 | 3 | 6 |
| 3 | Loader | 11 | 8 | 4 | 4 |
| 4 | Dump | 100 | 27 | 8 | 19 |
| 5 | Water tanker | 12 | 6 | 2 | 4 |
| 6 | Fuel tanker | 1 | 2 | 1 | 1 |
| 7 | Grader | 8 | 9 | 2 | 7 |
| 8 | Roller | 15 | 10 | 3 | 7 |
| 9 | CCP 180m3/h | 2 | 2 | 2 |  |
| 10 | Installation for the base | 1 |  |  |  |
| 11 | Concrete paver | 1 | 1 | 1 |  |
| 12 | Base paving machine | 2 | 1 | 1 |  |
| 13 | Crane | 5 | 2 | 1 | 1 |
| 14 | Trailer | 1 |  |  |  |
| 15 | Vehicle | 1 | 16 | 10 | 6 |
| 16 | Milling machine | 1 |  |  |  |
| 17 | Other | 63 |  |  |  |
| Total | 248 | 94 | 38 | 56 |

15. Personnel:

| № | Name | Plan for a month (Aug.) | The fact the current date | Personnel |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign (China) | Local (RK) |
|  | Administration | 10 | 8 | 7 | 1 |
|  | ETD | 9 | 23 | 7 | 16 |
|  | Surveyor | 5 | 10 | 3 | 7 |
|  | Surveyor’s assistant | 7 | 4 |  | 4 |
|  | Laboratory Engineer | 1 | 1 | 1 |  |
|  | Laboratory assistant | 2 | 2 | 2 |  |
|  | Lab worker | 4 | 4 |  | 4 |
|  | Mechanic Engineer | 2 | 2 | 2 |  |
|  | Mechanic | 88 | 94 |  | 94 |
|  | Dumper’s driver | 123 | 133 |  | 133 |
|  | Mechanic’s assistant | 12 | 13 | 2 | 11 |
|  | Road Workers | 20 | 31 |  | 31 |
|  | Supporting staff | 54 | 84 |  | 84 |
|  | Office manager | 1 | 1 | 1 |  |
|  | Office staff | 19 | 17 | 17 |  |
| Total | 357 | 427 | 42 | 385 |

Note:

Local personnel (385 people) consists of:

115 pers. – Kazygurt region;

6 pers. – Saryagash region;

2 pers. – Tolebi region;

3 pers. – Makhtyaral region;

2 pers. – Sayram region;

1 pers. – Sozak region;

6 pers. – Baidibek region;

2 pers. – Tulkubass region;

12 pers. – Shymkent city;

1 pers. – Taraz city.

The rest 208 pers. are the Subcontractors’ personnel.

16. Subcontractor organization:

| № | Name of Sub.organization | Type of work | Note |
| --- | --- | --- | --- |
|  | "Akzhol Astana 2030" LLP | Earthworks and sub base | Approved by COR ref.№ 23-23-03/976 dated 30.04.2015 |
|  | "TimSum" LLP | Earthworks and sub base | Approved by COR ref.№ 23-23-03/976 dated 30.04.2015 |
|  | "Baku Stroi" LLP | Earthworks and sub base | Approved by COR ref.№ 23-23-03/1797 dated 22.07.2015 |
|  | "ART-Kurylys" LLP | Erecting of artificial structures (culverts, tubing and cattle passes) | Approved by COR ref.№ 23-23-03/1796 dated 22.07.2015 |
|  | "Sovremenniye stroitelniye izdeliya" LLP | Erecting of artificial structures (culverts, tubing and cattle passes) | Approved by COR ref.№ 23-23-03/1798 dated 22.07.2015 |
|  | “Bereke А” Corporation" | Construction of bridges and underpasses | Approved by COR ref.№ 23-23-03/1799 dated 22.07.2015 |
|  | "Mega-Tech" LLP | Relocation of telephone line (Kazakhtelecom) | Approved by COR ref.№ 23-23-03/976 dated 30.04.2015 |
|  | "BerkutMika" LLP | Earthworks and sub base | Sent to COR for approval Ref. No 345 dated 21.05.2015 |
|  | "Kazvodenergostroi-service" LLP | Bridge dismantling | Approved by the Engineer |
|  | "ShymNurService" LLP | Earthworks and sub base | Returned to General Contractor. Incomplete set of documents ref.№ 04-15 (287) |
|  | "Kazspetselectromontazh PGS" LLP | Relocation of PTL | Sent to COR for approval dated 29.07.2015 |

17. Problem issues:

* According to the results of monitoring of progress, the Contractor has a growing delay from the Work Program. Considering the limited period of construction, Contractor needs to take radical measures for the recovering the delay in order to avoid the penalties by the Employer in accordance with GCC 8.7 [Delay damages].

Contractor needs to concentrate all of the major forces in the beginning of the section for the prompt start and smooth running of the arrangement of the construction of the pavement. To organize a separate gang independent from the gang involved at the beginning of the section, to perform works at PK 610 in the direction of Tashkent according to the schedule.

* Contractor has a shortage of qualified personnel with experience in the road construction, from the management personnel competent for the planning and organization of work to the workers on the site

Contractor needs to solve the problem of the personnel as per Clause 6.9 of GCC

* Site works of Subcontractors are very slow because of the lack of proper control by the Contractor. There is a lack of heavy road-building equipment and qualified staff.

Project Manager of the Contractor must appoint responsible representatives for each Subcontractor, conduct strict control and monitoring of progress, take serious measures to subcontractors with a large delay up to the termination of the Contract.

Resident Engineer  						          Irmanov S.

Prep.by. Quantity Engineer

Mamanazarov B.