As per 20.01.2017

INFORMATION

For implementation of section km 171.1 – km 214.3 “Almaty – Khorgos” Road

Western Europe – Western China Project in Almaty Region

Contractor «JV «Todini /Impregilo -Kazakhdorstroi», Lot 4

Main Contractor – JV «Todini /Impregilo-Kazakhdorstroy»

Contract – EWRP-171.1-214.3-ICB(W)-001/2013

Contract Amount - 12 423 346 359 KZT

Contract signed – 30.07.2013

Disbursed in 2013-2016 – 13 215 467 468 KZT

Disbursement plan for 2017 – 299 457 241,7 KZT

Engineer CSC – Sweroad/Gauff/QPEC

Designer – LLP “Kazdorproject”

- Main Project characteristics

| Length, km | 43.3 |
| --- | --- |
| Culverts, no’s. | 28 |
| Bridges and cattle creeps, nos. | 4 |
| Overpasses, nos. | 1 |
| Interchanges, no’s. | 0 |
| Earthworks, thous.m3 | 3 069 |
| Sub base, km/thous.m3 | 43.3 / 466 |
| CSCSM, km/thous.m3 | 43.3 / 179 |
| Cement concrete pavement, km/thous.m3 | 43.3 / 202 |

- Analysis for work schedule performance:

| N | Description of works | Total under Contract | Plan for 2017 | Actual for current date since 2017 start | performance vs annual plan | performance vs contract |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Prior to variation | After variation |  |  | remain | % | remain | % |
| 1. | Earthworks (thous.m3) | 3 069 | 2 828,8 | 232,80 | 2656.2 | 232.8 | 8.71% | 2656.2 | 93.23% |
|  | Strengthening layer for embankment |  |  |  | 206,00 |  |  |  |  |
| 2. | Subbase, km | 42,8 | 0 | 42.8 | 0 | 0% | 0 | 100% |
| 3. | Base course from CSCSM, km | 42,52 | 0,0040 | 42.516 | 0 | 0% | 0 | 100% |
| 4. | Cement concrete pavement, km | 42,48 | 0,0030 | 42.477 | 0 | 0% | 0 | 100% |
| 5. | Bridges and overpasses, nos. | 5 | 0 | 5 in progress |  |  |  | 98% |
| 6. | Culverts, nos. | 28 | 0 | 28 completed | 0.0 | 0.0% | 0.0 | 100% |

- Procurement of materials:

| N | Description of material | Total under Contract | Plan for 2016 | Actual for current date | % | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Crushed stone, thous.m3 | 506,96 | 332,31 | 304,49 | 91,62 |  |
| 2. | Sand, thous.m3 | 124,33 | 43,11 | 34,27 | 79,50 |  |
| 3. | SGM, thous.m3 | 544,82 | 159,79 | 90,27 | 56,50 |  |
| 4. | Cement, thous.m3 | 93,28 | 78,22 | 66,55 | 85,08 |  |
| 5. | RCP, thous.m3 | 6,20 | 6,2 | 6,00 | 96,78 |  |

- Personnel involvement:

| N | Description | Demand for 2017 | TOTAL actual | Main Contractor | Subcontractors |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | TOTAL | foreign | local | TOTAL | Sung Do | LLP "Kerege Trans Service" | LLP "AZMK" |
| 1 | Engineers and Technicians, Administration | 17 | 8 | 7 | 2 | 5 | 1 | 0 | 0 | 1 |
| 2 | Laboratory Assistants and Quality Service | 8 | 11 | 11 | 1 | 10 | 0 | 0 | 0 | 0 |
| 3 | Operators of special machinery | 50 | 29 | 24 | 0 | 24 | 5 | 0 | 0 | 5 |
| 4 | Surveyors | 3 | 16 | 15 | 1 | 14 | 1 | 0 | 0 | 1 |
| 6 | Road workers | 20 | 23 | 22 | 1 | 21 | 0 | 0 | 0 | 0 |
| 7 | Welders |  | 7 | 7 | 0 | 7 | 2 | 0 | 0 | 2 |
| 8 | Others |  | 29 | 15 | 0 | 15 | 14 | 0 | 0 | 14 |
|  | TOTAL | 148 | 123 | 101 | 5 | 96 | 24 | 0 | 0 | 24 |

- Mobilization of equipment:

| N | Description of equipment | Unit | Demand for 2017 | TOTAL actual |
| --- | --- | --- | --- | --- |
| 1 | Bulldozer | pcs | 2 | 2 |
| 2 | Excavator | pcs | 6 | 1 |
| 3 | Loader | pcs | 14 | 5 |
| 4 | Motor grader | pcs | 2 | 4 |
| 5 | Rollers | pcs | 10 | 5 |
| 6 | Dumpers | pcs | 79 | 35 |
| 7 | Water tank | pcs | 5 | 1 |
| 8 | Petrol tank | pcs | 4 | 4 |
| 9 | Asphalt paver | pcs | 3 | 1 |
| 10 | Concrete paver | pcs | 1 | - |
| 11 | Milling machine | pcs | - | - |
| 12 | Truck crane | pcs | 3 | 1 |
| 13 | Distributor | pcs | 1 | 1 |
| 14 | ACP | pcs | - | - |
| 15 | CCP | pcs | 2 | 2 |
| 16 | Crusher | pcs | 3 | 3 |
| 17 | Batching plant | pcs | 1 | 1 |
| 18 | Mixer | pcs | 1 | - |
| 19 | Boring equipment for drilled piles | pcs | 0 | 0 |
| TOTAL | pcs | 137 | 66 |

- Subcontractors:

| N | Name of Subcontractor | Type of work | Section from km – to km | Remarks |
| --- | --- | --- | --- | --- |
| 1 | LLP "AZMK" | Bridges, overpass | 4 bridges 1 overpass | approved |