As per 2.09.2015

INFORMATION

For implementation of section km 214.3 – km 259.3 “Almaty-Khorgos” of Western Europe – Western China Road Project in Almaty Region Lot 5

Main Contractor – JV «Todini /Impregilo-Kazakhdorstroi»

Contract – EWRP-214.3-259.3-ICB(W)-001/2013

Contract Amount - 15 973 021 205 KZT

Contract Amount – 15 956 834 042 KZT (considering variations No.1 and No.2)

Contract signed – 30.07.2013

Construction period – 22 / 10 / 2013 – 09 /.04 / 2016

Disbursed in 2014 году – 2 566 225 705 KZT

Disbursement plan for 2015 – 4 902 970 000 KZT

Engineer CSC – Sweroad/Gauff/QPEC

Designer – LLP “Kazakhstan zholdary”

- Main Project characteristics

| Length, km | 45 |
| --- | --- |
| Culverts, no’s. | 48 |
| Bridges and cattle creeps, nos. | 0 |
| Overpasses, nos. | 0 |
| Interchanges, no’s. | 3 |
| Earthworks, thous.m3 | 6 728 |
| Sub base, km/thous.m3 | 45 / 443,04 |
| CSCSM, km/thous.m3 | 45 / 186,84 |
| Cement concrete pavement, km/thous.m3 | 45 / 208,17 |

- Analysis for work schedule performance:

| N | Description of works | Total under Contract | Plan for 2015 | Actual for current date since 2015 start | performance vs annual plan | performance vs contract |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Prior to variation | After variation |  |  | остаток/remain | % | остаток/remain | % |
| 1 | Earthworks (thous.m3) | 6 728 | 4 382,27 | 2 115,0 | 1 363,70 | 539,66 | 74% | 622,27 | 86% |
|  | Strengthening layer for embankment |  |  |  | 211,64 |  |  |  |  |
| 2 | Subbase, km | 45,0 | 40,0 | 17,52 | 22,48 | 44% | 27,48 | 39% |
| 3 | Base course from CSCSM, km | 45,0 | 30,0 | 14,08 | 15,92 | 47% | 30,92 | 31% |
| 4 | Cement concrete pavement, km | 45,0 | 24,0 | 12,88 | 11,12 | 54% | 32,12 | 29% |
| 5 | Bridges and overpasses, nos. | 0 | 0 | - | - | - | - | - |
| 6. | Culverts, nos. | 58 | 21 | 46 completed 11 in progress | 10 | 29% | 12 | 76% |
|  | Strengthening layer for embankment |  |  | 17.44 |  |  |  |  |

- Procurement of materials for Заготовка материалов на 2015 год:

| N | Description of material | Total under Contract | Plan for 2015 | Actual for current date since 2015 start | % | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Crushed stone, thous.m3 | 391,76 | 210,93 | 308,28 | 146 |  |
| 2. | Sand, thous.m3 | 42,02 | 26,11 | 36,13 | 138 |  |
| 3. | SGM, thous.m3 | 538,14 | 437,04 | 298,69 | 68 |  |
| 4. | Cement, thous.m3 | 111,22 | 64,57 | 31,41 | 49 |  |
| 5. | RCP, thous.m3 | 4.61 | 4.61 | 4,53 | 98 |  |

- Personnel involvement Привлечение персонала:

| N | Description | Demand for 2015 | TOTAL actual | Main Contractor | Subcontractors |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | TOTAL | foreign | local | TOTAL |
| 1 | Engineers and Technicians, Administration | 34 | 34 | 19 | 14 | 5 | 15 |
| 2 | Laboratory Assistants and Quality Service | 8 | 8 | 4 | 2 | 2 | 4 |
| 3 | Operators of special machinery | 71 | 83 | - | - | - | 83 |
| 4 | Surveyors | 4 | 4 | - | - | - | 4 |
| 5 | Drivers of dumpers | 80 | 62 | - | - | - | 62 |
| 6 | Road workers | 40 | 33 | - | - | - | 33 |
| 7 | Welders |  |  |  |  |  |  |
| 8 | Others | - | - | - | - | - | - |
|  | TOTAL | 237 | 279 | 23 | 16 | 7 | 233 |

- Mobilization of equipment:

| N | Description of equipment |  | Unit | Demand for 2015 | TOTAL actual | Main Contractor Todini | Total for Subcontract |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | own | rented |  |
| 1 | Bulldozer |  | pcs | 8 | 17 | 0 | 0 | 17 |
| 2 | Excavator |  | pcs | 8 | 13 | 0 | 0 | 13 |
| 3 | Loader |  | pcs | 9 | 10 | 0 | 0 | 10 |
| 4 | Motor grader |  | pcs | 4 | 9 | 0 | 0 | 9 |
| 5 | Rollers |  | pcs | 20 | 12 | 0 | 0 | 12 |
| 6 | Dumpers |  | pcs | 80 | 62 | 0 | 0 | 62 |
| 7 | Water tank |  | pcs | 10 | 9 | 0 | 0 | 9 |
| 8 | Petrol tank |  | pcs | 6 | 5 | 0 | 0 | 5 |
| 9 | Asphalt paver |  | pcs | 4 | 0 | 0 | 0 | 0 |
| 10 | Concrete paver |  | pcs | 1 | 1 | 0 | 0 | 1 |
| 11 | Milling machine |  | pcs | 1 | 0 | 0 | 0 | 0 |
| 12 | Truck crane |  | pcs | 2 | 4 | 0 | 0 | 4 |
| 13 | Distributor |  | pcs | 1 | 0 | 0 | 0 | 0 |
| 14 | ACP |  | pcs | 1 | 0 | 0 | 0 | 0 |
| 15 | CCP |  | pcs | 1 | 1 | 0 | 0 | 1 |
| 16 | Crusher |  | pcs | 1 | 1 | 0 | 0 | 1 |
| 17 | Cement warehouse |  | pcs | 1 | 0 | 0 | 0 | 0 |
| 18 | Sand washer |  | pcs | 1 | 1 | 0 | 0 | 1 |
| 19 | Trawl (semitrailer) |  | pcs | 0 | 0 | 0 | 0 | 0 |
| 20 | Crushing machine |  | pcs | 0 | 0 | 0 | 0 | 0 |
| 21 | Batching plant |  | pcs | 0 | 0 | 0 | 0 | 0 |
| 22 | Other equipment |  | pcs | 0 | 0 | 0 | 0 | 0 |
| TOTAL |  | pcs | 159 | 185 | 0 | 0 | 185 |

- Subcontractors:

| N | Name of Subcontractor | Type of work | Section from km – to km | Remarks |
| --- | --- | --- | --- | --- |
| 1 | LLP “Sine Midas Stroy” | Full complex of works | km214.3- km 259,3 | Approved |

Problem issues:

| 1. | Corrected drawings are not available for construction of communications for RMD. |
| --- | --- |
| 2. | Determination is not available for construction of road to hothouse Agrodos |

Variations.

| No. | Name | Financial impact | Approval date | Remarks |
| --- | --- | --- | --- | --- |
| 01 | Variation Order Lot 5 | Increase for 495 887 645,4 KZT including VAT | Approved without comments Letter No. 23-23-05/415 dated 03.11.2014 |  |
| 02 | Variation Order Lot 5 | Reduce for 512 074 808,83 KZT including VAT | Approved with comments Letter No. 23-23-05/370 dated 27.10.2014 |  |