As per 16.06.2015

INFORMATION

For implementation of section km 259.3 – km 304.4 “Almaty-Khorgos” of Western Europe – Western China Road Project in Almaty Region Lot 6

Main Contractor – JV «Todini /Impregilo-Kazakhdorstroi»

Contract – EWRP-214.3-259.3-ICB(W)-001/2013

Contract Amount - 15 946 601 999 KZT

Contract signed – 30.07.2013

Construction period – 22 / 10 / 2013 – 09 /.04 / 2016

Disbursed in 2014 году – 4 710 841 617 KZT

Disbursement plan for 2015 – 5 823 500 000 KZT

Engineer CSC – Sweroad/Gauff/QPEC

Designer – LLP “Kazakhstan zholdary”

- Main Project characteristics

| Length, km | 45 |
| --- | --- |
| Culverts, no’s. | 52 |
| Bridges and cattle creeps, nos. | 0 |
| Overpasses, nos. | 0 |
| Interchanges, no’s. | 2 |
| Earthworks, thous.m3 | 5 072 |
| Sub base, km/thous.m3 | 45 / 458 |
| CSCSM, km/thous.m3 | 45 / 197 |
| Cement concrete pavement, km/thous.m3 | 45 / 219 |

- Analysis for work schedule performance:

| N | Description of works | Total under Contract | Plan for 2015 | Actual for current date since 2015 start |
| --- | --- | --- | --- | --- |
| 1. | Earthworks (thous.m3) | 5 072,0 | 1 271,1 | 1 086.2 |
| 2. | Sub base, km | 45,0 | 29,55 | 11.70 |
| 3. | Base course from CSCSM, km | 45,0 | 33,06 | 11.83 |
| 4. | Cement concrete pavement, km | 45,0 | 36,77 | 15.56 |
| 5. | Bridges and overpasses, nos. | 0 | 0 |  |
| 6. | Culverts, nos. | 53 | 14 | 53 completed |

- Procurement of materials for 2015:

| N | Description of material | Total under Contract | Plan for 2015 | Actual for current date since 2015 start | % | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Crushed stone, thous.m3 | 358,38 | 286,95 | 296.63 | 82.7 |  |
| 2. | Sand, thous.m3 | 38,97 | 36,09 | 36,74 | 94.2 |  |
| 3. | SGM, thous.m3 | 489,93 | 449,61 | 395.08 | 80.6 |  |
| 4. | Cement, thous.m3 | 102,88 | 92,03 | 15.81 | 16.0 |  |
| 5. | RCP, thous.m3 | 3.91 | 3.91 | 3.82 | 97 |  |

- Personnel involvement:

| No | Description | Demand for 2015 | TOTAL actual | Main Contractor |
| --- | --- | --- | --- | --- |
|  |  |  |  | TOTAL | international | local |
| 1 | Engineers and Technicians, Administration | 34 | 33 | 33 | 13 | 20 |
| 2 | Laboratory Assistants and Quality Service | 8 | 16 | 16 | 1 | 15 |
| 3 | Operators of special machinery | 72 | 45 | 45 | - | 45 |
| 4 | Surveyors | 4 | 21 | 21 | 1 | 20 |
| 5 | Drivers of dumpers | 80 | 120 | 120 | - | 120 |
| 6 | Road workers | 40 | 20 | 20 | - | 20 |
| 7 | Welders |  |  |  |  |  |
| 8 | Drivers of cars | - | 24 | 24 | - | 24 |
|  | TOTAL | 238 | 279 | 279 | 15 | 264 |

- Mobilization of equipment:

| No. | Description | Unit | Demand for 2015 | TOTAL actual | Main Contractor Todini | Total for Subcontractors |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | own | rented |  |
| 1 | Bulldozer | nos. | 8 | 15 | 0 | 0 | 15 |
| 2 | Excavator | nos. | 8 | 16 | 0 | 0 | 16 |
| 3 | Loader | nos. | 9 | 30 | 0 | 0 | 30 |
| 4 | Motor grader | nos. | 4 | 8 | 0 | 0 | 8 |
| 5 | Rollers | nos. | 20 | 15 | 0 | 0 | 15 |
| 6 | Dumpers | nos. | 80 | 60 | 0 | 0 | 60 |
| 7 | Water tank | nos. | 10 | 10 | 0 | 0 | 10 |
| 8 | Petrol tank | nos. | 6 | 0 | 0 | 0 | 0 |
| 9 | Asphalt paver | nos. | 4 | 3 | 0 | 0 | 3 |
| 10 | Concrete paver | nos. | 1 | 1 | 0 | 0 | 1 |
| 11 | Milling machine | nos. | 1 | 0 | 0 | 0 | 0 |
| 12 | Truck crane | nos. | 2 | 6 | 0 | 0 | 6 |
| 13 | Distributor | nos. | 1 | 0 | 0 | 0 | 0 |
| 14 | ACP | nos. | 1 | 0 | 0 | 0 | 0 |
| 15 | CCP | nos. | 1 | 1 | 0 | 0 | 1 |
| 16 | Crusher | nos. | 1 | 1 | 0 | 0 | 1 |
| 17 | Cement warehouse | nos. | 1 | 0 | 0 | 0 | 0 |
| 18 | Sand washer | nos. | 1 | 0 | 0 | 0 | 0 |
| 19 | Trawl (semi-trailer) | nos. | 0 | 0 | 0 | 0 | 0 |
| 20 | Crushing machine | nos. | 0 | 0 | 0 | 0 | 0 |
| 21 | Concrete mixer | nos. | 0 | 0 | 0 | 0 | 0 |
| 22 | Other machinery | nos. | 0 | 9 | 0 | 0 | 9 |
| TOTAL | nos. | 159 | 175 | 0 | 0 | 175 |

- Subcontractors:

| No. | Name of Subcontractor | Type of work | Section from km to km | Remarks |
| --- | --- | --- | --- | --- |
| 1 | LLP “Sine Midas Stroi” | Full complete of works | km259.3- km 304.4 | approved |

Problem issues:

- No access to the site of the last kilometer (area of connection). It is not clear for location of Customs Post, coordinates were not determined. In addition, from CH 887+65 to CH 899+64 there is a neutral zone (zone of impact of China), and access is not possible to this section. When determination of location for Customs Post we request you to consider the location of bridges across Khorgos River at CH 873+96 and across Exclusion Zone (EZ) at CH 888+10.

- Container for video surveillance in border zone was not re-approved

Variation Orders.

| No. | Name | Financial impact | Approval date | Remarks |
| --- | --- | --- | --- | --- |
| 01 | Variation Order Lot 6 | Increase for 529 871 101.21 KZT including VAT | Approved without comments Letter No 23-23-05/416 dated 03.11.2014 |  |
| 02 | Variation Order Lot 6 | Increase for 365 901 682.29 KZT including VAT | Approved without comments Letter No 23-23-05/506 dated 12.11.2014 |  |
| 03 | Variation Order Lot 6 | Reduce for 619 290 836.0 KZT including VAT | Approved without comments Letter No 23-23-05/367 dated 27.10.2014 |  |