As per 20.01.2017

INFORMATION

For implementation of section km 259.3 – km 304.4 “Almaty-Khorgos” of Western Europe – Western China Road Project in Almaty Region Lot 6

Main Contractor – JV «Todini /Impregilo-Kazakhdorstroi»

Contract – EWRP-259.3-304.4-ICB(W)-001/2013

Contract Amount - 15 670 120 051 KZT

Contract signed – 30.07.2013

Disbursed in 2013-2016 – 15 650 041 154.20 KZT

Disbursement plan for 2015 – 5 823 500 000 KZT

Engineer CSC – Sweroad/Gauff/QPEC

Designer – LLP “Kazakhstan zholdary”

- Main Project characteristics

| Length, km | 45 |
| --- | --- |
| Culverts, no’s. | 52 |
| Bridges and cattle creeps, nos. | 0 |
| Overpasses, nos. | 0 |
| Interchanges, no’s. | 2 |
| Earthworks, thous.m3 | 7 238 |
| Sub base, km/thous.m3 | 45 / 458 |
| CSCSM, km/thous.m3 | 45 / 197 |
| Cement concrete pavement, km/thous.m3 | 45 / 219 |

- Analysis for work schedule performance:

| № | Description of works | Total under Contract | Performed till 2016 | Actual for current date TOTAL | Performed in 2016-2017 | Remaining from Contract. |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 20.01.2017 |  | remaining | % |
| 1 | Earthworks (thous.m3) | 5 333,40 | 4 808,70 | 4 876,99 | 68,29 | 0,00 | 100% |
|  | Strengthening layer for embankment |  | 444,91 | 456,41 | 11,50 |  |  |
| 2 | Subbase, km | 43,46 | 41,68 | 42,69 | 1,01 | 0,77 | 98% |
| 3 | Base course from CSCSM, km | 43,38 | 36,18 | 42,61 | 6,43 | 0,77 | 98,22% |
| 4 | Cement concrete pavement, km | 42,92 | 35,61 | 42,15 | 6,54 | 0,77 | 98,20% |
| 5 | Expansion joint | 261,50 | 45,76 | 201,09 | 155,33 | 106,17 | 76,90% |
| 6 | Strengthening of shoulders, km | 42,92 | 0,00 | 24,70 | 24,70 | 18,22 | 57,55% |
| 7 | Base of dividing strip, km | 42,92 | 0,00 | 42,15 | 42,15 | 0,77 | 98,20% |
| 8 | Asphalt, dividing strip, km | 42,92 | 0,00 | 42,15 | 42,15 | 0,77 | 98,20% |
| 9 | Guardrail (axe), rm | 89,00 | 0,00 | 70,46 | 70,46 | 18,54 | 79,17% |
| 10 | Guardrail (shoulder), rm. | 73,69 | 0,00 | 1,24 | 1,24 | 72,45 | 1,68% |
| 11 | Road marking, rm. | 42,92 | 0,00 | 0,00 | 0,00 | 42,92 | 0,00% |
| 12 | Chutes, rm | 27,41 | 0,00 | 25,87 | 25,87 | 1,54 | 94,39% |
| 13 | Culverts, pcs/ | 58,00 | 55 | 58,00 | 2,00 | 0,00 | 100,00% |
| 14 | Strengthening layer for embankment (culverts) |  | 19 | 18,50 |  |  |  |
| 15 | Geotextile, m2 |  | 557 | 567,13 | 9,86 |  |  |

- Procurement of materials:

| N | Description of material | Total under Contract | Plan for 2016 | Actual for current date | Suppliers |
| --- | --- | --- | --- | --- | --- |
| 1. | Crushed stone, thous.m3 | 357,69 | 17,89 | 17,60 | “JV SineMidasStroi” |
| 2. | Sand, thous.m3 | 38,97 | 0.36 | 0,36 |  |
| 3. | SGM, thous.m3 | 493,55 | 20,13 | 20,13 | “JV SineMidasStroi” |
| 4. | Cement, thous.m3 | 102,88 | 19,81 | 14,41 |  |
| 5. | RCP, thous.m3 | 3.91 | 0.02 | 0,00 | LLP AZMK |

- Personnel involvement:

| N | Description | Demand for 2016 | TOTAL actual | Main Contractor | Subcontractors |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | TOTAL | foreign | local | TOTAL |
| 1 | Engineers and Technicians, Administration | 37 | 20 | 17 | 12 | 5 | 3 |
| 2 | Laboratory Assistants and Quality Service | 8 | 3 | 3 | 1 | 2 | 0 |
| 3 | Operators of special machinery | 72 | 5 | 0 | 0 | - | 5 |
| 4 | Surveyors | 4 | 3 | 0 | 0 | - | 3 |
| 5 | Drivers of dumpers | 80 | 5 | 0 | 0 | - | 5 |
| 6 | Road workers | 40 |  | 0 | 0 | - |  |
| 7 | Welders |  |  | 0 | 0 |  |  |
| 8 | Others | - |  | 0 | 0 | - |  |
|  | TOTAL | 241 | 36 | 20 | 13 | 7 | 16 |

- Mobilization of equipment:

| N | Description of equipment | Unit | Demand for 2016 | TOTAL actual | Main Contractor Todini | Total for Subcontractors |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | own | rented |  |
| 1 | Bulldozer | pcs | 8 | 0 | 0 | 0 | 0 |
| 2 | Excavator | pcs | 8 | 2 | 0 | 0 | 2 |
| 3 | Loader | pcs | 9 | 1 | 0 | 0 | 1 |
| 4 | Motor grader | pcs | 4 | 1 | 0 | 0 | 1 |
| 5 | Rollers | pcs | 16 | 1 | 0 | 0 | 1 |
| 6 | Dumpers | pcs | 80 | 5 | 0 | 0 | 5 |
| 7 | Water tank | pcs | 10 | 0 | 0 | 0 | 0 |
| 8 | Petrol tank | pcs | 6 | 0 | 0 | 0 | 0 |
| 9 | Asphalt paver | pcs | 4 | 0 | 0 | 0 | 0 |
| 10 | Concrete paver | pcs | 1 | 0 | 0 | 0 | 0 |
| 11 | Milling machine | pcs | 0 | 0 | 0 | 0 | 0 |
| 12 | Mixer | pcs | 0 | 0 | 0 | 0 | 0 |
| 13 | Truck crane | pcs | 1 | 0 | 0 | 0 | 0 |
| 14 | ACP | pcs | 1 | 1 | 0 | 0 | 1 |
| 15 | CCP | pcs | 1 | 3 | 0 | 0 | 3 |
| 16 | Crusher | pcs | 1 | 1 | 0 | 0 | 1 |
| 17 | Other equipment | pcs | - |  | 0 | 0 |  |
| TOTAL | pcs | 159 | 15 | 0 | 0 | 15 |

- Subcontractors:

| N | Name of Subcontractor | Type of work | Section from km – to km | Remarks |
| --- | --- | --- | --- | --- |
| 1 | LLP “Sine Midas Stroi” | Full complex of works | km259.3- km 304.4 | Approved |

Problem issues:

| 1. | There is no decision on construction of section in frontier zone |
| --- | --- |