# Work progress report

“Western Europe – Western China” International transit corridor reconstruction project in Kyzylorda oblast.

Contract: SWRP-1702-1752-ICB(W/7)-001/2013

31.03.2017

| № | Description | Details |
| --- | --- | --- |
| 1 | Contractor | Evrascon JSC |
| 2 | Construction Supervision Consultant | “Kazdorproject” LLP |
| 3 | Contract | SWRP-1702-1752-ICB-(W/7)-001/2013 |
| 4 | Date of Contract award | 23 July 2013 |
| 5 | Contract amount taking into account VO | 8 323 920 292,09 KZT |
| 6 | Length of road | 49 км |
| 7 | Engineering structures | Bridges and overpasses 13 pcs., culverts 45 pcs. |
| 8 | Commencement date | 06 September 2013. |
| 9 | Initial completion date | 06 December 2014 |
| 10 | Approved extension of Contract term | 05 October 2015 |
| 11 | Approximate date of works completion | October 2017 |
| 12 | Advance payment | 1 221 721 945,94 KZT |
| 13 | Disbursed taking into account the last approved Certificate | 5 719 052 139,56 KZT |
| 14 | Remaining amount for disbursement under the Contract | 2 604 868 152,53 KZT. |

Progress of main works:

| № | Decsription of works | Total under Contract | Actual from beginning of construction | Remainder as of 31.03.17 | Performance in % |
| --- | --- | --- | --- | --- | --- |
| 1 | Road |
| 1.1 | Earthworks, km | 49 | 49,0 | 0,0 | 100% |
| 1.2 | Subbase, km | 49 | 49,0 | 0,0 | 100% |
| 1.3 | Lower layer of base С-4, km | 49 | 49,0 | 0,0 | 100% |
| 1.4 | Upper layer of base 12 cm, km | 49 | 49,0 | 0,0 | 100% |
| 1.5 | Binding course 10 cm, km | 49 | 49,0 | 0,0 | 100% |
| 1.6 | Wearing course from CSMA, km | 49 | 49,0 | 0,0 | 100% |
| 1.7 | Strengthening of river bed and bottom at entrance and exit (pipe), pcs | 45 | 25 | 20 | 55% |
| 1.8 | Bridges, pcs. | 13 | 12,6 | 0,4 | 97% |
| 1.9 | Strengthening of shoulders С6, km (right and left sides) | 98 | 72 | 26 | 73% |
| 1.10 | Construction of intersections and junctions, rest area at level of binding course Н=10 cm, pcs. | 33 | 27 | 6 | 81% |
| 1.11 | Construction of intersections and junctions, rest area at level CSMA Н=5 cm, pcs | 33 | 0 | 33 | 0% |
| 1.12 | Strengthening of slope by geogrid with filling of topsoil, m2 | 142 843 | 130 843 | 12 000 | 92% |
| 1.13 | Strengthening of slope by geotextile, m2 | 59 745 | 57 845 | 1 900 | 96% |
| 1.14 | Chutes for water collection at roadside, rm | 5 515 | 5 515 | 0 | 100% |
| 1.15 | Discharge at shoulder, pcs. | 106 | 6 | 100 | 5% |
| 1.16 | Chutes at slopes, pcs. | 1361 | 60 | 1301 | 4% |
| 1.17 | Extinguisher at embankment bed, pcs. | 106 | 6 | 100 | 6% |
| 1.18 | Curbstones ant bus stops and rest areas БР100х30х18, rm | 2 123 | 0 | 2 123 | 0% |
| 1.19 | Curbstones ant bus stops and rest areas , 100х20х0,8, rm | 6 430 | 2 932 | 3 498 | 46% |
| 1.20 | Land restoration of road, % | 100 | 0 | 100 | 0% |
| 2 | Road furniture |
| 2.1 | Bus shelters, pcs | 11 | 11 | 0 | 100% |
| 2.2 | Toilets woth 2 seats, total 15 pcs, % | 100 | 70 | 30 | 70% |
| 2.3 | Equipment for bus stops and rest areas (benches, bins), % | 100 | 0 | 100 | 0% |
| 2.4 | Pedestrian crossings at bus stops and rest areas, rm | 3 600 | 0 | 3 600 | 0% |
| 2.5 | Guardrail of type 11-ДО-ММ 1 and 11-ДО-ММ, rm | 32 719 | 15 703 | 17 016 | 49% |
| 2.6 | Road marking | 203 551 | 0 | 203 551 | 0% |
| 2.7 | Permanent road signs, pcs | 487 | 279 | 208 | 57% |
| 2.8 | Filled berms under road signs, m3 | 17 074 | 8 642 | 8 432 | 51% |
| 2.9 | Road cones. pcs | 1 923 | 0 | 1 923 | 0% |
| 2.10 | Fencing by mesh wire, rm | 17 910 | 0 | 17 910 | 0% |
| 2.11 | Kilometer signs, pcs | 49 | 49 | 0 | 100% |
| 3 | Transport interchange |
| 3.1 | Construction of CSMA Н=5cm, m2 | 19 464 | 19 464 | 0 | 100% |
| 3.2 | Chutes for water collection at roadside, rm | 1 700 | 1 700 | 0 | 100% |
| 3.3 | Discharge at shoulder, pcs | 34 | 34 | 0 | 100% |
| 3.4 | Chutes at slopes, pcs | 775 | 700 | 75 | 90% |
| 3.5 | Extinguishers at embankment bed, pcs | 34 | 32 | 2 | 94% |
| 3.6 | Strengthening of slope by geogrid with filling by topsoil, m2 | 30 000 | 0 | 30 000 | 0% |
| 3.7 | Guardrail of type 11-ДО-ММ 1 and 11-ДО-ММ, rm | 10 930 | 0 | 10 930 | 0% |