INFORMATION

about «Khorgos – Almaty – Shymkent – border of Uzbekistan» road section km 593-632

of «Western Europe – Western China» project in South-Kazakhstan region  
  «Dena Rahsaz and Sargin» JV (Iran/Turkey)

as of 29.06.2015

General contractor –  «Denf Rahsaz and Sargin» JV (Iran/Turkey)

The contract SWRP-593-632-IBC(W)-001/2013 dated 27.06.2013

The contract was signed on 27.06.13 - «Den Rahsaz and Sargin» JV (Iran/Turkey)

The contract amount – 15 751 627 460 tenge

Construction period – 24 months

CSC Engineer – Temelsu/Consult JV

Designer  – «SK Engineering »

- Analysis of work performance schedule compliance:

| № | Work description | Total under the contract | Plan on 2015 | Fact on current date | Fact for whole construction period |
| --- | --- | --- | --- | --- | --- |
| 1. | Earth works (thous.m3) | 1966 | 757,6 | 468,54 | 1676,96 |
| 2. | Subbase, km | 81 | 32,3 | 9,06 | 57,06 |
| 3. | Base course from CSSCM, km | 81 | 33,95 | 10,15 | 56,15 |
| 4. | High porous a/c, 12cm, km | 81 | 44,55 | 13,66 | 49,99 |
| 5. | Coarse-grained а/c, 10 cm, km | 81 | 46,94 | 14,9 | 43,19 |
| 6. | CSMA, 5 cm, km | 81 | 81 | 0 | 0 |
| 7. | Bridge, Nos. | 9 | 5,5 | 2,6 | 6,1 |
| 8. | Culverts, Nos. | 64 | 42 | 6 | 28 |
| 9. | Tunnel (one direction), m | 1382,6 | 1049,05 | 405,35 | 738,9 |

- Materials procurment for 2015:

| № | Material description | Total under the contract | Plan on 2015 | Fact for 2015 | Fact for whole construction period | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Crushed-stone, thous.m3 | 416,387 | 97,01 | 27,83 | 326,6 | "Kaz Intex" LLP, "Dena Rahsaz and Sargyn" JV |
| 2. | Sieve, thous.m3 | 122,652 | 37,15 | 13 | 98,5 | "Kaz Intex" LLP, "Dena Rahsaz and Sargyn" JV |
| 3. | GSM, thous.m3 | 374,900 | 96,9 | 67,4 | 345,2 | Borrow pit PK 265 |
| 4. | Bitumen, thous.tenge | 28,265 | 17,67 | 7,86 | 21,46 | "KazBitumService" JSC, "Kaztechnoimport LTD" LLP, "TPK Energyplus" LLP, "Bitoil" LLP, «Omar Trans» LLP |

- Equipment and machinery: 280 Nos.

- Personnel: 846 persons

- Tunnel:

Right side: Exit – 147,3 m, Entry – 212,8 m

Left side: Exit – 152,3 m, Entry – 226,5 m

Shaft tunnel – 51 m

- Disbursement:

In 2013 certificates are paid for the amount of - 782 183 661,33 tenge

In 2014 certificates are paid for the amount of – 6 337 408 473,51 tenge

In 2015 certificates are paid for the amount of – 1 588 770 318,28 tenge

Total for 2013-2015 years certificates are paid for the amount of – 8 708 352 453,12 tenge

Issues of concern:

-  work performance schedule delay under tunnel construction, and also under construction of subbase, base course and a/c pavement, (taking into account actual progress of work, the Contractor will not confine into construction contract period). The Engineer is regularly informing in written form the Contractor about delay from WS and suggests ways of problem solution, influencing on slow work process.

- in view of delay it’s necessary additionally to involve subcontractors for culvert construction.

- DED on RRP have been delivered into Government expert review, but up to now Government expert review conclusion has not been obtained.

Additional works:

| № VO | Description | Amount | Status |
| --- | --- | --- | --- |
| 1 | Water pipe relocation, PK 139, 150+35, 164+94, 225+00 | 13 200 000,00 | Variation Order No.1 (approved by CfR) |
| 2 | PTL 10-35 kW relocation | 32 879 000,00 | Variation Order No.2 (approved by CfR) |
| 3 | RUT line relocation, PK 61, PK 78, PK 120, Beeline communication cable relocation, PK321, PK 368+00-370+00 | 4 862 000,00 | Variation Order No.3 (approved by CfR) |
| 4 | Old r/c ring change (4х2,5m) to new ones at PK 220+95, PK 81в+81, total 186 Nos. | 55 570 000,00 | Variation Order No.4 (approved by CfR) |
| 5 | Water pipe relocation according to citizens request PK 140, 185, 368, 223 | 59 950 000 | Variation Order No.5 (returned to rework) |
| 6 | Replacement of precast bridge structures to in-situ (3 bridges, 4 overpasses, 2 passages for agricultural equipment) | Without value change | Variation Order No.6 (returned to rework) |
| 7 | Removal of fertile soil layer | 37 361 764,59 | Documents are being prepared |
| 8 | Change of cement concrete pavement to asphalt concrete, 40,5 km | Without value change | Documents are being prepared |
| 9 | Tunnel construction instead of excavation | Without value change | Documents are being prepared |
| 10 | Shoulder protection on existing road, GSM=10 080 m3 | 9 908 640,00 | Documents are being prepared |
| 11 | Additional ramps and replacement of pipes to cattle passes (6 aramps, 4 pipes) | 106 842 053,00 | Documents are being prepared |
| 12 | Culverts repair on existing road, construction of drainage gutter | Volumes are under determination by fact | Documents are being prepared |
| 13 | RRP Construction | Project in government expert review | Documents are being prepared |
| Total | 320 573 457,59 |  |