Information

Salini Costruttori S.p.A

South West road project: Western Europe – Western China International Transit Corridor

km 1240-1330 (Lot №1) in Kyzylorda oblast

length 90 km.

Contractor:  Salini Costruttori S.p.A

Engineer:    Isan Corporation in association with Zhol Sapa LLP

Contract amount: KZT 12 061 123 911,3;

Disbursed in 2010- 2012 - KZT 9, 709 618 bln.;

Amount of works to be done in 2013 - KZT 4,23 bln.

Laboratory.

Laboratory in Lot № 1 is located at PK 471 (1287 km), it is fully equipped.

Compliance with Work Program  (Plan for  2013)                      13.09.2013

| № | Description of works | Total in Contract | Performed in 2010-2012 | Planned for 2013 | Fact as of 13.09. 2013 | Fact for September 2013 | Total for 2010-2013 | Remaining for 2013 (+,-) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks, thous. m3: slope of subgrade and junctions | 647,23 | 599,32 | 27,4 | 25,2 | 0 | 624,46 | -2,2 |
| 2 | Subbase, km | 90 | 90 | 0 | 0 | 0 | 90 | - |
| 3 | Base coarse С-4, km | 90 | 90 | 0 | 0 | 0 | 90 | - |
| 4 | Upper layer, km | 90 | 90 | 0 | 0 | 0 | 90 | - |
| 5 | Lower layer, km | 90 | 90 | 0 | 0 | 0 | 90 | - |
| 6 | Upper layer from CSMA, km | 90 | 10,63 | 79,4 | 49,13 | 1,71 | 59,76 | -30,27 |
| 7 | Shoulder stabilization | 90 | 10,63 | 79,4 | 26,0 | 3,0 | 36,63 | -53,4 |
| 8 | Culverts, pcs. | 14 | 14 | 0 | 0 | 0 | 14 | 0 |

| Procurement of material | Plan for 2013 | Fact for 13.09.2013 | Supply Per day | Required (+,-) | Remains in the sections |
| --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone thous./tons | 237,99 | 149,95 | 0 | -88,04 |  |
| Incl.: - 10-20 | 94,68 | 71,22 | 0 | -23,46 | 3,30 |
| - 0-40 | 138,96 | 48,81 | 0 | -90,15 | 0 |
| - 0-5 | 27,49 | 20,22 | 0 | -7,27 | 2,38 |
| 2 | Bitumen thous./tons | 5,7 | 3,97 | 0 | -1,73 | 0,04 |
| 3 | Cellulose additive for CSMA, t | 425 | 531 | 0 | 106 | 167,7 |
| 4 | Min.fine thous./tons | 9,58 | 5,17 | 0 | -4,41 | 0,14 |

| Equipment required for work schedule implementation for 2013 |
| --- |
| Analysis of availability and condition of Road Building Equipment |
| № Description Requirement Available at site Repairs Additionally Required Section PK 0 – PK 900 “RKDS” LLP (Salini) 1 Автогрейдер/ Grader 4 2 2 - 2 Бульдозер/Dozer 5 3 2 - 3 Экскаватор/Excavator 4 2 2 - 4 Погрузчики/Loader 5 4 1 - 5 Катки грунтовые/Roller for earthwork 5 3 2 - 6 Катки для асфальта/Roller for asphalt 6 4 1 1 7 Водовозы/Water tank 4 2 2 - 8 Асфальтоукладчики/Paver 4 4 0 - 9 Фреза/Milling machine 1 - 1 - 10 Автокран/Crane 2 1 1 - 11 Автосамосвалы на технологию/Dumper for technology 20 15 5 - 12 Автосамосвалы На перевозку ДСМ/Dumper for transporting materials 20 11 4 5 13 АБЗ/Asphalt plant 2 2 0 - 14 Прочая техника/Others 18 17 1 - Total/Всего 100 70 24 6 |  |  |  |  |  |