Western Europe – Western China International Transit Corridor Road reconstruction project

Aktobe-Martuk (km 0 - 102)

Beginning of the Project – October 2010

Completion of the project – April 2013

Extension due to the project changes of Bridge over Ilek river

With the approach km 63-72 – 1 October 2013

Cost of the project – 13,989 billion tenge

Disbursed – 16,454 billion tenge

Variation order of project – 1, 164 billion tenge

Escalation – 5,026 billion tenge (36%)

Main works are done.

Defects

km94+500-97+500 – replacement of material on the roadside

Pipe km 91+100 – riprap stone construction.

Clearance of channels in the pipes.

Correction geometry of berm at road signs.

Contractor’s resources

Personnel

Contractor  (Turkish company) jointly with the Subcontractor Ivrus (Kazakhstan) have recruited:

- Up to 60 foreign experts

- Up to 520 local specialists

Settings for all employees (camp, office apartments) were in Aktobe and Martuk village

Equipment

- 40% of the equipment (Contractors and Subcontractors) were new

- 60% were second hand equipments

Facilities on equipment maintenance (repair room, stores, petrol and service station) were in Aktobe and in Martuk village.

Main Reinforced Cement Constructions

km 24+827: Overpass through railroad [18м+24м+18м spans]

km 35+563: Bridge[5 spans x 18м]

km 65+371: Bridge through Ilek river[12 spans x 24м]

km 75+072: Overpass through railroad [18м+24м+18м spans]

Public issues

- From July 2010 to October 2013:

- The existing road has always been in working condition, local and international transportation have never frustrated. Contractor's plan for traffic management was executed, and the temporary bypass road was built to go around Contractor’s site, which is under construction.

- There were no reports of any accidents in the work of the Contractor,

- Several fatal accidents have been reported, especially after the asphalt laying

- We recorded a lot of cars’ breakdowns on the main road due to the unsatisfactory state of transport.

Special attention was paid to the construction of rest areas (in the amount of 4 pcs) in the service of people living along the road. Planned and improved approched to the villages and to Martuk village due to the acute need associated, added some bus shelters, in general there are 14 stops.

- Quality Assurance / Quality Control

- Work has performed on the basis of an international standard in accordance with FIDIC 1999 and GOST. Supervision was constantly involved in the daily assistance of the Contractor upon the realization of its quality plans, as well as the systematic sequential execution of its internal quality plan.