Information on implementation of section km 593-632

«Khorgos – Almaty – Shymkent – border of the Republic of Uzbekistan» road

of the «Western Europe – Western China» project in SKO

«Dena Rahsaz & Sargin» JV Contractor (Iran/Turkey)

01.04.2016

The Contractor – «Dena Rahsaz & Sargin» JV (Iran/Turkey)

Contract SWRP-593-632-IBC(W)-001/2013 dated 27.06.2013

The Contract was signed in 27.06.2013 - «Dena Rahsaz & Sargin» JV (Iran/Turkey)

Contract price –15 751 627 460 KZT

Construction time – 24 months

The Engineer, CSC – «Temelsu/Consult» JV

Project Designer – «SK Engineering» LLP

- Analysis of the Work Program performance:

| Description | Unit | Total under Contract | Performed until 2016 | Plan for 2016 | Actual for 2016 | Total remaining | % of performance |
| --- | --- | --- | --- | --- | --- | --- | --- |
| •Earthworks | th. m3 | 1966,0 | 1938 | 28 | 3,7 | 24,3 | 13,2% |
| •Subbase H-25 cm | km | 81,00 | 75,18 | 5,82 | 0 | 5,82 | 0% |
| • Base course construction H-25 cm | km | 81,00 | 73,6 | 7,4 | 0 | 7,4 | 0% |
| • highporous asphalt-concrete, 12 cm | km | 81,00 | 70,51 | 10,49 | 0 | 10,49 | 0% |
| • coarse grained asphalt-concrete, 10 cm | km | 81,00 | 67,96 | 13,04 | 0 | 13,04 | 0% |
| •CSMA, 5 cm | km | 81,00 | 43,88 | 37,12 | 0 | 37,12 | 0% |
| •Bridges and Overpasses | pcs | 9,00 | 8,9 | 0,1 | 0 | 0,1 | 0% |
| •Culverts | pcs | 65,00 | 41 | 24 | 0 | 27 | 0% |
| Tunnel | % | 100,00 | 67,5 | 32,5 | 2 | 30,5 | 6,5% |

- Procurement of materials for 2016:

| № | Description of the material | Total under the Contract | Plan for 2016 | Actual for 2016 | Remains | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Crushed stone, ths.m3 | 416,387 | 41 | 0 | 0 | KazInteks" LLP, “Dena Rahsaz &Sargin” JV |
| 2. | Reinforced concrete products | 6,1 | 2,57 | 0 | 0 | Ak Zhol LLP |
| 3. | GSM, ths.m3 | 374,900 | 22 | 4,35 | 17,65 | Borrow pit at PK 265 |
| 4. | Bitumen, ths.ton | 28,265 | 4,29 | 0 | 0 | JSC "KazBitum Service", "Kaztechnoimport LTD" LLP, "TPK Energoplyus” LLP, "Bitoil" LLP, «Omar Trans» LLP |

- Equipment: 155 units

- Personnel: 119 people, 42 of them are foreigners

- Tunnel:

RHS: Exit – 193,5 m, Entrance – 218,2 m.

LHS: Exit – 262,85 m, Entrance – 411,9 m.

Adit – 51 m.

Overall drilled 1086,45 m out of 1382,6 m (78%)

- Disbursement:

In 2013 signed IPC for the amount - 782 183 661,33 tenge

In 2014 signed IPC for the amount – 6 337 408 473,51 tenge

In 2015 signed IPC for the amount – 4 130 055 357,77 tenge

Total for 2013-2015 signed IPC for the amount – 11 249 657 492,61 tenge

Issues of concern:

- Significant delay on construction of culverts, 63% performed.

- There is financial debt to subcontractors, material suppliers and landlord of equipments.

Additional works:

| No. of the VO | Description | Amount | Status |
| --- | --- | --- | --- |
| 1 | Relocation of water pipelines, PK 139, 150+35, 164+94, 225+00 | 13 200 000,00 | VO No.1 (approved by CFR) |
| 2 | Relocation of the Power Transmission Line 10-35 kW | 32 879 000,00 | VO No.2 (approved by CFR) |
| 3 | Relocation of RUT, PK 61, PK 78, PK 120, relocation of telecommunication cable Beeline, PK 321, PK 368+00-370+00 | 4 862 000,00 | VO No.3 (approved by CFR) |
| 4 | Relocation of the old reinforced-concrete pipe elements (4х2,5 m) to the new at PK 220+95, PK 81в+81, total 186 un. | 55 570 000,00 | VO No.4 (approved by CFR) |
| 5 | Relocation of water supply line by request of residents at PK 140, 185, 368, 223 | 59 950 000 | VO No.5 (approved by CFR) |
| 6 | Replacement of precast bridge structures to cast in-situ (3 bridges, 4 overpasses, 2 passages for agriculture equipments) | Without change of cost | VO No.6 (approved by CfR) |
| 7 | Removal of topsoil, preparation of existing surface for embankment, water drain channels | 38 712 166,39 | Vo no. 7 (sent to the CfR) |
| 8 | Replacement of the cement-concrete pavement to the asphalt-concrete pavement , 40,5 km, construction of tunnel instead of cutting | Without change of cost | Under preparation |
| 9 | Geomemebrane for tunnel |  | Under preparation |
| 10 | Rerouting TUSM-11 PK371-377 | 3 036 008,51 | Under preparation |
| Total | 205 173 166,39 |  |