Background information on implementation of section km 593-632

road «Khorgos – Almaty – Shymkent – border of the Republic of Uzbekistan»

of the project «Western Europe – Western China» in SKO

the Contractor «Dena Rahsaz & Sargin» JV (Iran/Turkey)

02.09.2015

The Contractor – «Dena Rahsaz & Sargin» JV (Iran/Turkey)

Contract SWRP-593-632-IBC(W)-001/2013 dated 27.06.2013

The Contract was signed 27.06.2013 - «Dena Rahsaz & Sargin» JV (Iran/Turkey)

Contract price –15 751 627 460 KZT

Construction time – 24 months

The Engineer, CSC –  «Temelsu/Consult» JV

Project Designer – «SK Engineering»

- Analysis of performance by the Work Program:

| Description | Unit | By Contract | Executed in 2013 | Executed in 2014 | 2015 |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Plan for 2015 | Actual for 2015 | Total executed | Remains |
| •Earthworks | th. m3 | 1966 | 96,8 | 1111,56 | 757,58 | 653,1 | 1861,5 | 105 |
| •Subbase | km | 81 | 0 | 48 | 33 | 21,11 | 69,1 | 12 |
| •Crushed stone base course | km | 81 | 0 | 46 | 35 | 21,65 | 67,7 | 13 |
| •Bituminous base course, 12 cm | km | 81 | 0 | 36 | 45 | 26,42 | 62,4 | 19 |
| •Bituminous binder course, 10 cm | km | 81 | 0 | 32 | 49 | 27,62 | 59,6 | 21 |
| •SMA, 5 cm | km | 81 | 0 | 0 | 81 | 29,86 | 29,9 | 51 |
| •Bridges and Overpasses | ea | 9 | 0 | 3,5 | 5,5 | 5,07 | 8,57 | 0,43 |
| •Culverts | ea | 65 | 0 | 20 | 45 | 8 | 28,0 | 37 |

- Preparation of materials for 2015:

| № | Description of the material | Total by the Contract | Plan for 2015 | Actual for 2015 | Remains | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Crushed stone, ths.m3 | 416,387 | 97,01 | 71,43 | 25,58 | KazInteks" LLP, “Dena Rahsaz &Sargin” JV |
| 2. | Stone dust, ths.m3 | 122,652 | 37,15 | 28 | 9,15 | KazInteks" LLP, “Dena Rahsaz &Sargin” JV |
| 3. | GSM, ths.m3 | 374,900 | 96,9 | 96,4 | 0,5 | Borrow pit at PK 265 |
| 4. | Bitumen, ths.ton | 28,265 | 14,67 | 11,37 | 3,3 | JSC "KazBitum Service", "Kaztechnoimport LTD" LLP, "TPK Energoplyus” LLP, "Bitoil" LLP, «Omar Trans» LLP |

- Equipment: 278 un.

- Personnel: 802 people, 230 of them are foreigners

- Tunnel:

RHL: Outlet – 179,0 m, Inlet – 213,2 m.

LHS: Outlet – 199,5 m, Inlet – 258,8 m.

Adit – 51 m.

- Disbursement:

In 2013 signed IPC for the amount - 782 183 661,33 tenge

In 2014 signed IPC for the amount – 6 337 408 473,51 tenge

In 2015 signed IPC for the amount – 2 863 045 255,47 tenge

Total for 2013-2015 signed IPC for the amount – 9 982 637 390,31 tenge

Problematic issues:

- Delay by the Work Programme on construction of the tunnel, as well as on subbase works, the base and asphalt-concrete pavement, (including the actual progress, the Contractor fails to meet the contractual construction time). The Engineer regularly in writing notifies the Contractor about the delay from the Work Programme and offers ways to solve problems affecting to the slow progress of work.

- Due to the delay on construction of culverts, it is necessary to engage additionally subcontractor for construction of culverts. From 15.08.2015 «Ak Zhol» LLP has been suspended works due to the non-payment for executed works by the Contractor.

- There is financial debt to subcontractors, material suppliers and landlord of equipments which significantly affects to the slow progress of work.

Additional works:

| No. of the VO | Description | Amount | Status |
| --- | --- | --- | --- |
| 1 | Relocation of water pipelines, PK 139, 150+35, 164+94, 225+00 | 13 200 000,00 | VO No.1 (approved by CFR) |
| 2 | Relocation of the Power Transmission Line 10-35 kW | 32 879 000,00 | VO No.2 (approved by CFR) |
| 3 | Relocation of RUT, PK 61, PK 78, PK 120, relocation of telecommunication cable Beeline, PK 321, PK 368+00-370+00 | 4 862 000,00 | VO No.3 (approved by CFR) |
| 4 | Relocation of the old reinforced-concrete pipe elements (4х2,5 m) to the new at PK 220+95, PK 81в+81, total 186 un. | 55 570 000,00 | VO No.4 (approved by CFR) |
| 5 | Relocation of water supply line by request of residents at PK 140, 185, 368, 223 | 59 950 000 | VO No.5 (approved by CFR) |
| 6 | Replacement of precast bridge structures to cast in-situ (3 bridges, 4 overpasses, 2 passages for agriculture equipments) | Without change of cost | VO No.6 (approved by PMC) |
| 7 | Removal of topsoil | 37 361 764,59 | Under preparation |
| 8 | Replacement of the cement-concrete pavement to the asphalt-concrete pavement , 40,5 km | Without change of cost | Under preparation |
| 9 | Construction of the Tunnel instead of cutting | Without change of cost | Under preparation |
| 10 | Shoulder protection works on the existing road, GSM=10 080 m3 | 9 908 640,00 | Under preparation |
| 11 | Additional Ramps and replacements of pipes to cattle crossings (6 Ramps, 4pipes) | 106 842 053,00 | Under preparation |
| 12 | Repair of pipes on the existing road, installation of drainage trays | Determinates the amount by actual | Under preparation |
| 13 | Construction of the RMB | Project is in the State Expertise | Under preparation |
| Total | 320 573 457,59 |  |