Information on implementation of section km 593-632

«Khorgos – Almaty – Shymkent – border of the Republic of Uzbekistan» road

of the «Western Europe – Western China» project in SKO

«Dena Rahsaz & Sargin» JV Contractor (Iran/Turkey)

As of 04.04.2017

General Contractor–  «Dena Rahsaz & Sargin» JV (Iran/Turkey)

Contract SWRP-593-632-IBC(W)-001/2013 dated 27.06.2013

The Contract was signed in 27.06.13г. - «Dena Rahsaz & Sargin» JV (Iran/Turkey)

Contract price – 15 751 627 460 KZT

Construction time – 24 months

The Engineer, CSC – «Temelsu/Consult» JV

Project Designer – «SK Engineering» LLP

- Analysis of the Work Program performance:

| № | Description | Unit | Total under Contract | Performed until 2017 | Plan for 2017 | Actual for 2017 | Total remaining | % of performance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Earthworks | thous.m3 | 1966,0 | 1956,0 | 9,9 | 0,0 | 9,9 | 99,49% |
|  | Subbase Н-25 cm | km | 81,00 | 78,0 | 3,0 | 0,0 | 3,0 | 96,30% |
|  | Base course construction Н-25 cm | km | 81,00 | 77,7 | 3,3 | 0,0 | 3,3 | 95,93% |
|  | highporous asphalt-concrete Н-12 cm | km | 81,00 | 75,3 | 5,7 | 0,0 | 5,7 | 92,96% |
|  | coarse grained asphalt-concrete Н-10 cm | km | 81,00 | 73,6 | 7,4 | 0,0 | 7,4 | 90,86% |
|  | CSMA Н-5 cm | km | 81,00 | 44,0 | 37,0 | 0,0 | 37,0 | 54,32% |
|  | Bridges and Overpasses | pcs | 9,00 | 8,9 | 0,1 | 0,0 | 0,1 | 98,89% |
|  | Водопропускные трубы | pcs | 74,00 | 44,0 | 21,0 | 0,0 | 21,0 | 59,46% |
|  | Culverts | % | 100,00 | 69,5 | 30,5 | 0,0 | 30,5 | 69,50% |
|  | Guardrail | km | 55,34 | 13,60 | 41,74 | 0,00 | 41,7 | 24,58% |
|  | Road marking | km | 267,00 | 0,00 | 267,00 | 0,00 | 267,0 | 0,00% |
|  | Ligting | object | 4,00 | 0,00 | 4,00 | 0,00 | 4,0 | 0,00% |
|  | Road signs | pcs | 467,00 | 119,00 | 348,00 | 0,00 | 348,0 | 25,48% |
|  | Kilometer posts | pcs | 41,00 | 0,00 | 41,00 | 0,00 | 41,0 | 0,00% |
|  | Road cones | pcs | 2581,00 | 0,00 | 2581,00 | 0,00 | 2581,0 | 0,00% |
|  | Bus stops | pcs | 7,00 | 0,00 | 7,00 | 0,00 | 7,0 | 0,00% |
|  | Rest areas | pcs | 1,00 | 0,00 | 1,00 | 0,00 | 1,0 | 0,00% |
|  | Toilet | pcs | 6,00 | 0,00 | 1,00 | 0,00 | 1,0 | 0,00% |

- Procurement of materials for 2017:

| № | Description of the material | Total under the Contract | Plan for 2017 | Actual for 2017 | Remains | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Reinforced concrete products | 6,1 | 1,1 | 0 | 1,1 | Ak Zhol LLP, Art Kurylys LLP |
| 2 | Bitumen, ths.ton | 28,265 | 3,04 | 0 | 3,04 | JSC "KazBitum Service", "Kaztechnoimport LTD" LLP, "TPK Energoplyus” LLP, "Bitoil" LLP, «Omar Trans» LLP |

- Tunnel:

RHS: Exit – 193,5 m, Entrance – 218,2 m. Remaining: 280,3 m

LHS: Exit – 262,85 m, Entrance – 411,9 m. Remaining: 18,9 m

Adit – Drilled: 51 m, Remaining: 60 m.

- Disbursement:

Advance payment fro mobilization – 1 575 162 746 KZT

In 2013 paid IPC for the amount - 782 183 661,33 KZT

In 2014 paid IPC for the amount – 6 337 408 473,51 KZT

In 2015 paid IPC for the amount – 4 130 065 357,77 KZT

In 2016 paid IPC for the amount – 715 380 832,43 KZT

Total for 2013-2016 paid IPC for the amount – 11 965 038 325,04 KZT