Information on implementation of section km 593-632

«Khorgos – Almaty – Shymkent – border of the Republic of Uzbekistan» road

of the «Western Europe – Western China» project in SKO

«Dena Rahsaz & Sargin» JV Contractor (Iran/Turkey)

As of 09.01.2017

The Contractor – «Dena Rahsaz & Sargin» JV (Iran/Turkey)

Contract SWRP-593-632-IBC(W)-001/2013 dated 27.06.2013

The Contract was signed in 27.06.2013 - «Dena Rahsaz & Sargin» JV (Iran/Turkey)

Contract price –15 751 627 460 KZT

Construction time – 24 months

The Engineer, CSC – «Temelsu/Consult» JV

Project Designer – «SK Engineering» LLP

- Analysis of the Work Program performance:

| Description | Unit | Total under Contract | Performed until 2016 | Plan for 2016 | Actual for 2016 | Total remaining | % of performance |
| --- | --- | --- | --- | --- | --- | --- | --- |
| •Earthworks | th. m3 | 1966,0 | 1938 | 28 | 21,28 | 6,7 | 99,66% |
| •Subbase H-25 cm | km | 81,00 | 75,18 | 5,82 | 3,77 | 2,0 | 97,47% |
| • Base course construction H-25 cm | km | 81,00 | 73,6 | 7,4 | 4,11 | 3,3 | 95,94% |
| • highporous asphalt-concrete, 12 cm | km | 81,00 | 70,51 | 10,49 | 4,73 | 5,8 | 92,89% |
| • coarse grained asphalt-concrete, 10 cm | km | 81,00 | 67,96 | 13,04 | 5,64 | 7,4 | 90,86% |
| •CSMA, 5 cm | km | 81,00 | 43,88 | 37,12 | 0 | 37,1 | 54,17% |
| •Bridges and Overpasses | pcs | 9,00 | 8,9 | 0,1 | 0,09 | 0,010 | 99,89% |
| •Culverts | pcs | 65,00 | 41 | 24 | 2,8 | 33,20 | 55,14% |
| Tunnel | % | 100,00 | 67,5 | 32,5 | 2,00 | 30,5 | 69,50% |

- Procurement of materials for 2016:

| № | Description of the material | Total under the Contract | Plan for 2016 | Actual for 2016 | Remains | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Crushed stone, ths.m3 | 416,387 | 41 | 41 | 0 | KazInteks" LLP, “Dena Rahsaz &Sargin” JV |
| 2. | Reinforced concrete products | 6,1 | 2,57 | 1,47 | 1,1 | Ak Zhol LLP |
| 3. | GSM, ths.m3 | 374,900 | 22 | 22 | 0 | Borrow pit at PK 265 |
| 4. | Bitumen, ths.ton | 28,265 | 4,29 | 1,25 | 3,04 | JSC "KazBitum Service", "Kaztechnoimport LTD" LLP, "TPK Energoplyus” LLP, "Bitoil" LLP, «Omar Trans» LLP |

- Tunnel:

RHS: Exit – 193,5 m, Entrance – 218,2 m, Remaining: 280,3 m.

LHS: Exit – 262,85 m, Entrance – 411,9 m, Remaining: 18,9 m.

Adit – Drilled: 51 m, Remaining: 60 m.

- Disbursement:

Advance payment fro mobilization – 1 575 162 746 tenge

In 2013 signed IPC for the amount - 782 183 661,33 tenge

In 2014 signed IPC for the amount – 6 337 408 473,51 tenge

In 2015 signed IPC for the amount – 4 130 055 357,77 tenge

In 2015 signed IPC for the amount – 715 380 832, 43 tenge

Total for 2013-2016 signed IPC for the amount – 11 965 038 325,04 tenge

Remaining – 3 663 969 167, 57 tenge