Information as of 01.07.2016

Regarding site implementation at 0-50 km, Project of Almaty- Khorgos Road, Section “International Transit Corridor ‘Western Europe-Western China” with JV «Dogus Insaat &Gulsan Isaat Sanayi Turizm», Lot 1

General Contractor –JV «Dogus Insaat &Gulsan Isaat Sanayi Turizm»

Contract– EWRP-0-50-ICB(W)-001/2013

Signing of contract – 17.07.2013

Construction period –November 2013 –  2016

Contract amount of General Contractor : 25 233 582 346,00 tenge

Disbursement (earlier) till  2016: 10 759 806 070,30 tenge

Disbursement  in 2016 :  5 272 791 970,78  tenge

Disbursement plan: 14 473 776 275,80 tenge

The Consultant – DongSung Engineering Co. Ltd. /Dong Myeong Engineering Consultants and Architecture Co. Ltd./ LLP Zhol Sapa

Designer – KazNIiPI  “Dotrans” LTD

- Project’s key results

| Section length, km | 50 |
| --- | --- |
| Culverts, nos | 120 |
| Bridges and overpasses, km | 30 |
| Overpasses, km | 1 |
| Transport junction, km | 3 |
| Earthworks thous.m3 | 5 282,3 |
| Subbase km.thous/m3 | 50/718,41 |
| Base course km/thous.m3 | 50/263,43 |
| Cement-concrete pavement km/thous.m3 | 50/275,84 |

2. Analysis of work schedule performance

| № | Description | Total as per Contract | Plan for 2016 | Actual for 2016 | Performed from the beginning of the project |
| --- | --- | --- | --- | --- | --- |
| 1 | Earthworks (thous.m3) | 5 282,3 | 3 251,5 | 1 962,55 | 3 763,10 |
| 2 | Granular subbase, km | 50 | 43,98 | 28,53 | 34,41 (2 direction.) |
| 3 | Base course, км | 50 | 43,98 | 27,567 | 33,45 (2 direction.) |
| 4 | Concrete pavement, км | 50 | 44,04 | 25,421 | 31,305 (2 direction.) |
| 5 | Bridges, pcs | 34 | 34 | 32 in progress | 32 in progress |
| 6 | Culverts, pcs | 120 | 52 | 20 in progress (41 installed.) | 20 in progress (109 installed.) |

3. Material procurement for 2016

| № | Description | Total as per Contract | Plan for 2016 | Actual work done to the current date | % | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone, base, thous.m3 | 421,09 | 206,08 | 160,36 | 78% | Own |
| 2 | Sand, thous.m3 | 227,03 | 86,27 | 75,77 | 88% | Own |
| 3 | SGM, thous.m3 | 954,12 | 266,94 | 309,14 | 116% | own |
| 4 | Cement, thous.tn | 144,06 | 92,83 | 59,44 | 64% | Own |
| 5 | R/C elements, thous.m3 | 43,01 | 15,03 | 7,40 | 49% | AZMK, ККК |

4. Attraction of personnel:

| № | description | Required for 2016 | Actual | Among them |
| --- | --- | --- | --- | --- |
|  |  |  |  | foreign | local |
| 1 | ИТР, АУП | 60 | 5 | 5 | - |
| 2 | Quality and control department | 5 | 17 | 4 | 13 |
| 3 | Machinery department | 15 | 30 | 10 | 20 |
| 4 | Survey | 8 | 17 | 6 | 11 |
| 5 | Technical department | 3 | 5 | 1 | 4 |
| 6 | Earthwork and artificial structures department | 5 | 25 | 5 | 20 |
| 7 | Administrative and financial department | 25 | 23 | 6 | 17 |
| 8 | Department for construction and assembly works on artificial structures | 20 | 27 | 7 | 20 |
| 9 | Road workers | 220 | 30 | 10 | 20 |
| 10 | Foremen | 10 | 7 | 5 | 2 |
| 11 | Equipment operators | 70 | 32 | 10 | 22 |
| 12 | Vehicles drivers | 30 | 26 | - | 26 |
| 13 | Dump track drivers | 70 | 85 | - | 85 |
| 14 | others | 40 | 34 | 4 | 30 |
| Total | 548 | 363 | 73 | 290 |

5. Mobilization of equipment:

| № | Description | Required for 2016 | Actual | Among them |
| --- | --- | --- | --- | --- |
|  |  |  |  | own | Subcon/rent |
| 1 | Bulldozer | 4 | 8 | 8 |  |
| 2 | Excavator | 11 | 10 | 10 |  |
| 3 | Loader | 12 | 8 | 8 |  |
| 4 | Grader | 4 | 8 | 8 |  |
| 5 | Roller | 12 | 11 | 11 |  |
| 6 | Dumper Trucks | 70 | 82 | 82 |  |
| 7 | Watering machine | 7 | 7 | 7 |  |
| 8 | Gas-tank truck |  | 4 | 4 |  |
| 9 | Asphalt Paver | 3 | 2 | 2 |  |
| 10 | Concrete Paver | 1 | - | - |  |
| 11 | Crane | 4 | 5 | 5 |  |
| 12 | Batching Plant | 2 | 3 | 3 |  |
| 13 | Crushing plant | 1 | 1 | 1 |  |
| 14 | Concrete Mixer | 4 | 6 | 6 |  |
| 15 | Manipulating equipment | 4 | 1 | 1 |  |
| 16 | Lowbed Trailer | 4 | 6 | 6 |  |
| 17 | Piling Machine | 1 | 2 | 2 |  |
| 18 | Vehicles | 34 | 130 | 130 |  |
| 19 | Other | 15 | 25 | 25 |  |
| Total | 193 | 319 | 319 |  |
| № | Description | Work type | Section from km to km | Notes |
| 1 | “ ElektroStar” and “Cellsystem” LLP | PTL Relocation | km 0-50 | Approved |

6. Subcontractors:

7. Pending issues:

| Pending issues | Way of solutions |
| --- | --- |
| Delay on execution of earthworks quantities | It is necessary to arrange double shift work and speed up work pace |