INFORMATION as of 01.09.2015

Construction (reconstruction) of Road “Almaty-Kokpek-Chunja-Koktal-Khorgos”  Lot 2

Contract : EWRP-50-111,7-ICB(W)-001/2013

Designer : « KazNIiPI«Dortrans  » LLP

Engineering Service:Dongsung/DongMyeong/Zhol-Sapa DDZ

General Contractor:  JV  Dogus Insaat&Gulsan Insaat Sanayi Turizm

Subcontractor: «Yug Asar », «Techstroyproduct », «Ew Intercomplex» LLP

Laboratory: Dogus Insaat&Gulsan Insaat Sanayi Turizm

Contract amount: 23 216  mln.tenge

Disbursement (earlier)  till 2015 : 7 859,68 mln.tenge

Disbursement  for 2015 :  17 050 mln.tenge

Construction period : 30 month

Construction starting date : 10.2014

Сompletion date: 04.2016

Brief information regarding the Project:

Source of funding: International Bank for Development and Reconstruction

Road division”:  Ib

Length:   61,7 km

Type of top pavement:   concrete

Thickness of road pavement: 76 cm

- Main

| Description | Total as per Contract | Plan for 2015 | Actual |
| --- | --- | --- | --- |
| Bridges and Cattlepasses | 18 | 18 | - |
| Overpasses | 4 | 4 | - |
| Interchanges | 4 | 4 | - |
| Culverts | 150 | 71 | 79 |
| Enclosed bus stops | 2 | 2 | - |

| № | Description | Total as per Contract | Performed in 2013-2014 | Plan for 2015 | Actual in 2015 | % |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks thous.m3 | 4508,62 | 1437,30 | 3438 | 1652,67 | 48,0 |
| 2 | Subbase, km | 62 | 6,86 | 47 | 37,3 | 79,3 |
| 3 | Base course Н – 18, km | 62 | 5,85 | 48 | 30,71 | 63,9 |
| 4 | Cement concrete pavement | 62 | 3.26 | 48 | 27,45 | 57,1 |

- Materials procurement

| № | Описание материала | Total as per Contract | Performed from the beginning of the construction | 2015 | Suppliers |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | plan | Actual | % |  |
| 1 | Crushed stone for base course, thous.m3 | 519,99 | 150,59 | 101,1 | 74,49 | 73,7 | own |
| 2 | Crushed stone for concrete, thous.m3 |  |  | 96,93 | 58,8 | 60,6 | - |
| 3 | Sand and gravel mix, thous.m3 | 1,178,2 | 1192,16 | 512,32 | 248,20 | 48,2 | - |
| 4 | Sand 0-5, thous.m3 | 280,35 | 82,76 | 138,64 | 89,91 | 64,5 | - |
| 5 | R/C elements, thous.m3 | 22,36 | 10,81 | 12,9 | 7,10 | 55,2 | AZMK |
| 6 | Cement thous.tn | 184,68 | 10,74 | 92,73 | 38,61 | 42,1 | Semei Cement |

- Mobilization of equipment:

| № | Descriptions | Required for 2015 | Actual | Among them |
| --- | --- | --- | --- | --- |
|  |  |  |  | Own | Subcont./rent |
| 1 | Bulldozer | 4 | 9 | 8 | 1 |
| 2 | Excavator | 12 | 21 | 20 | 1 |
| 3 | Loader | 11 | 18 | 17 | 1 |
| 4 | Grader | 5 | 9 | 9 |  |
| 5 | Roller | 14 | 24 | 22 | 2 |
| 6 | Dumper Trucks | 70 | 195 | 186 | 9 |
| 7 | Watering machine | 8 | 11 | 11 |  |
| 8 | Fuel – Oil Tank |  | 2 | 2 | 1 |
| 10 | Asphalt Paver | 3 | 4 | 4 |  |
| 11 | Concrete Paver | 1 | 2 | 2 |  |
| 13 | Crane | 4 | 10 | 10 |  |
| 14 | Batching Plant | 2 | 3 | 3 |  |
| 15 | Crushing Plant | 1 | 1 | 1 |  |
| 16 | Crushing Plant | 1 |  |  |  |
| 17 | Concrete mixer | 5 | 3 | 3 |  |
| 18 | Truck with Hoist | 4 | 1 | 1 |  |
| 19 | Lowbed Trailer | 4 | 7 | 7 |  |
| 20 | Piling machine or boring machine | 1 | 1 | 1 |  |
| 21 | Cars | 34 | 74 | 72 | 2 |
| 22 | Others | 15 | 19 | 19 |  |
|  | Total | 200 | 414 | 397 | 17 |

- Provision

| Description | As per tech. spec/contract | Actual |
| --- | --- | --- |
| Apartments | 10 | 10 |
| Cars | 6 | 6 |
| Office | 1 | 1 |
| Special clothing | 10 | 10 |

- Pending issues :

| Pending issues | Way of solutions |
| --- | --- |
| Delay of work on production schedule | Adequate organization and qualified specialists |
| Land acquisition (Shelek) | Speed up all documentation |
| Delay of work during the bridge constructions | Adequate organization and qualified specialists |