INFORMATION

Implementation of Western Europe –Western China Project

Almaty-Khorgos Roads, section km 111.7 – 171.1

Almaty Oblast, Lot 3

Contract : EWRP- 111,7- 171,1- ICB(W)-001/2013

Designer :  Kazdorproject LLP

Consultant:  Dongsung Engineering/Dongmeoung/ Zhol-Sapa LLP

General Contractor: Todini/Impregilo/Kazakhdorstroi JV

Subcontractors: AZMK Service LLP, Vesta Trans Service LLP, Zhanbota Trans Service LLP, Montazhnik LLP, Asia Energo Stroi LLP, Almaty Svyaz Stroi LLP, Temad LLP.

Laboratory:  Contractor’s property

Contractor’s Contract Amount: 14 683 716 863,20 KZT

Disbursed up to 2015: 5 282 003 841,65 KZT

Disbursement Plan 2015: 7 563 570 000 KZT

Construction time: 900 calendar days

Commencement date:  22.10.2013

Completion date: 07.04.2016

Summary of Project:

Source of financing:  World Bank

Road Category:  I b

Length 59,5 km

Type of upper layer of pavement: concrete (25cm)

Thickness of road pavement (76cm)

Executive documents:

Number of instructions 0 nos , letters 12 nos issued per week

Dead line of submission of Work Production Project, and Quality Control Plan - 07.04.2016 actual

(reason of delay)

- Basic

| Description | Total Contract | Plan 2015 г. | Actual as of date |
| --- | --- | --- | --- |
| Bridge |  |  |  |
| Cattle pass | 8 | 7 | 5 |
| Overpass |  |  |  |
| Interchange | 1 | 1 | 0,52 |
| Culverts | 57 | 45 | 41 |
| Bus shelter |  |  |  |
| Road Maintenance Facility |  |  |  |
| Overhead road | 6 | - | - |

| № | Description of works | Total Contract | Performed in 2013-2014 | Plan for 2015 | Actual 2015 | % |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks (thous m3) | 3785,47 | 3071,47 | 727,01 | 3765,51 | 99 |
| 2 | Concrete pavement, km | 59,5 | 0,35 | 44,00 | 19,8 | 33 |
| 3 | Base course, km | 59,5 | 4,33 | 55,1 | 21,65 | 36,4 |
| 4 | Subbase, km | 59,5 | 6,00 | 50,68 | 38,55 | 64,8 |

- Material Stockpile 2015:

| № | Description | Total Contract | 2015 | Suppliers |
| --- | --- | --- | --- | --- |
|  |  |  | Plan | Actual as of date | % |  |
| 1. | Crushed stone, thous cum | 691,41 | 540,02 | 380,34 | 70,43 | Todini |
| 2. | Sand, thous cum | 51,78 | 38,35 | 38,35 | 100 | Todini |
| 3. | SGM, thous cum | 607,86 | 514,53 | 514,53 | 100 | Todini |
| 4 | Cement, thous ton | 104,34 | 108,2 | 71,74 | 66,3 | Semei Cement |
| 5 | PC elements, thous cum | 3,45 | 1,71 | 1,74 | 50,4 | AZMK |

- Mobilization of Equipment:

| № | Description | Requirement 2015 | Actual as of date | Out of them |
| --- | --- | --- | --- | --- |
|  |  |  |  | own | Sucontractors’/rented |
| 1 | Bulldozer | 9 | 13 | 10 | 3 |
| 2 | Excavator | 13 | 16 | 8 | 8 |
| 3 | Loader | 12 | 19 | 11 | 8 |
| 4 | Grader | 6 | 10 | 3 | 7 |
| 5 | Roller | 15 | 17 | 5 | 12 |
| 6 | Dumper Trucks | 22 | 90 | 40 | 50 |
| 7 | Watering machine | 3 | 17 | 5 | 12 |
| 8 | Fuel – Oil Tank | 2 | 3 |  | 3 |
| 9 | Asphalt Paver | 4 | 3 | 3 |  |
| 10 | Concrete Paver | 1 | 1 | 1 |  |
| 11 | Milling machine |  | 1 | 1 |  |
| 12 | Crane | 6 | 9 | 5 | 4 |
| 13 | Bitumen spraying machine |  |  |  |  |
| 14 | Asphalt Plant |  |  |  |  |
| 15 | Batching plant |  | 2 | 2 |  |
| 16 | Crushing plant | 1 | 2 | 2 |  |
| 17 | Piling machine |  |  |  |  |
| 18 | Trawl | 5 | 10 | 7 | 3 |
| 19 | Concrete mixer | 3 | 3 | 1 | 2 |
| 20 | Others | 34 | 113 | 90 | 23 |
| TOTAL | 136 | 329 | 194 | 135 |