Information as of 23.01.2017

Regarding site implementation at 0-50 km, Project of Almaty- Khorgos Road, Section “International Transit Corridor ‘Western Europe-Western China” with JV «Dogus Insaat &Gulsan Isaat Sanayi Turizm», Lot 1

General Contractor –JV «Dogus Insaat &Gulsan Isaat Sanayi Turizm»

Contract– EWRP-0-50-ICB(W)-001/2013

Signing of contract – 17.07.2013

Construction period –November 2013 –  2016

Contract amount of General Contractor : 25 233 582 346,00 tenge

Disbursement (earlier) till  2016: 10 759 806 070,30 tenge

Disbursement  in 2016 :  5 272 791 970,78  tenge

Disbursement plan: 14 473 776 275,80 tenge

The Consultant – DongSung Engineering Co. Ltd. /Dong Myeong Engineering Consultants and Architecture Co. Ltd./ LLP Zhol Sapa

Designer – KazNIiPI  “Dotrans” LTD

- Project’s key results

| Section length, km | 50 |
| --- | --- |
| Culverts, nos | 120 |
| Bridges and overpasses, km | 30 |
| Overpasses, km | 1 |
| Transport junction, km | 3 |
| Earthworks thous.m3 | 5 282,3 |
| Subbase km.thous/m3 | 50/718,41 |
| Base course km/thous.m3 | 50/263,43 |
| Cement-concrete pavement km/thous.m3 | 50/275,84 |

2. Analysis of work schedule performance

| № | Description | Total as per Contract | Plan for 2016 | Actual for 2016-2017 | Performed from the beginning of the project |
| --- | --- | --- | --- | --- | --- |
| 1 | Concrete pavement, км | 50 | 44,04 | 44,04 | 50 (2 directions) |
| 2 | Base course, км | 50 | 43,98 | 43,98 | 50 (2 direc) |
| 3 | Granular subbase, km | 50 | 43,98 | 43,98 | 50 (2 direc) |
| 4 | Earthworks (thous.m3) | 927,85 | 732,89 | 402,89 | 597.85 |
| 5 | Asphalt (dividing strip), km | 50 | 50 | 48,82 | 1.18 |
| 6 | Guard rail, km | 134,13 | 128,13 | 46,200 | 52.200 |
| 7 | Road marking, km | 377,23 | 377,23 | 15,500 | 15.500 |
| 8 | Culverts, pcs | 120 | 76 | 76 | 120 |
| 9 | Bridges, pcs | 34 | 34 | 34 | 34 |

3. Material procurement for 2016

| № | Description | Total as per Contract | Plan for 2016 | Actual work done to the current date | % | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone, base, thous.m3 | 421,09 | 206,08 | 169,38 | 82% | Own |
| 2 | Sand, thous.m3 | 227,03 | 86,27 | 83,10 | 96% | Own |
| 3 | SGM, thous.m3 | 954,12 | 493,37 | 473,44 | 96% | own |
| 4 | Cement, thous.tn | 144,06 | 92,83 | 75,95 | 82% | Own |
| 5 | R/C elements, thous.m3 | 43,01 | 15,03 | 9,26 | 62% | AZMK, ККК |

4. Attraction of personnel:

| № | description | Required for 2016 | Actual | Among them |
| --- | --- | --- | --- | --- |
|  |  |  |  | foreign | local |
| 1 | ИТР, АУП | 60 | 5 | 5 | - |
| 2 | Quality Control Department | 5 | 17 | 4 | 13 |
| 3 | Machinery department | 15 | 30 | 10 | 20 |
| 4 | Survey | 8 | 17 | 6 | 11 |
| 5 | Technical Department | 3 | 5 | 1 | 4 |
| 6 | Department for earthworks and artificial structures | 5 | 25 | 5 | 20 |
| 7 | Administration and financing department | 25 | 15 | 4 | 14 |
| 8 | Department for construction and assembling works of artificial structures | 20 | 20 | 2 | 18 |
| 9 | Road workers | 220 | 10 | - | 10 |
| 10 | Foremen | 10 | 7 | 5 | 2 |
| 11 | Equipment operators | 70 | 32 | 10 | 22 |
| 12 | Vehicles drivers | 30 | 26 | - | 26 |
| 13 | Dump track drivers | 70 | 55 | - | 55 |
| 14 | others | 40 | 34 | 4 | 30 |
| Total | 548 | 306 | 66 | 240 |

5. Mobilization of equipment:

| № | Description | Required for 2016 | Actual | Among them |
| --- | --- | --- | --- | --- |
|  |  |  |  | own | Subcon/rent |
| 1 | Bulldozer | 4 | 8 | 8 |  |
| 2 | Excavator | 11 | 10 | 10 |  |
| 3 | Loader | 12 | 8 | 8 |  |
| 4 | Grader | 4 | 8 | 8 |  |
| 5 | Roller | 12 | 11 | 11 |  |
| 6 | Dumper Trucks | 70 | 55 | 55 |  |
| 7 | Watering machine | 7 | 2 | 2 |  |
| 8 | Fuel Tanker |  | 4 | 4 |  |
| 9 | Asphalt Paver | 3 | 2 | 2 |  |
| 10 | Concrete Paver | 1 | - | - |  |
| 11 | Crane | 4 | 5 | 5 |  |
| 12 | Batching Plant | 2 | 3 | 3 |  |
| 13 | Crushing plant | 1 | 1 | 1 |  |
| 14 | Concrete mixer | 4 | 6 | 6 |  |
| 15 | Manipulator | 4 | 1 | 1 |  |
| 16 | Lowbed Trailer | 4 | 2 | 2 |  |
| 17 | Piling Machine | 1 | - | - |  |
| 18 | Cars | 34 | 13 | 13 |  |
| 19 | Other | 15 | 10 | 10 |  |
| Total | 193 | 178 | 178 |  |
| № | Description | Work type | Section from km to km | Notes |
| 1 | “ ElektroStar” and “Cellsystem” LLP | PTL Relocation | km 0-50 | Approved |

6. Subcontractors: