Information

Regarding site implementation km 50-111, 7 of Almaty- Khorgos road, of the project ‘Western Europe-Western China” in Almaty region by JV «Dogus Insaat &Gulsan Isaat Sanayi Turizm», Lot 2

General Contractor:  JV  Dogus Insaat&Gulsan Insaat Sanayi Turizm

Contract: EWRP-50-111,7-ICB(W)-001/2013

Signing of contract: 17.07.2013г.

Contract amount- 23 216 954 457,00 tenge

Construction period : 30 month

Disbursement   in 2013 - 477 408 163,68 tenge

Disbursement   in 2014 -5 285 586 398.13 tenge

Disbursement   in 2015 -    6 492 428 052,58 tenge

Disbursement  for 2015 -17 050 280 000,00  tenge

Engineering Service:Dongsung/DongMyeong/Zhol-Sapa DDZ

Designer : « KazNIiPI«Dortrans  » LLP

- Project’s key results:

| Section length , km | 61,7 км |
| --- | --- |
| Culverts, nos | 150 |
| Bridges and Overpasses , nos | 18 |
| Earthworks , km/thous.m3 | 4520, |
| Sub base, km/thous.m3 | 61,7/1651,88 |
| Base course, km/thous.m3 | 61,7/1279,92 |
| Cement-concrete pavement , km/thous.m3 | 61,7/6552,67 |

- analysis of work schedule execution  :

| № | Works description | Total as per Contract | Plan for 2015 | Performed | Performed from the beginning of the project |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | In 2015 |  |
| 1. | Earthworks (thous m3) | 4520,00 | 3438,00 | 1801,54 | 3238,54 (1437) |
| 2. | Granular subbase, km | 62,00 | 47,0 | 44,21 | 51,07 (6,86) |
| 3. | Base course, км | 62,00 | 48,0 | 41,93 | 47,78 (5,85) |
| 4. | Concrete pavement, км | 62,00 | 48,0 | 42,43 | 45,69 (3,26) |
| 5. | Bridges, pcs | 18,00 | 18,00 | 70 | 104 |
| 6. | Culverts, pcs | 150,00 | 79,0 | 18 in progress | 18 in progress |

Notes

- Materials procurements for 2015:

| № | Description | Required | Plan for 2015 | Actual | % | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Crushed stone, base, thous.m3 | 519,99 | 101,10 | 82,54 | 81 | own |
| 2 | Crushed stone, pavement, thous.m3 |  | 96,29 | 47,34 | 87 | own |
| 2. | Sand, thous.m3 | 280,35 | 138,63 | 86,61 | 80 | own |
| 3. | SGM, thous.m3 | 1178,2 | 512,32 | 248,20 | 50 | own |
| 4. | Cement, thous.tn | 184,68 | 92,72 | 35,61 | 70 | Semei |
| 5. | R/C elements, thous.m3 | 22,36 | 12,9 | 6,9 | 87 | АЗМК,ККК |
| 6. | Rebar (anchor) tn. | 210,0 | 171,12 | 18,1 | 11 | ТОО”VILLAR Kazakhstan” |
| 7. | Rebar (dowel) tn | 1000,0 | 819,28 | 72,3 | 9 | ТОО”VILLAR Kazakhstan” |

Notes:

- Mobilization of equipment:

| № | Description | Required for 2015 | Actual | Among them |
| --- | --- | --- | --- | --- |
|  |  |  |  | own | subconrt./rent |
| 1 | Bulldozer | 4 | 5 | 5 |  |
| 2 | Excavator | 12 | 8 | 8 |  |
| 3 | Loader | 11 | 8 | 8 |  |
| 4 | Grader | 5 | 5 | 5 |  |
| 5 | Roller | 14 | 11 | 11 |  |
| 6 | Dumper Trucks | 70 | 43 | 43 |  |
| 7 | Watering machine | 8 | 11 | 11 |  |
| 8 | Fuel – Oil Tank | 1 | 2 | 2 |  |
| 9 | Asphalt Paver | 3 | 4 | 4 |  |
| 10 | Concrete Paver | 1 | 2 | 2 |  |
| 11 | Crane | 4 | 4 | 4 |  |
| 12 | Batching Plant | 3 | 3 | 3 |  |
| 13 | Crushing plant | 2 | 1 | 1 |  |
| 14 | Piling Machine | 1 | 1 | 1 |  |
| 15 | Lowbed Trailer | 4 | 7 | 7 |  |
| 16 | Concrete mixer | 5 | 3 | 3 |  |
| 17 | Cars | 14 | 34 | 34 |  |
| 18 | Others | 37 | 7 | 7 |  |
| TOTAL | 199 | 159 | 159 |  |

5  Attraction of personnel :

| № | Description | Required for 2015 | Actual | Among them |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign | local |
| 1 | ИТР | 3 | 6 | 6 |  |
| 2 | Laboratory | 5 | 17 | 4 | 13 |
| 3 | Survey | 10 | 19 | 7 | 12 |
| 4 | Equipment operators | 70 | 131 | 16 | 115 |
| 5 | Dump track drivers | 70 | 43 |  | 43 |
| 6 | Road workers | 283 | 40 |  | 40 |
| 7 | Service staff | 112 | 148 | 97 | 51 |
| Total | 553 | 404 | 130 | 274 |

- Subcontractors:

| № | Description | Work types | Section from kmto km | Notes |
| --- | --- | --- | --- | --- |
| 1 | ТОО " Yug Asar" | Communication | 50-112 | Approved |
| 2 | ТОО»Elektrostart» | Electric works | 50-112 | Approved |
| 3 | ТОО»Demirok» | Electric works | 50-112 | Approved |
| 4 | ТОО»Sell Sistem» | Electric works | 50-112 | Approved |

- Pending issues :

| № | Pending Issues on Lot2 | Ways of solutions |
| --- | --- | --- |
| 1 | Relocation of communication cable Beeline and OL “KTJ” | Speed up the approval |
| 2 | Relocation of communication | Adequate organization and qualified specialists |
| 3 | Crossing with gas pipe line | Speed up and solve pending issues |
| 4 | Lacks of design and estimate documentation | Correction and speed up the approval |