INFORMATION

Reconstruction of International Transit Corridor

“Western Europe – Western China”

km774-806(LOT 2) in South Kazakhstan Oblast

as on 15.04.2015

General Contractor – «EVRASCON» JSC Euro-Asian Construction Corporation (Azerbaijan)

Contract EBRD/CW-02/2013 (22/08/2014)

Cost of the Contract – 12 585 798 659,48 tenge

Advance payment amount – 1 887 869 798,91 tenge (28/12/2014)

SCS –«KazDorNII»  in association with «KAzNIIPI» Dortrans KHA

Completion period – 18 months (540 days)

Designer – “SK Engineering” LLP

- Basic indicators of the project

| Length of the section (km) | 32 |
| --- | --- |
| Culverts, incl.: (nos) - cattle pass | 101 10 |
| Transport interchange in two levels(nos) | 2 |
| Bridges, underpasses, agricultural machinery pass (nos) | 2/2/5 |
| Earthworks (ths. m3) | 697,57 |
| GSM С-4 for sub base thick. Н=35cm(ths. m3) | 566,90 |
| CSGSM С-6 reinfor. 7% cement for base coarse thick. Н=20cm(ths. m3) | 176,86 |
| Cement concrete pavement Btb-4,8 – strength in bending; B-35 strength in compression thick. Н=27cm(ths. m3) | 157,64 |
| Bus pavilions / Bus stops / Underground pedestrian crossing 4mх45,73m (nos) | 10/10/1 |
| Rest area with ramp(nos) | 1 |

- Laboratory:

Laboratory of the Contractor will be established in the Camp at km 780 (RHS) and will be equipped with all necessary equipment and instruments. The equipment ordered: Supplier «Ариант» JSC, Barnaul city, Russian Federation. Date of delivery - April 2015. Laboratory building left from Turkey and till April 30, is expected to arrive at the construction  site

- Camp

On the territory of the Camp (12 hectares at km 780) there is a two-floor house for the Contractor’s office and housing for employees of the company, the preparation for concreting of the foundation for office and living buildings are being carried out. The canteen for foreign and local personnel is working.Office for Engineer was provided  in village Zhibek Zholly. There is hostel is completed  for 160 person.

- Surveying works:

Leveling line is completed; new executive survey was carried out; the working drawings for road are completed – 15 km.   km 6  (774-806)  transferred  to the Engineering Services

- Information on the completed works:

| Name of the works | Unit | Total under Contract | Plen for 2015 | Performed from the beginning of the year | Remaining |
| --- | --- | --- | --- | --- | --- |
| Earthworks | ths. m3 | 697,57 | 512,57 | 0 | 697,57 |
| Sub base | km | 32 | 18 | 0 | 32 |
| Base (CSCSM) | km | 32 | 18 | 0 | 32 |
| C/c pavement | km | 26,49 | 16 | 0 | 26,49 |
| Culverts | nos | 101 | 52 | 0 | 101 |
| Bridges and underpasses | nos | 9 | 6 | 0 | 6 |

- Procurement of main road-building materials

| Name of materials | Units | Total under the contract | Plan for 2015 | Prepared from the beginning of the year | Remining |
| --- | --- | --- | --- | --- | --- |
| Crushed stone | thous. m3 | 176,86 | 104,18 | 3,2 | 173,66 |
| SGM | thous. m3 | 566,90 | 333,95 | 2,8 | 564,10 |
| Sand | thous. m3 | 74,80 | 45,67 | 0,8 | 74,72 |
| Concrete goods | thous. m3 | 6,45 | 3,88 | 0,32 | 6,13 |
| Concrete | thous. m3 | 67,80 | 41,60 | 0,006 | 67,794 |

- Personnel:

| № | Name | Requirement for 2015 | The fact that the current date | Personnel |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign | Local |
| 1 | ИТР, АУП | 13 | 13 | 10 | 3 |
| 2 | Laboratory | 5 | 1 |  | 1 |
| 3 | Surveying | 20 | 9 | 2 | 7 |
| 4 | Operators of special tehn. | 43 | 14 | 6 | 8 |
| 5 | Drivers of trucks | 180 | 12 |  | 12 |
| 6 | Road workers | 40 | 18 |  | 18 |
| 7 | Other | 80 | 48 | 8 | 40 |
| Total | 386 | 115 | 26 | 89 |

- Mobilization of equipment:

| № | Name | Requirement for 2015 | The fact that the current date | % | Note |
| --- | --- | --- | --- | --- | --- |
| 1 | Bulldozer | 3 | 1 | 33,3 |  |
| 2 | Excavator | 12 | 4 | 25,0 |  |
| 3 | Loader | 8 | 2 | 12,5 |  |
| 4 | Grader | 5 | 3 | 60,0 |  |
| 5 | Roller | 9 | 2 | 22,2 |  |
| 6 | Dump | 90 | 5 | 5,5 |  |
| 7 | Water carrier | 6 | 2 | 33,3 |  |
| 8 | Asphalt paver | 2 | 0 | 0,0 |  |
| 9 | Concrete paver | 1 | 1 | 100,0 |  |
| 10 | Truck crane | 7 | 2 | 28,6 |  |
| 11 | CCP | 2 | 1 | 50,0 |  |
| 12 | SCM | 2 | 0 | 0,0 |  |
| 13 | Piling machine | 2 | 0 | 0,0 |  |
| 14 | Thrall | 2 | 2 | 100,0 |  |
| 15 | Concrete mixer (mixer) | 5 | 2 | 40,0 |  |
| 16 | Vehicles | 16 | 14 | 87,5 |  |
| 17 | Other | 62 | 13 | 20,6 |  |
| 18 | Milling | 1 | 0 |  |  |
| Total | 235 | 58 | 24,68 |  |

- Subcontractor organization:

| № | Name | Type of work | Note |
| --- | --- | --- | --- |
| 1 | LLP «Dani-ER» | Reconstruction of the main gas pipeline | Submitted for approval |
| 2 | LLP «Shyrak-LKS» | Reconstruction of line | Approved |
| 3 | LLP «КазTsEP» | Relocation and reconstruction of power lines, Reconstruction of the pipeline medium and high pressure | Approved |
| 4 | LLP «Energoteploproekt» | Reconstruction of the pipeline medium and high pressure | Is being carried out negotiation process |

Suppliers of road construction materials:

- There is being carried out negotiations on registration of suppliers of building and inert materials

Problematic issues:

- Obtaining permission for quarrying and inert materials

- There are not  acquisition of  5 land

Project Manager                                   Gadjiev N.G.