# Work progress information

Western Europe – Western China International Transit Corridor reconstruction project km1702-km 1752 (LOT №7) in Kyzylorda region.

length 49 km.

# Contractor:  «Evrascon»

# Engineer:     «Kazdorproject» LLP

New Contract amount:  8 233 648 569,50 KZT;

Disbursement – 3 804 913 425,57 KZT.

Incl. advance payment of 5% for mobilization – 407 240 645 KZT.

Remaining works –4 428 735 143,93 KZT;

Subcontractors: General Contractor has concluded the Contract with Subcontractor KREC JSC for PTL-35 kV relocation in Kyzylorda region.

Base at the section PK196  (ACP, CCP and Laboratory).

Work program performance                                               		   	 02.09.2015

| № | Work description | Total under Contract | Actual from beginning of construction | Remaining work as of 02.09.15 | Actual performed from the beginning of the year | Delay /advance from the work program, in days | Performance |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks, km | 49 | 49,0 | 0,0 | 6,50 | 0 | 100% |
| 2 | Subbase, km | 49 | 49,0 | 0,0 | 6,59 | 0 | 100% |
| 3 | Lower layer of the base course С-4, km | 49 | 49,0 | 0,0 | 7,57 | 0 | 100% |
| 4 | Binding course 12 cm, km | 49 | 49,0 | 0,0 | 7,84 | 0 | 100% |
| 5 | Wearing course 10 cm, km | 49 | 49,0 | 0,0 | 7,8 | 0 | 100% |
| 6 | Top layer of crushed stone mastic asphalt concrete, km | 49 | 14,4 | 34,6 | 14,4 | -81 | 29% |
| 7 | Culverts, pcs. | 45 | 42,4 | 2,6 | 3,2 | -46 | 94% |
| 8 | Bridges, pcs. | 13 | 10,59 | 2,41 | 1,2 | -60 | 80% |
| 9 | Shoulder protection С6, km | 49 | 0,0 | 0,0 | 0,0 | -93 | 0% |
| 10 | Intersection and junction construction, rest area with wearing course Н=10 cm, pcs | 32 | 11 | 21 | 10 | -85 | 34% |
| 11 | Guardrails, m | 45 656 | 0,0 | 45 656 | 0,0 | -45 | 0% |
| 12 | Rad marking, r.m | 229 680 | 0,0 | 229 680 | 0,0 | -51 | 0% |
| 13 | Sand depot | 1 | 0,0 | 1 | 0,0 | -43 | 0% |

Material procurement:

| Material procurement | Plan for 2015 | Actual stockpiled as of 0209.2015 | Delay/advance from work program, in days | Performed % taking into account laid |
| --- | --- | --- | --- | --- |
| 1 | Бутовый камень для заготовки щебня тыс./тонн | 258,623 | 40,150 | 0 |  |
| 2 | Щебень тыс./тонн |  | 15,413 | -64 | 86% |
| 3 | ПГС тыс./тонн | 240,250 | 79,386 | -86 | 61% |
| 4 | Отсев тыс./тонн | 54,080 | 3,200 | -77 | 57% |
| 5 | Битум тыс./тонн | 8,105 | 0,575 | -95 | 99% |
| 6 | Материал для ЩМА |  |
|  | Отсев тыс./тонн | 8 539 | 4 890 | -23 | 88% |
|  | Щебень 5/10 тыс./тонн | 8 539 | 2560 | -60 | 68% |
|  | Щебень 10/20 тыс./тонн | 44 506 | 3 211 | -120 | 35% |
|  | Мин. порошок тыс./тонн | 6 875 | 150 | -121 | 30% |
|  | Стаб. Добавка тыс./тонн | 289 | 33 | -120 | 34% |

# Количество техники, необходимое  для выполнения программы работ на 2015 год.

| Name | Requiremetn for July 2015 | As of 02.09.2015 |
| --- | --- | --- |
|  |  | Actual available as of 02.09.2015 | Additional requirement |
| Бульдозер / Bulldozer | 3 | 2 | 1 |
| Экскаватор / Excavator | 9 | 4 | 5 |
| АВЗ/ ACP | 2 | 1 | 1 |
| Бетонный завод/ Concrete plant | 1 | 1 |  |
| ДСУ/RCA | 2 | 2 |  |
| Погрузчик / Loader | 4 | 3 | 1 |
| Автогрейдер / Grader | 4 | 3 | 1 |
| Фреза / Milling machine | 0 | 0 |  |
| Катки / Rollers | 5 | 5 |  |
| Асфальтовый каток/Asphalt compactor | 10 | 6 | 4 |
| Асфальтоукладчик / Asphalt paver | 5 | 4 | 1 |
| Автосамосвалы / Dump trucks | 31 | 102 |  |
| Автогудронатор / Bitumen distributor | 1 | 1 |  |
| Битумовоз / Bitumen truck | 4 | 3 | 1 |
| Поливочная машина / Water truck | 6 | 3 | 3 |
| Бензовоз / Gas tank truck | 2 | 2 |  |
| Кран / Crane | 3 | 3 |  |
| тралл / Trailer | 1 | 1 |  |
| миксеры для бетона / Concrete mixer | 4 | 4 |  |
| Цементовоз/Cement truck | 2 | 1 |  |
| Разметочная машина / Measuring machine | 1 | 0 |  |
| Total | 101 | 152 | 18 |

# Personnel:

| Personnel | Lot №7 | % |
| --- | --- | --- |
|  | Plan | Actual |  |
| Total personnel for July 2015. | 303 | 410 | 100 |

# Issues of concern and reasons occuring at this section:

- Partial disorder of mobilized road-building machinery and equipment (crusher, ACP);

- Insufficient quantity of qualified personnel;

- Partial lack of fuel, stabilizer for CSMA;

- Absence of concluded contract for supply of geogrid, biomat, mineral powder, guardrails;

- Unresolved issue of road-building materials from the former Contractor "Impresa".

- Lack of funds for work performance.