INFORMATION

On the “Western Europe-Western China”

International transit corridor Reconstruction Project

km 774-806 (LOT 2) in South-Kazakhstan Region

on the 13.03.2017

General Contractor –  «EVRASCON» JSC Evro-Asian Construction Corporation (Azerbaijan)

Contract EBRD/CW-02/2013 (22/08/2014)

Contract price – 12 585 798 659,48 tenge

Amount of advance  – 1 887 869 798,91 tenge (28/12/2014)

Construction Supervision Consultant –«KazDorNII» in association with «KazNiiPI»  Dortrans and KHA

Time for Completion – 18 months (540 days)

Project Designer – SK «Engineering» LLP

- Main aspects of the project:

| Section length (km) | 32 |
| --- | --- |
| Culverts, including: (nos) - on the main road - on the ramps | 96 35 61 |
| Traffic interchange in two levels (nos) | 2 |
| Bridges, overpasses, driveways for agricultural machinery (nos) | 3/2/5 |
| Earthworks (thous. m3) | 697,58 |
| Gravel and sand mix С-4 for subbase with thickness Н=35cm(thous. m3) | 566,90 |
| Crushed stone base course С-6 treated with cement 7%, thickness Н=20cm(thous. m3) | 176,86 |
| Concrete pavement type Btb-4,8 – bending tensile strength; B-35 compression strength; thickness Н=27cm(thous. m3) | 157,64 |
| Bus shelters / Stopping points / Pedestrian underpass 4mх45,73m (nos) | 10/10/2 |
| Rest area with repair trestle (nos) | 1 |

- Laboratory:

The laboratory is located at the production base km 780 (right side).

- Production base (12 he. at km 780, right side):

All the buildings as follows: office, canteen, laboratory, dormitories for engineering staff and labors are being operated

Concrete batching plant with production capacity 180 m3/hour produces concrete for cement-concrete pavement and equipped with cement silos of total capacity 650 tons. The second Concrete batching plant with production capacity 120 m3/hour produces mix for CCSM (7%) and equipped with cement silos of total capacity 450 tons. The Asphalt concrete plant "Lintek" is also mounted with a production capacity 300 ton / hour. On production base the concrete goods are issued (beams and culvert links)

- Information on executed works as:

| No | Works | Unit | on Contract | Actual on 2015 | Actual on 2016 | Plan on 2017 | Executed from 2016 beginning | Executed from construction beginning | % of execution | balance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks | m3 | 697,57 | 285,420 | 230,78 | 181,37 | 2,40 | 518,60 | 74% | 178,97 |
|  |  | km | 57,97 | 5,94 | 34,75 | 17,28 | 0,40 | 41,09 | 71% | 16,88 |
| 2 | Subgrade | km | 57,97 | 1,74 | 36,42 | 19,83 | 0,20 | 38,36 | 66% | 19,63 |
| 3 | Crushed stone base | km | 57,97 | 0,60 | 37,01 | 20,36 | 0 | 37,61 | 65% | 20,36 |
| 4 | Concrete pavement | km | 49,81 | 0,00 | 29,75 | 20,06 | 0 | 29,75 | 60% | 20,06 |
| 5 | Culverts | nos | 96 | 3 | 32,8 | 60,20 | 8,50 | 44,30 | 46% | 51,70 |
| 6 | Bridges | nos | 3,00 | 0,00 | 2,15 | 0,85 | 0,30 | 2,45 | 82% | 0,55 |
| 7 | Overpasses | nos | 2,00 | 0,00 | 1,60 | 0,40 | 0,15 | 1,75 | 88% | 0,25 |
| 8 | Agricultural machinery passes | nos | 5,00 | 0,00 | 3,95 | 1,05 | 0,15 | 4,10 | 82% | 0,90 |
| 9 | Milling | km | 57,97 | 14,50 | 24,30 | 19,17 | 13,62 | 52,42 | 90% | 5,55 |
| 10 | Dismantling of lean concrete | km | 57,97 | 13,20 | 25,60 | 11,35 | 0 | 46,62 | 80% | 11,35 |

- Financial Disbursement.

| Total on Contract | Disbursed in 2015 | Disbursed in 2016 | Disbursement Total | % disbursement |
| --- | --- | --- | --- | --- |
| 12 585,82 mill. t-ge | 699,47 | 7059,28 | 7758,75 | 62 |

- Main road-construction materials procurement as :

| No | Works | Unit of measure | Plan on Contract | Actual on 2015 | Actual on 2016 | Plan on 2017 | Accumulative fact | % of execution |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone | thous.m3 | 433,92 | 20,116 | 239,854 | 173,95 | 265,833 | 61% |
| 2 | Sand and gravel mix | thous.m3 | 566,83 | 115,00 | 253,43 | 198,4 | 373,71 | 66% |
| 3 | Sand | thous.m3 | 138,812 | 4,28 | 80,32 | 54,21 | 85,87 | 62% |
| 4 | Cement | thous.ton | 98,809 | 1,909 | 58,86 | 38,04 | 61,751 | 62% |
| 5 | Reinforced concrete goods | thous.m3 | 6,45 | 1,253 | 4,237 | 0,96 | 5,487 | 85% |

- Personnel:

| No. | Description | Plan | Foreign | Local | Total |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | SKR | RK |  |
| 1 | Administration | 12 | 4 |  |  | 4 |
| 2 | Engineering and administrative personnel | 15 | 9 | 2 |  | 11 |
| 3 | Surveyor | 5 | 5 | 3 | 1 | 9 |
| 4 | Surveyor Assistant | 10 |  | 5 |  | 5 |
| 5 | Laboratory Assistant | 4 | 1 | 1 | 1 | 3 |
| 6 | Laboratory Engineer | 5 | 0 | 2 | 2 | 4 |
| 7 | Laboratory Workers | 8 | 0 | 2 |  | 2 |
| 8 | Mechanical Engineer | 4 | 1 |  |  | 1 |
| 9 | Mechanic | 17 | 3 | 21 |  | 24 |
| 10 | Mechanical Assistant | 8 | 4 | 11 |  | 15 |
| 11 | Drivers and operators | 320 | 40 | 41 |  | 81 |
| 12 | Road Worker | 152 | 13 | 221 |  | 234 |
| 13 | Support personnel | 173 | 48 | 80 |  | 128 |
| 14 | Office manager | 40 | 2 | 15 |  | 17 |
| 15 | Office Workers | 8 |  | 15 | 1 | 16 |
|  | Total | 781 | 130 | 419 | 5 | 554 |

(The actual number on February 21, 2017 amounts to 251 people)

- Equipment mobilization:

| No. | Name | Plan on month | Own/subcontract | Rent | On repair | Total (on object) | % |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Bulldozer | 6 | 4/3 | 1 | 4 | 4 | 66% |
| 2 | Excavator | 18 | 14/7 |  | 3 | 18 | 100% |
| 3 | Loader | 10 | 7/4 | 1 | 2 | 10 | 100% |
| 4 | Dump truck | 110 | 90/32 |  | 47 | 75 | 68% |
| 5 | Water tank | 10 | 4 |  | 1 | 3 | 30% |
| 6 | Fuel tank | 3 | 3 |  |  | 3 | 100% |
| 7 | Grader | 7 | 7/3 |  | 2 | 8 | 114% |
| 8 | Roller | 16 | 12/7 |  | 3 | 16 | 100% |
| 9 | Concrete batching plant | 1 | 1 |  |  | 1 | 100% |
| 10 | Crushing plant | 1 | 1 |  |  | 1 | 100% |
| 11 | Concrete paver | 2 | 1 |  |  | 1 | 50% |
| 12 | CSCM paver | 2 | 1 |  |  | 1 | 50% |
| 13 | Crane | 10 | 6 | 2 |  | 8 | 80% |
| 14 | Trailer | 4 | 2 |  |  | 2 | 50% |
| 15 | Milling machine | 2 | 2 |  |  | 1 | 50% |
| 16 | Light vehicles | 18 | 18 | 2 |  | 20 | 111% |
| 17 | Crushing screening plant | 1 | 1 |  |  | 1 | 100% |
| 18 | Asphalt batching plant | 1 | 1 |  |  | 1 | 100% |
| 19 | Others | 76 | 29 |  | 5 | 24 | 32% |
|  | TOTAL | 298 | 204/56 | 6 | 67 | 195 | 65% |

- LLP "Accord-Kazakhstan SDI» performs work on the section PK 694 + 00 + 844 ÷ 00 (10 km) on the R.H.S. of the road. All performed work shows as separate table.

- Subcontract Organizations:

LLP "Shyrak-LKS» has finished work on the transfer of communication lines.

LLP "Corporation Bereke A" works on the construction of asphalt pavement in the village of Zhibek Zholy.

LLP "Mary Company" has finished works on installation of traffic lights.

LLP "Atom BG" performs construction of fences on parking lots № 4-4, № 2-2 and installation of canopies on parking lots № 4-4, № 2-2. At this time, completed the construction of toilets in the parking lots, the remaining work on the electricity and water supply.

LLP "UPK Adhesiya" has finished work on the transfer of the gas pipeline of high, low and medium pressure.

LLP "KazTsep" performed the transfer of power lines (10 and 0.4 kW).

- Material suppliers:

| No. | Material | Supplier | Note |  |
| --- | --- | --- | --- | --- |
| 1 | Crushed stone | LLP "Taza Astyk" IP "Tulametov" | for pavement | approved approved |
|  |  | LLP "Nygmet Kum" | for base course | approved |
| 2 | Sand Gravel Mix | LLP "Nygmet LTD", LLP "Kaz Tas" | for sub base | approved |
| 3 | Sand | LLP "Sairam Trans" | for pavement | approved |
| 4 | Cement | LLP "Standard Cement" | for pavement | approved |
|  |  | LLP "Standard Cement" | for base course | approved |
| 5 | Film (geomembrane) | LLP "Kurylys Polymer" | for pavement | approved |
| 6 | Dowel bar | LLP "Kor.Metall Service" | for pavement | approved |
| 7 | Anchor bar | Com. "EVRASCON" | for pavement | approved |
| 8 | Concrete goods for bridges | Com. "EVRASCON" | for artificial constructions | approved |
| 9 | Concrete goods for culverts and tubings | Com. "EVRASCON" | for artificial constructions | approved |