INFORMATION

East-West Roads Project Western Europe-Western China International Transit Corridor (CAREC 1B), Reconstruction (construction) of road “ALMATY-KOKPEK-CHUNJA-KOKTAL-KHORGOS”

- Contract – EWRP-Bridges and overpasses on lot V and VI -ICB(W)-001/2013

- Contractor –JV “Evrascon & MO-1”

- Contract amount – 6 803 041 924 tg

- Construction period– 30 month

Commencement date: 11th October 2013

Time for completion: 10th April 2016

- Money developed up to 2014 - 2 220 586 800,02 tg

- Money development plan for 2015– 3 874 133 000 tg

- Consultant Engineer– «Dongsung Engineering/Dongmyeng Engineering» / «Zhol-Sapa»LLP

- Design Company – “Kazakhstan zholdary”

22.09.2015

- Main indicators

Total: 30 bridges & Khorgos dam protection

| Description | Quantity | Description | Quantity |
| --- | --- | --- | --- |
| Bridges | 14 | Overpasses | 3 |
| Cattle crosses | 9 | Interchanges | 4 |

- Details of works performance according to schedule:

| № | Description | Evrascon | MO-1 | Total |
| --- | --- | --- | --- | --- |
| 1 | Bridges | Started | 17 | 11 | 28 |
|  |  | On progress | 12 | 1 | 13 |
|  |  | Suspended | 5 | 10 | 15 |
|  |  | Remained | 1 (663) | 1 (385) | 2 |
| 2 | Dam protection | Retaining wall | - | 216 m | 216 m/216 m |
|  |  | Sheet piles | - | 70 m | 70 m/70 m |
|  |  | Slope protection | - | 103 m | 103 m/1,036 m |

  - Progress

| № | Description | Total on Contract | Developed in 2013-2014 | Plan for 01.06.2015 (mln. tg) | Performed according to Contract |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Plan | As of date | % | Sum | % |
| 1. | Monetary progress, tg | 6 803 | 2 220 | 3 874 | 892 | 23 | 3 092 | 45 |

  - Bridge works

| № | Works description | Total on contract | Performed in 2013-2014г | 2015 | % |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Plan | As of date |  |
| 1 | Earthworks, m3 | 256 573 | 11 139 | 245 434 | 10 507,4 | 4,3 |
| 2 | Pile driving, m3 | 5 460 | 2 518 | 2 942 | 1 888 | 64 |
| 3 | Installation of foundation, m3 | 14 272 | 4 433 | 9 839 | 3 381 | 34 |
| 4 | Installation of columns and cross bars (wall) | 10 896 | 2 544 | 8 352 | 1 723 | 21 |
| 5 | Installation of rubber bearings | 3 432 | 140 | 3 292 | 424 | 13 |
| 6 | Installation of span slabs, un. | 968 | 106 | 542 | 52 | 10 |
| 7 | Installation of span beams, un. | 572 | 20 | 872 | 200 | 23 |
| 8 | Installation of handrails | 3 024 | 0 | 3 024 | 0 | 0 |
| 9 | Installation of guard rails | 11 064 | 0 | 11 064 | 0 | 0 |

- Materials procurement for 2015:

| № | Description | Total on contract | 2015 | Suppliers |
| --- | --- | --- | --- | --- |
|  |  |  | Plan | As of date | % |  |
| 1. | Aggregate,thous. m3 | 50,9 | 28,9 | 19,5 | 68 | “Dostar-S” |
| 2. | Sand, thous. m3 | 14,9 | 6,8 | 5,8 | 86 | “Dostar-S” |
| 3. | Sand (mixed), thous. m3 | 21,7 | 11,2 | 8,4 | 75 | “Dostar-S” |
| 4. | Cement, thous. m3 | 30,5 | 18,0 | 5,0 | 28 | “Bukhtarma” |
| 5. | Concrete products, thous. m3 | 26,6 | 16,0 | 6,32 | 37 | Production base of Evrascon/MO-1 |
| 6. | Re-bar and embedded parts, ton | 3 767 | 3 157 | 1150,5 | 36 | “Mechel” |

- Staff mobilization:

| № | Description | Requirement for 2015 | As of date |  |
| --- | --- | --- | --- | --- |
|  |  |  |  | foreign | local |
| 1 | Engineers | 65 | 62 | 21 | 41 |
| 2 | Lab. | 10 | 7 | 2 | 5 |
| 3 | Survey | 10 | 7 | 3 | 4 |
| 4 | Operators | 60 | 50 | 10 | 40 |
| 5 | Dump trucks drivers | 70 | 66 | 1 | 65 |
| 6 | Labors | 200 | 92 | 25 | 67 |
| 7 | Assembler, mounters | 70 | 34 | 4 | 30 |
| 8 | Others | 100 | 39 | 4 | 35 |
| Total | 585 | 357 | 70 | 287 |

- Equipment mobilization:

| № | Description | Requirement for 2015 | As of date | JV “Evrascon&MO-1” |
| --- | --- | --- | --- | --- |
|  |  |  |  | Evrascon | МО-1 |
| 1 | Dozer | 5 | 1 | 1 | 0 |
| 2 | Excavator | 5 | 2 | 2 | 0 |
| 3 | Loader | 5 | 1 | 1 | 0 |
| 4 | Grader | 3 | 1 | 1 | 0 |
| 5 | Roller | 5 | 1 | 2 | 0 |
| 6 | Dump trucks | 15 | 8 | 8 | 0 |
| 7 | Water tank | 3 | 2 | 2 | 0 |
| 8 | Asphalt paver | 2 | 0 | 0 | 0 |
| 9 | Crane | 10 | 5 | 4 | 0 |
| 10 | Cement concrete plant | 3 | 2 | 1 | 1 |
| 11 | Pile driver | 5 | 2 | 2 | 0 |
| 12 | Trail | 5 | 2 | 1 | 0 |
| 13 | Mixer | 10 | 3 | 2 | 1 |
| 14 | Vehicles | 25 | 12 | 10 | 2 |
| 15 | Other | 10 | 12 | 10 | 2 |
| Total | 111 | 54 | 48 | 6 |